## WS-A Data Analytics_V2
Level | Description | Work Type | Action | Output → To | Depends On
Better Proxy, Better History length , Better Data Quality to meet regulatory and modellability expectation
Deliverable | Foundation 1: Establish Proxy Enhancement & Proxy BAU Governance Framework — Principles, Methodologies, Assesment, and Proxy BAU Control
Output Summary | Outputs: Proxy principles paper · Asset-class methodologies · Proxy registry with full lineage · Validated proxy assignments (G/Y/R) · BAU proxy management process
Goal | This deliverable establishes the proxy framework first (rules ), then implements per asset class, then operationalises. Every proxy in production must be traceable back to this framework.
Define proxy principles, develop asset-class proxy methodologies, build a full-lineage proxy ,validate proxy assignments using G/Y/R status, and implement a sustainable BAU process for proxy ownership, review, remediation, and governance.
Milestone | M1 — Define Proxy Principles & Governance Framework |  |  | Formal proxy methodology paper
Task | Define proxy acceptability criteria and quantitative thresholds and metrics | Risk Development | Develop | Acceptability rules → M2 | RA: co-develop
Subtask | Collaborate with RA to define proximity requirements (same asset class, currency, sector, risk type), basis risk tolerance, and conditions that trigger NMRF reclassification | Risk Development | Collaborate |  | RA
Subtask | Collaborate with RA to define quantitative thresholds: correlation floor, volatility ratio band, tracking error ceiling, test requirements | Risk Development | Develop |  | RA
Subtask | Collaborate with RA to define stress-period validation: test over GFC, COVID, 2022 rates — stress-specific pass/fail thresholds | Risk Development | Develop |  | RA
Subtask | Collaborate with RA and MRO to define the NMRF boundary: what threshold separates "proxied but modellable" from "proxy too weak, must be NMRF" — direct capital implications | Cross-Team | Collaborate |  | Capital Tech: SES impact
Task | Define proxy hierarchy, lifecycle, and governance rules | Risk Development | Develop | Lifecycle rules → M2 | RA
Subtask | Establish hierarchy: direct observation > same-issuer different tenor > same-sector peer > sector/rating index > broad benchmark > cross-asset — document when each level is acceptable | Risk Development | Develop |  | RA
Subtask | Define lifecycle: assign (new RF, no history) → upgrade (direct data becomes available) → challenge (metrics breach) → retire/NMRF (no fix) — with capital impact assessment at each decision | Risk Development | Develop |  | Capital Tech
Subtask | Define override rules: when can a lower-hierarchy proxy be selected over a higher one (e.g., stress-period behaviour)? Define approval workflow for overrides | Governance | Develop |  | Risk Model: governance
Task | Document formal proxy methodology documents | Risk Development | Develop | Methodology paper → MRM validation | RA + Risk Model
Subtask | Produce standalone regulatory deliverable: acceptability criteria, thresholds, hierarchy, lifecycle, stress-period testing, override governance, NMRF escalation | Risk Development | Develop
Subtask | Submit it to MRO for review as they will be involved in the BAU and approval process | Cross-Team
Subtask | Submit to Model Risk Management (MRM) for independent intitial validation — address potential challenges | Model Validation | Collaborate | MRM sign-off | MRM / Risk Model
M1 Output → Formal proxy principles: validated by MRM, accepted as the governing framework for all proxy assignments in M2
Milestone | M2 — Develop & Implement Proxy Methodologies Per Asset Class |  |  | Proxy registry with full lineage | Requires M1 principles
Task | Develop asset-class-specific proxy methodologies with RA | Risk Development | Develop | Proxy methods per AC | RA: co-develop
Subtask | IR: collaborate with RA to develop tenor interpolation/extrapolation, curve-to-curve proxying, cross-currency basis, inflation — implement in Python, validate against known benchmarks | Risk Development | Develop |  | RA
Subtask | FX: collaborate with RA to develop EM pegged-currency handling, vol surface proxying — implement and validate against direct observations where available | Risk Development | Develop |  | RA
Subtask | Credit: collaborate with RA to develop issuer-to-sector, single-name to index, CDS-bond basis, — handle credit event contamination | Risk Development | Develop |  | RA
Subtask | Equity: collaborate with RA to develop single-name to sector/index, dividend proxying, vol surface proxying — handle corporate actions (splits, mergers, delistings) | Risk Development | Develop |  | RA
Subtask | Commodity: collaborate with RA to develop location basis — implement with calendar-mismatch handling ( Argus vs WTI) | Risk Development | Develop |  | RA
Task | Run proxy assignment and validation across all RFs requiring proxying | Data Analytics | Analyze | Validated assignments | RA: expert review
Subtask | Per RF: identify candidate proxies per hierarchy, compute validation metrics (correlation, vol ratio, tracking error, cointegration), rank by quality, select best | Data Analytics | Analyze
Subtask | Run stress-period validation: compute metrics separately over GFC, COVID, 2022 — document how each proxy behaved during each stress | Data Analytics | Analyze
Subtask | Classify each proxy: green (all pass), yellow (marginal in stress — acceptable with justification), red (fails — must remediate, upgrade, or escalate to NMRF) | Data Analytics | Classify |  | RA
Subtask | Red proxies: investigate alternatives with RA; if no fix, escalate to NMRF with capital impact quantification — collaborate with Capital Tech for SES estimate | Cross-Team | Collaborate | NMRF escalations → Capital | RA + Capital Tech
Task | Produce proxy registry with full lineage | Data Analytics | Develop | Proxy registry → ES, Regulatory
Subtask | Per proxy: original RF → proxy RF → time series → source → effective dates → splice methodology → validation metrics ( + stress) → justification narrative | Data Analytics | Develop
Subtask | Produce proxy concentration risk analysis: desks/ACs where large proportion of ES is driven by proxy relationships | Data Analytics | Analyze | Concentration report → Mgmt
Subtask | Quantify capital impact: per red/yellow proxy, ES difference between proxy vs. direct data vs. NMRF — drives investment decisions | Data Analytics | Analyze | Capital impact → Mgmt | Capital Tech
Task | Document asset-class proxy methodologies for MRM validation | Risk Development | Develop | AC methodology papers → MRM | RA
Subtask | Per asset class: formal methodology paper (proxy types, selection algorithm, validation criteria, stress testing, edge cases, limitations) | Risk Development | Develop
Subtask | Submit to MROs and Model Validation for independent validation — sample proxy , methodology challenge | Cross-Team | Collaborate | MRM sign-off | MRM
M2 Output → Proxy registry with full lineage, validation metrics, quality classification, capital impact — MRM-validated methodology per asset class
Milestone | M3 — BAU Proxy Management |  |  | Proxy BAU process + tools | Requires M2 registry
Task | Build proxy monitoring tools | Data Analytics | Develop | Monitoring tools → BAU ops
Subtask | Build automated proxy drift detection: monthly refresh of validation metrics, alert when proxy breaches correlation/tracking-error thresholds | Data Analytics | Develop
Subtask | Build proxy age tracker: flag proxies in place beyond review cycle without re-validation | Data Analytics | Develop
Subtask | Work with Tech to deploy monitoring tools into production with dashboard and alerting | Tech Collab | Collaborate | Production dashboard | Risk Tech: deployment
Task | Establish BAU proxy governance process | Cross-Team | Develop | BAU process doc
Subtask | Monthly: refresh validation metrics, flag drifting proxies, investigate and remediate | Governance | Develop
Subtask | Quarterly: full proxy coverage reconciliation, quality distribution review, concentration risk update | Governance | Develop
Subtask | Annual: deep audit — full lineage review, stress-period re-validation, regulatory exam prep | Governance | Develop
Subtask | Promotion path: proxy → direct when vendor data becomes available — with capital impact assessment and cutover plan | Governance | Develop |  | Capital Tech
Subtask | Roles:Risk Quant (methodology, validation), MRO( Oversight), Risk Tech (tools, monitoring), Risk Model (governance sign-off), Market Data (vendor management), Capital Tech (impact runs) | Governance | Develop
Subtask | Document BAU process: runbooks, escalation matrices, SLA definitions | Governance | Develop | BAU manual
M3 Output → Governed proxy BAU: monitoring tools in production, monthly/quarterly/annual cadence, documented and audit-ready
Deliverable | Foundation 2: Build Advanced Data Quality Tools for both AdHoc historical assessment and ongoing checks in Prod
Output Summary | Outputs: 4-tier DQ methodology · DQ scoring engine · Early warning system · Production dashboard with alerting · BAU monitoring process
Sequence | M4 (methodology with RA) → M5 (PoC + validation) → M6 (work with Tech to productionise) → M7 (BAU)
Milestone | M4 — Build Advanced DQ Check Methodologies |  |  | DQ framework methodology
Design the intelligence layer — not just "is data missing?" but "is this data behaving consistently with its peers, its own history, and what the market is doing?" Context-aware, not just rule-based.
Task | Collaborate with RA to develop Tier 1 — Deterministic checks | Data Analytics | Develop | Tier 1 rules → engine | RA: co-develop
Subtask | Missing data detection: gap counts, consecutive gap length, weekend/holiday calendar validation per market | Risk Development | Develop |  | RA
Subtask | Stale price flagging: unchanged value for N business days (configurable per asset class), with low-vol exceptions | Risk Development | Develop |  | RA
Subtask | Extreme outlier detection: absolute thresholds (negative prices, rates outside plausible range) + relative thresholds (N-sigma daily return) | Risk Development | Develop |  | RA
Task | Collaborate with RA to develop Tier 2 — Advanced statistical checks | Data Analytics | Develop | Tier 2 rules → engine | RA: co-develop
Subtask | Volatility regime shift detection: EWMA vs. historical vol divergence, CUSUM/Bai-Perron structural break tests | Risk Development | Develop |  | RA
Subtask | Distribution shift tests: KS-test, Anderson-Darling against rolling baseline — detect series whose return distribution has changed vs. peers | Risk Development | Develop |  | RA
Subtask | Autocorrelation anomaly detection: sudden appearance/disappearance of serial correlation (may indicate stale pricing or interpolation artefacts) | Risk Development | Develop |  | RA
Task | Collaborate with RA to develop Tier 3 — Peer-group & benchmarking checks | Data Analytics | Develop | Tier 3 rules → engine | RA: co-develop
Subtask | Cross-RF correlation monitoring: detect correlation breakdowns between historically correlated RFs (e.g., 5Y and 10Y swap rates) | Risk Development | Develop |  | RA
Subtask | Sector-vs-name divergence: single names moving dramatically vs. sector peers — genuine event or data error? | Risk Development | Develop |  | RA
Subtask | Basis relationship monitoring: CDS-bond basis, swap spread, cross-currency basis — detect when basis moves outside historical norms | Risk Development | Develop |  | RA
Subtask | Proxy tracking drift: monitor proxied RFs vs. their proxies — detect divergence beyond tolerance from proxy framework (Deliverable 1) | Risk Development | Develop |  | RA
Task | Collaborate with RA to develop Tier 4 — ML-based intelligent triage to reduce false positive | Data Analytics | Develop | ML model spec → PoC | RA: co-develop
Subtask | Train XGBoost (or similar) classifier on historical DQ alert data — labelled by resolution outcome (genuine issue vs. false positive) — using Tier 1-3 features as inputs | Risk Development | Develop |  | RA
Subtask | Design model output: severity score, routing recommendation (auto-resolve / analyst queue / immediate escalation), explainability (which inputs drove classification) | Risk Development | Develop |  | RA
Subtask | Define model governance: quarterly retraining, performance monitoring (precision/recall), degradation alerting | Risk Development | Develop |  | RA + Risk Model
Task | Collaborate with RA to estimate VaR and Capital Attribution | Data Analytics | Develop | Impact model → scoring | RA + Capital Tech
Subtask | For each DQ alert, estimate: can this cause PLA failure? Backtesting exception? ES instability? — so remediation is prioritised by capital materiality, not just data severity | Data Analytics | Analyze |  | RA
Subtask | Define severity tiers: Critical (capital misstatement risk → SLA), High (could escalate), Medium (batch remediation), Low (informational) | Risk Development | Develop |  | RA
M4 Output → 4-tier DQ methodology: deterministic, advanced statistical, peer-group context-aware, ML intelligent triage — with downstream capital impact linkage
Milestone | M5 — Build DQ PoC & Validate |  |  | Validated DQ scoring engine | Requires M4 methodology
Task | Build DQ PoC in Python | Data Analytics | Build PoC | PoC results → demo
Subtask | Implement all Tier 1-3 checks with configurable thresholds per asset class and RF type | Data Analytics | Build PoC
Subtask | Implement composite scoring engine: aggregate into per-RF quality score with drill-down | Data Analytics | Build PoC
Subtask | Implement alert generation and routing: generate alerts per severity, route to queue | Data Analytics | Build PoC
Subtask | Build unit tests: inject synthetic deficiencies (gaps, outliers, stale prices, correlation breaks) — confirm correct detection and scoring | Data Analytics | Analyze
Task | Validate PoC against real data | Data Analytics | Analyze | Validation report | RA: expert review
Subtask | Run across all RF time series — compare DQ scores against expert assessment | Data Analytics | Analyze |  | RA
Subtask | Backtest ML triage: precision/recall against historical DQ incidents | Data Analytics | Analyze |  | RA
Subtask | Demo to stakeholders: show detection accuracy, false positive rate, alert routing, capital impact linkage | Cross-Team | Collaborate | Sign-off → Tech build | Risk Model + Capital Tech
M5 Output → Validated DQ PoC with stakeholder sign-off — ready for productionisation
Milestone | M6 — Work with Tech to Productionise DQ Framework |  |  | Production DQ engine + dashboard | Requires M5 PoC sign-off
Task | Specify production requirements to Tech | Data Analytics | Develop | Production spec → Risk Tech
Subtask | Scheduling spec: daily refresh after market data ingestion, compute requirements, database for scores and alert history | Data Analytics | Develop
Subtask | Dashboard spec: per-RF quality scores, asset-class/desk aggregations, trend views, alert queue management, drill-down | Data Analytics | Develop
Subtask | API spec: downstream consumers (ES engine, PLA, backtesting) can query DQ status per RF | Data Analytics | Develop
Task | Work with Tech to build and deploy production DQ engine | Tech Build | Build (Tech) | Production DQ engine | Risk Tech builds
Subtask | Tech builds: scoring engine, alert generation, dashboard, API — per Quant specification | Tech Build | Build (Tech) |  | Risk Tech builds
Subtask | Validate Tech's implementation: run full DQ assessment, compare against PoC, confirm scoring consistency and alert accuracy | Data Analytics | Analyze | Validation report
Task | Work with Tech to deploy ML triage model in production | Tech Collab | Collaborate | ML model in production | Risk Tech builds
Subtask | Specify model deployment requirements: daily scoring, automated routing, confidence thresholds, retraining pipeline | Data Analytics | Develop
Subtask | Tech deploys; Quant validates production model output against PoC baseline | Tech Build | Build (Tech) |  | Risk Tech
M6 Output → Production DQ engine: 4-tier assessment, ML triage, dashboard, alerting — built by Tech, specified and validated by Quant
Milestone | M7 — BAU DQ Monitoring & Early Warning |  |  | BAU DQ process | After M6 production
Task | Establish BAU DQ operating model | Governance | Develop | BAU process doc
Subtask | Daily: exception review, analyst assignment, resolution SLA per severity tier | Governance | Develop
Subtask | Monthly: DQ governance report, trend analysis, ML model performance review | Governance | Develop
Subtask | Quarterly: ML model retraining, threshold recalibration, framework effectiveness review | Governance | Develop |  | RA
Subtask | Roles: Quant Data (methodology, thresholds), Risk Tech (infrastructure, SLA), Risk Model (governance), Market Data (vendor escalation) | Governance | Develop
Subtask | Document: runbooks, escalation matrices, SLA definitions | Governance | Develop | BAU manual
M7 Output → Governed DQ BAU: daily monitoring, early warning, ML triage, documented and audit-ready
Deliverable | Foundation 3: Data Quality Remediation Methodologies
Output Summary | Outputs: Approved remediation methods (interpolation, adjustments, overrides, special computation) · Event calendar · BAU process for applying historical treatments
Sequence | M8 (methodology with RA) → M9 (work with Tech to build tools) → M10 (BAU process)
Milestone | M8 — Develop Approved Remediation Methodologies |  |  | Remediation methodology paper
Task | Collaborate with RA to develop gap-filling methodologies per asset class | Data Analytics | Develop | Gap-fill rules → tools | RA: co-develop
Subtask | Single-day gaps: linear interpolation (rates), last-known-good carry-forward (prices) | Risk Development | Develop |  | RA
Subtask | Multi-day gaps: cubic spline (curves/surfaces), vol-surface arbitrage-free interpolation | Risk Development | Develop |  | RA
Subtask | Extended gaps: carry-forward with decay, proxy-based filling, or flag-and-exclude | Risk Development | Develop |  | RA
Task | Collaborate with RA to develop outlier treatment methodologies | Risk Development | Develop | Outlier rules → tools | RA: co-develop
Subtask | Detection: Z-score, IQR fencing, Hampel filter (MAD-based), market-event-aware overrides | Risk Development | Develop |  | RA
Subtask | Treatment options: winsorisation, nearest-neighbour replacement, interpolation, flag-and-retain | Risk Development | Develop |  | RA
Subtask | Build event calendar: registry of stress events, corporate actions, index reconstitutions, benchmark transitions — observations during these are tail risk, not outliers | Data Analytics | Develop | Event calendar → DQ engine | RA + FO
Task | Collaborate with RA to develop special computation / adjustment methodologies | Risk Development | Develop | Adjustment methods → tools | RA: co-develop
Subtask | Override rules: when manual correction is justified, approval workflow, documentation requirements | Risk Development | Develop |  | RA + Risk Model
Subtask | Special computation: derived RF reconstruction, cross-source reconciliation, redenomination adjustment | Risk Development | Develop |  | RA
Task | Validate that remediation preserves tail risk properties ( ex: outlier treatment does not remove genuine stress) | Cross-Team | Analyze | Validation report → MRM | RA
Subtask | Compare ES with pre- and post-remediation data — confirm gap-filling doesn't suppress tails, outlier treatment doesn't remove genuine stress | Data Analytics | Analyze |  | Capital Tech: ES runs
Subtask | Submit remediation methodology paper to MRM and MRO for feedback | Cross-Team | Collaborate | MRM sign-off | MRM
M8 Output → MRM-validated remediation methodologies: gap-fill, outlier treatment, adjustments, overrides, event calendar
Milestone | M9 — Work with Tech to Build Remediation Tools |  |  | Production remediation pipeline | Requires M8 methodology
Task | Specify remediation tool requirements to Tech | Data Analytics | Develop | Tool spec → Risk Tech
Subtask | Automated remediation pipeline: detect DQ issue (from Deliverable 2) → apply approved method → log before/after → produce audit trail | Data Analytics | Develop
Subtask | Manual override interface: analyst reviews, selects treatment, provides justification — all logged with timestamp and approver | Data Analytics | Develop
Task | Work with Tech to build and deploy remediation pipeline | Tech Build | Build (Tech) | Production pipeline | Risk Tech builds
Subtask | Tech builds automated pipeline + manual override interface per Quant specification | Tech Build | Build (Tech) |  | Risk Tech builds
Subtask | Validate Tech's implementation: run remediation on known test cases, verify audit trail completeness | Data Analytics | Analyze
M9 Output → Production remediation tools: automated pipeline + manual override — built by Tech, validated by Quant
Milestone | M10 — BAU Process for Historical Data Treatment |  |  | BAU remediation process | After M9 tools
Task | Establish BAU process, policies, and procedures for applying historical treatments | Governance | Develop | BAU policy doc
Subtask | Define when automated remediation applies vs. when manual review is required | Governance | Develop
Subtask | Define approval workflow: who can approve overrides, what documentation is needed, escalation for material corrections | Governance | Develop |  | Risk Model
Subtask | Define capital impact assessment requirement: any remediation that changes ES by more than threshold requires pre-deployment sign-off | Governance | Develop |  | Capital Tech
Subtask | Document: policies, procedures, runbooks, audit trail requirements | Governance | Develop | BAU policy manual
M10 Output → Governed BAU remediation: automated + manual, approval workflows, capital-aware, documented
Deliverable | Foundation 4: Risk Factor Onboarding & Rederivation Process
Output Summary | Outputs: End-to-end RF onboarding process (vendor → methodology → proxy → prod build → VaR impact → backtesting → NTE/TSV → sign-off → production) · Documented lifecycle for every new RF
Sequence | M11 is the end-to-end process — each step is sequential within a single RF onboarding, but multiple RFs can be onboarded in parallel
Milestone | M11 — Establish End-to-End RF Onboarding Process |  |  | Onboarding process + completed RF builds
This is a repeatable process — every new RF (from WS-A Cat 2/5 gap register, or from future model changes) follows this pipeline. Build the process once, execute many times.
Task | Internal or Vendor assessment & selection for new RF data | Data Analytics | Gather | Vendor recommendation
Subtask | Assess available vendor sources for the new RF: coverage, history depth, quality, cost | Sourcing | Analyze
Subtask | Select vendor and negotiate data licensing — coordinate with Procurement | Sourcing | Collaborate |  | Business + Procurement
Task | Vendor onboarding & data ingestion | Data Analytics | Collaborate | Data feed live | Risk Tech: ingestion
Subtask | Work with Tech to build ingestion connector for new vendor/feed — parsing, validation, storage | Tech Collab | Collaborate |  | Risk Tech builds
Subtask | Validate ingested data: completeness, format, reconcile against vendor-provided benchmarks | Data Analytics | Analyze
Task | Develop RF methodology: how to build history | Risk Development | Develop | RF history methodology | RA: co-develop
Subtask | Collaborate with RA to define derivation methodology: direct observation, model-implied, interpolated, constructed from components | Risk Development | Develop |  | RA
Subtask | Collaborate with RA to define backfill strategy to 2007: vendor sourcing, curve reconstruction, or proxy extension | Risk Development | Develop |  | RA
Task | Develop RF methodology: how to generate ongoing | Risk Development | Develop | RF generation methodology | RA + FO Quant Strat
Subtask | Collaborate with RA and FO Quant Strat to define daily generation logic: source MDOs, transformation steps, shift type, carry treatment | Risk Development | Develop |  | RA + FO Quant Strat
Task | Build proxy (if direct history insufficient) | Data Analytics | Analyze | Proxy assignment
Subtask | Apply proxy framework (Deliverable 1): identify candidate, validate, classify, produce lineage record | Data Analytics | Analyze |  | Proxy framework from D1
Task | Work with Tech to build RF in production (history + ongoing generation + proxy + mapping ) | Data Analytics | Build (Tech) | RF in production | Risk Tech builds
Subtask | Work with Tech to implement historical time series (direct + backfill + proxy splice) in production data warehouse | Tech Collab | Collaborate |  | Risk Tech builds
Subtask | Work with Tech to implement daily generation logic in RF generation pipeline | Tech Collab | Collaborate |  | Risk Tech builds
Subtask | Validate production output: compare against methodology PoC, confirm history and daily generation are correct | Data Analytics | Analyze
Task | Assess VaR / ES impact of new RF | Cross-Team | Analyze | VaR impact report | Capital Tech: ES runs
Subtask | Run ES with and without the new RF — quantify desk-level and firm-level capital impact | Data Analytics | Analyze |  | Capital Tech
Task | Assess backtesting impact | Cross-Team | Analyze | Backtesting report
Subtask | Run backtesting with new RF included — does exception count change? Do clustering patterns shift? | Data Analytics | Analyze
Task | Produce NTE / TSV documentation | Risk Development | Develop | NTE/TSV → Risk Model | Risk Model
Subtask | Prepare New Trade Event (NTE) or Time Series Validation (TSV) documentation per internal governance requirements | Risk Development | Develop
Subtask | Submit to Risk Model / MRM for review and approval | Model Validation | Collaborate | MRM approval | MRM
Task | Obtain sign-off for production deployment | Cross-Team | Collaborate | Production sign-off | Senior Mgmt
Subtask | Present VaR impact, backtesting results, NTE/TSV approval — obtain sign-off from Risk Model, Capital, and senior management | Cross-Team | Collaborate
Task | Deploy to production and confirm consumption | Tech Collab | Collaborate | RF live in production | Risk Tech
Subtask | Work with Tech to activate the new RF in ES/VaR engines, confirm PLA includes it, confirm backtesting picks it up | Tech Collab | Collaborate |  | Risk Tech + Capital Tech
Subtask | Post-deployment monitoring: two weeks of daily validation that the new RF behaves as expected in production | Data Analytics | Analyze
M11 Output → End-to-end RF onboarding process: repeatable pipeline from vendor to production, with full governance gate at each step
Deliverable | Deliverable 5: Carry Removal
Output Summary | Outputs: Carry applicability assessment · Three-scenario methodology · Decision tree · Impact analysis · Production implementation (daily + historical)
Sequence | M12 (methodology with RA) → M13 (PoC + impact) → M14 (work with Tech for production) → M15 (BAU)
Milestone | M12 — Assess Carry & Build Methodology |  |  | Carry methodology + decision tree
Task | Assess carry applicability per RF type | Risk Development | Analyze | Applicability assessment | RA: co-develop
Subtask | Collaborate with RA to determine which RF types have material carry: IR rates (roll-down), IR/FX/EQ vols (time decay), commodity (contango/backwardation), equity (dividends) | Risk Development | Analyze |  | RA
Subtask | Quantify carry magnitude per RF type: what fraction of daily/10-day returns is carry vs. genuine market moves? Analyze across benign and stress periods | Data Analytics | Analyze
Subtask | Collaborate with RA to build carry applicability decision tree: map each RF type to appropriate scenario based on data availability and carry mechanism | Risk Development | Develop | Decision tree | RA
Task | Develop carry stripping methodologies with RA and nuances of 1day vs 10 days | Risk Development | Develop | Three-scenario methodology | RA: co-develop
Subtask | Scenario A — Curve interpolation carry removal: collaborate with RA to use full curve snapshots to interpolate aged-tenor rate and subtract carry directly — implement in Python | Risk Development | Develop |  | RA
Subtask | Scenario B — Black-Scholes √T theta approximation: collaborate with RA for vol surface time decay estimation — implement in Python, validate against FO theta | Risk Development | Develop |  | RA + FO: theta comparison
Subtask | Scenario C — Rolling median statistical estimator: collaborate with RA for equity/commodity fallback — implement in Python with configurable window | Risk Development | Develop |  | RA
Subtask | Collaborate with RA on 10-day carry: sum ten daily carry values (not naive 10× scaling) to capture intraperiod curve shape changes | Risk Development | Develop |  | RA
Subtask | Collaborate with RA on regime-conditioned adaptive windowing for Scenario C: shorter windows during stress using CDX IG regime signal | Risk Development | Develop |  | RA
M12 Output → Three-scenario carry methodology with decision tree, 10-day aggregation, regime conditioning — developed with RA
Milestone | M13 — Build PoC & Assess Impact |  |  | Validated PoC + impact analysis + methodology paper | Requires M12
Task | Build carry removal PoC in Python | Data Analytics | Build PoC | PoC results → demo
Subtask | Implement all three scenarios end-to-end on representative RFs per asset class | Data Analytics | Build PoC
Subtask | Validate against known carry decompositions from Front Office — confirm methodology produces sensible carry estimates | FO Collaboration | Analyze |  | FO: carry decomposition
Task | Assess impact on downstream outputs | Data Analytics | Analyze | Impact report → Mgmt | Capital Tech: ES runs
Subtask | Impact on return distributions: does carry removal eliminate systematic drift? Does it change tail shape? | Data Analytics | Analyze
Subtask | Impact on PLA: re-run Spearman/KS-distance with carry-adjusted returns — quantify improvement per desk | Data Analytics | Analyze |  | PLA team
Subtask | Impact on ES: compare current and stress period ES with/without carry stripping — quantify capital delta | Data Analytics | Analyze |  | Capital Tech
Task | Document carry methodology documents | Risk Development | Develop | Methodology paper → MRM | RA
Subtask | Produce formal methodology paper: regulatory motivation, three scenarios, decision tree, 10-day aggregation, regime conditioning, impact analysis | Risk Development | Develop
Subtask | Submit to MRM for independent validation — address challenges, obtain sign-off | Model Validation | Collaborate | MRM sign-off | MRM
M13 Output → Validated carry PoC + impact analysis + MRM-approved methodology paper
Milestone | M14 — Work with Tech to Implement Carry in Production |  |  | Carry-adjusted returns in production | Requires M13 + Tech resources
Task | Work with Tech to implement carry removal in daily RF generation | Tech Collab | Collaborate | Daily carry pipeline | Risk Tech builds
Subtask | Specify to Tech: integrate decision tree into daily pipeline, apply assigned scenario per RF, compute carry-adjusted 1-day and 10-day returns alongside raw | Data Analytics | Develop | Pipeline spec → Tech
Subtask | Specify to Tech: store both raw and carry-adjusted, implement regime-conditioned window for Scenario C | Data Analytics | Develop
Subtask | Tech builds daily carry pipeline; Quant validates: parallel run for 1+ month against PoC output | Tech Build | Build (Tech) |  | Risk Tech builds
Task | Work with Tech to apply carry removal to full historical time series | Tech Collab | Collaborate | Historical carry-adjusted series | Risk Tech builds
Subtask | Specify to Tech: run carry stripping retrospectively across all carry-applicable RFs, handle periods where Scenario A data is incomplete (fallback to C) | Data Analytics | Develop
Subtask | Tech builds historical backfill pipeline; Quant validates consistency across full history | Tech Build | Build (Tech) |  | Risk Tech builds
Task | Run capital impact and obtain sign-off | Cross-Team | Collaborate | Sign-off → production | Capital Tech + Senior Mgmt
Subtask | Run ES with raw vs. carry-adjusted across current + stress periods — produce capital impact report | Data Analytics | Analyze | Capital impact report | Capital Tech
Subtask | Obtain senior management sign-off; deploy carry-adjusted series to production with audit trail | Cross-Team | Collaborate | Production deployment | Senior Mgmt
M14 Output → Carry-adjusted returns in daily production + full historical backfill, validated, signed off, audit-trailed
Deliverable | Deliverable 6: History Assessment & Strengthening ( not in production yet)
Output Summary | Outputs: History inventory register · Assessment (good vs. bad) · Remediation options analysis · Strengthening & extension methodology · Extended histories to 2007
Sequence | M15 (assess) → M16 (decide good/bad) → M17 (develop methodology with RA for bad) → M18 (work with Tech to execute) → M19 (BAU)
Milestone | M15 — Assess History, Data Lineage & Proxy Coverage |  |  | History inventory register
Task | Catalog all historical time series and their lineage | Data Analytics | Gather | History inventory → M16 | Risk Tech: system access
Subtask | Per RF: source system, start date, end date, frequency, gap count, derivation chain, proxy flag, transition status | Data Analytics | Gather
Subtask | Assess coverage vs. 2007 stress lookback — quantify gap per RF, identify missing stress periods | Data Analytics | Analyze
Subtask | Audit existing proxy relationships: document proxy, splice, justification — classify green/yellow/red | Data Analytics | Classify
Subtask | Catalog benchmark transitions: LIBOR→SOFR, EONIA→€STR, CDOR→CORRA — status per RF | Data Analytics | Analyze
Subtask | Catalog structural breaks: EM rebasings, corporate actions, index reconstitutions | Data Analytics | Analyze
Task | Produce History and Proxy Inventory | Data Analytics | Analyze | Register → all teams
Subtask | One row per RF: source, coverage, gaps, derivation, proxy details, transitions, readiness (G/Y/R) | Data Analytics | Develop
Subtask | Summary analytics: coverage heatmap, proxy concentration, transition readiness, top-priority remediation targets | Data Analytics | Analyze |  | RA: ES materiality
M15 Output → History inventory register — the single view of what exists, what's missing, and what's broken
Milestone | M16 — Decide: Good vs. Bad — Assess Remediation Options |  |  | Decision register + remediation plan | Requires M15
Task | Classify each RF history as Good or Bad | Data Analytics | Classify | Classification → M17
Subtask | Good: sufficient depth (to 2007), acceptable quality (DQ green/yellow), direct data or validated proxy, benchmark transitions handled — no action needed | Data Analytics | Classify
Subtask | Bad: insufficient depth, poor quality (DQ red), unvalidated proxy, unhandled transitions, proxy chains — requires remediation | Data Analytics | Classify
Task | For each "Bad" RF, assess remediation options | Data Analytics | Analyze | Remediation options → M17 | RA
Subtask | Option A — Source: vendor data exists but hasn't been procured — assess cost, timeline, quality | Data Analytics | Analyze
Subtask | Option B — Construct: data can be derived from available raw data (constant-maturity rolling, vintage reconstruction, cross-source derivation) | Data Analytics | Analyze |  | RA: feasibility
Subtask | Option C — Proxy: no direct or constructible data — assign proxy per Deliverable 1 framework | Data Analytics | Analyze |  | Proxy framework from D1
Subtask | Option D — Accept gap: document that history cannot be extended, flag for regulatory discussion, quantify ES impact of truncated stress window | Data Analytics | Analyze |  | Capital Tech: ES impact
Subtask | Per RF: recommend option, estimate effort, quantify capital impact of each option vs. status quo — prioritise by net capital benefit | Data Analytics | Analyze | Prioritised remediation plan
M16 Output → Per-RF decision (good/bad), recommended remediation option, prioritised by capital impact
Milestone | M17 — Develop Data Strengthening & History Extension Methodology |  |  | Extension methodologies → Tech | Requires M16 decisions
Task | Collaborate with RA to develop construction methodologies | Risk Development | Develop | Construction methods | RA: co-develop
Subtask | Constant-maturity rolling curve construction: for IR and commodity RFs from archived raw curve snapshots | Risk Development | Develop |  | RA
Subtask | Vintage curve reconstruction: rebuild historical curves from available node points using current bootstrap methodology | Risk Development | Develop |  | RA
Subtask | Cross-source derivation: construct RF from combinations of other available data (implied vol from options, credit spread from bond yield minus swap) | Risk Development | Develop |  | RA
Task | Collaborate with RA to develop benchmark transition methodologies | Risk Development | Develop | Transition methods → Tech | RA + FO Models
Subtask | LIBOR→SOFR: direct splice with spread adjustment, reconstructed SOFR backcast (ISDA spreads), or hybrid — validate consistency with FO pricing | Risk Development | Develop |  | RA + FO Models
Subtask | EONIA→€STR, CDOR→CORRA: apply same framework per currency | Risk Development | Develop |  | RA
Subtask | Validate no artificial jumps at splice points — inspect return distributions, confirm ES not dominated by transition-day artefact | Data Analytics | Analyze
Task | Validate all methodologies | Model Validation | Collaborate | MRM sign-off | MRM
Subtask | Confirm constructed/extended histories preserve tail behaviour, vol clustering, cross-asset correlation | Data Analytics | Analyze | Validation report
Subtask | Submit methodology paper to MRM — obtain sign-off | Model Validation | Collaborate |  | MRM
M17 Output → MRM-validated construction and transition methodologies — ready for Tech execution
Milestone | M18 — Work with Tech to Execute History Extension |  |  | Extended histories in production | Requires M17 + vendor data from sourcing
Task | Work with Tech to ingest sourced historical backfill data | Tech Collab | Collaborate | Sourced data ingested | Risk Tech builds
Subtask | Coordinate with Tech to ingest vendor historical archives; validate against benchmarks at splice points | Tech Collab | Collaborate |  | Risk Tech
Task | Work with Tech to implement construction methodologies in production | Tech Build | Build (Tech) | Constructed histories | Risk Tech builds
Subtask | Tech implements constant-maturity rolling, vintage reconstruction, cross-source derivation per Quant specification — with configurable parameters and audit trail | Tech Build | Build (Tech) |  | Risk Tech builds
Subtask | Validate Tech's output: compare against methodology PoC, confirm statistical properties preserved | Data Analytics | Analyze
Task | Work with Tech to implement benchmark transition adjustments | Tech Build | Build (Tech) | Transition-adjusted histories | Risk Tech builds
Subtask | Tech implements LIBOR→SOFR and other transitions per Quant specification; Quant validates splice points | Tech Build | Build (Tech) |  | Risk Tech builds
Task | Run capital impact and obtain sign-off | Cross-Team | Collaborate | Sign-off → production | Capital Tech + Senior Mgmt
Subtask | Run ES with old vs. new (extended) data — stress period sensitivity, capital delta decomposition | Data Analytics | Analyze | Capital impact report | Capital Tech
Subtask | Obtain sign-off; deploy extended histories to production | Cross-Team | Collaborate |  | Senior Mgmt
M18 Output → All in-scope RFs extended to 2007, benchmark transitions handled, deployed to production with audit trail
Milestone | M19 — BAU History Maintenance & Ongoing Assessment |  |  | BAU history process | After M18
Task | Establish BAU process for ongoing history maintenance | Governance | Develop | BAU process doc
Subtask | Daily: automated data append, DQ scoring on new observations | Governance | Develop
Subtask | Monthly: proxy drift review, gap detection, new RF onboarding queue | Governance | Develop
Subtask | Quarterly: history completeness audit, proxy coverage reconciliation | Governance | Develop
Subtask | Annual: deep audit — full lineage review, stress-period revalidation, regulatory exam prep | Governance | Develop
Subtask | Change control: any data change (proxy swap, correction, backfill) requires capital impact assessment before production deployment | Governance | Develop |  | Capital Tech
Subtask | Document: policies, procedures, runbooks, audit trail requirements | Governance | Develop | BAU manual
M19 Output → Governed BAU: daily/monthly/quarterly/annual cadence, change-controlled, capital-aware, audit-ready
Deliverable | Deliverable 7: Execute — Deliver Complete, Accurate, High-Quality Risk Factor Data Into Production
Output Summary | Outputs: Per-RF readiness assessment · Remediation execution using all foundation tools · Validated, production-ready RF data (proxied, carry-stripped, history-extended, DQ-passed) · Integrated to ES, VaR, PLA, Backtesting · Ongoing monitoring
Goal | Foundations 1–6 build the capabilities (proxy framework, DQ engine, remediation tools, onboarding process, carry methodology, history extension). This deliverable uses them. The team assesses every risk factor, decides what action is needed, executes using the right foundation tools, validates the result, and pushes to production. This is where the work becomes tangible — every RF ends up with accurate, complete, defensible data.
Sequence | Requires Foundations 1–6 to be established (tools, methodologies, BAU processes built) ¦ M20 (assess every RF) → M21 (execute remediation) → M22 (validate & integrate to production) → M23 (ongoing monitoring & continuous improvement)
Milestone | M20 — Assess Every Risk Factor: Connect the Dots Across All Foundations
Task | For every RF in the IMA universe, produce a single integrated readiness assessment | Data Analytics | Analyze | Per-RF readiness profile → M21
Subtask | Pull DQ status from Foundation 2: quality score (G/Y/R), active alerts, downstream impact estimate | Data Analytics | Gather |  | DQ engine (F2)
Subtask | Pull proxy status from Foundation 1: direct or proxied? If proxied: quality classification (G/Y/R), validation metrics, stress-period behaviour, proxy age | Data Analytics | Gather |  | Proxy registry (F1)
Subtask | Pull history status from Foundation 6: coverage depth (to 2007?), gaps, benchmark transitions handled?, structural breaks adjusted? | Data Analytics | Gather |  | History inventory (F6)
Subtask | Pull carry status from Foundation 5: carry-applicable? If yes: carry stripped? Which scenario (A/B/C)? Regime conditioning active? | Data Analytics | Gather |  | Carry pipeline (F5)
Subtask | Pull RFET status from WS-B: Modellable or NMRF? RPO count? Days-to-threshold-breach? | Data Analytics | Gather |  | RFET engine (WS-B)
Subtask | Pull onboarding status from Foundation 4: NTE/TSV submitted? MRM approved? Backtesting assessed? | Data Analytics | Gather |  | Onboarding tracker (F4)
Task | Classify every RF into action categories | Data Analytics | Classify | Action register → M21
Subtask | Category A — Production Ready: all dimensions green — DQ passed, proxy validated (or direct), carry stripped (if applicable), history to 2007, RFET classified, backtesting clean → no action, monitor only | Data Analytics | Classify
Subtask | Category B — Needs Proxy Work: history exists but proxy quality is yellow/red — apply Foundation 1 tools: re-run proxy assignment, find better candidate, validate, update registry | Data Analytics | Classify
Subtask | Category C — Needs History Work: direct or proxy data available but history depth insufficient — apply Foundation 6 tools: source vendor data, construct from raw, or extend via proxy | Data Analytics | Classify
Subtask | Category D — Needs DQ Remediation: history exists but quality is red — apply Foundation 3 tools: gap-fill, outlier treatment, adjustment, benchmark transition | Data Analytics | Classify
Subtask | Category E — Needs Carry Stripping: applicable RF type but carry not yet stripped — apply Foundation 5 methodology: assign scenario, implement, validate | Data Analytics | Classify
Subtask | Category F — Needs Full Onboarding: new RF (from WS-A Cat 2/5) — run Foundation 4 end-to-end: vendor → methodology → proxy → build → VaR impact → NTE/TSV → production | Data Analytics | Classify
Subtask | Category G — Blocked: cannot proceed without external input (vendor contract pending, FO Model upgrade required, Tech capacity unavailable) — document blocker, escalate, track | Data Analytics | Classify
Task | Prioritise the action register by capital impact | Data Analytics | Analyze | Prioritised action plan → Mgmt | Capital Tech
Subtask | Per RF needing action: estimate the capital benefit of fixing it (SES → IMCC if modellability improves, ES precision if history/proxy improves, PLA if carry/DQ improves) | Data Analytics | Analyze |  | Capital Tech: ES estimates
Subtask | Rank all RFs by net capital benefit: highest-impact RFs get resourced first — produce the prioritised execution plan for senior management | Data Analytics | Analyze | Execution plan → Senior Mgmt
Outcome | M20 Output → Every RF assessed across all dimensions, classified into action categories, prioritised by capital impact — the execution roadmap
Milestone | M21 — Execute: Apply Foundation Tools to Deliver Production-Ready Data
Task | Execute proxy remediation (Category B RFs) using Foundation 1 tools | Data Analytics | Analyze | Upgraded proxies → registry | Proxy framework (F1)
Subtask | Per RF: re-run proxy assignment engine from F1 — identify better candidates, compute validation metrics, run stress-period tests, select and assign | Data Analytics | Analyze
Subtask | Update proxy registry with new assignments: full lineage, validation metrics, justification — per F1 standards | Data Analytics | Develop
Subtask | For RFs upgraded from proxy to direct (vendor data now available): retire proxy, switch to direct, run capital impact — per F1 BAU promotion path | Data Analytics | Analyze |  | Capital Tech
Task | Execute history extension (Category C RFs) using Foundation 6 tools | Data Analytics | Analyze | Extended histories | History methods (F6)
Subtask | Per RF: apply the appropriate extension strategy identified in M20 — vendor sourcing (coordinate with Procurement), curve construction (apply F6 methodology with RA), or proxy extension (apply F1 framework for backfill period) | Data Analytics | Analyze |  | RA + Procurement
Subtask | Work with Tech to ingest sourced data, implement constructed histories, apply benchmark transitions (LIBOR→SOFR) — per F6 production pipeline | Tech Collab | Collaborate |  | Risk Tech builds
Subtask | Validate extended histories: confirm splice points clean, statistical properties preserved, no artificial ES artefacts | Data Analytics | Analyze
Task | Execute DQ remediation (Category D RFs) using Foundation 3 tools | Data Analytics | Analyze | Remediated time series | Remediation tools (F3)
Subtask | Per RF: apply approved remediation methodology — gap-fill, outlier treatment, adjustment, override — using F3 automated pipeline or manual override interface | Data Analytics | Analyze
Subtask | Validate remediated data: confirm gap-filling doesn't suppress tails, outlier treatment doesn't remove genuine stress events — per F3 validation rules | Data Analytics | Analyze
Subtask | Log all treatments in audit trail: what was changed, why, method used, before/after values, approver — per F3 BAU process | Governance | Develop
Task | Execute carry stripping (Category E RFs) using Foundation 5 tools | Data Analytics | Analyze | Carry-adjusted returns | Carry methodology (F5)
Subtask | Per RF: assign carry scenario (A/B/C) per F5 decision tree, apply carry stripping to daily generation and historical backfill | Data Analytics | Analyze
Subtask | Work with Tech to integrate carry-adjusted returns into production pipeline — per F5 implementation specs | Tech Collab | Collaborate |  | Risk Tech
Subtask | Validate carry removal impact: return distribution, PLA improvement, ES delta — per F5 validation framework | Data Analytics | Analyze
Task | Execute full onboarding (Category F RFs) using Foundation 4 process | Cross-Team | Collaborate | New RFs in production | Onboarding process (F4)
Subtask | Per new RF: run the full F4 pipeline — vendor assessment → selection → onboarding → history methodology with RA → generation methodology with RA + FO Quant Strat → proxy if needed → Tech build → VaR impact → backtesting → NTE/TSV → MRM approval → sign-off → deploy | Cross-Team | Collaborate |  | All foundations
Task | Unblock Category G RFs — escalate and track dependencies | Cross-Team | Collaborate | Unblock actions | External teams
Subtask | Per blocked RF: document the blocker, identify the owning team, escalate with capital impact context, agree on unblock timeline, track progress weekly | Cross-Team | Collaborate
Outcome | M21 Output → Foundation tools applied across the full RF population: proxies upgraded, histories extended, DQ remediated, carry stripped, new RFs onboarded — all validated, audit-trailed, and ready for production integration
Milestone | M22 — Validate & Integrate Into ES, VaR, PLA, Backtesting
Task | Run parallel capital calculations: old data vs. new (foundation-treated) data | Data Analytics | Analyze | Capital impact report → Mgmt | Capital Tech
Subtask | Work with Capital Tech to run ES with old data vs. strengthened data — at desk level, asset class level, firm level | Data Analytics | Analyze |  | Capital Tech: ES runs
Subtask | Assess stress period sensitivity: does the selected stress period change with extended histories? If GFC data is now available for RFs that previously started in 2010, does stress window shift — and is that correct? | Data Analytics | Analyze
Subtask | Decompose capital delta: how much driven by carry removal vs. history extension vs. DQ remediation vs. proxy improvement vs. new RF onboarding — attribute each driver | Data Analytics | Analyze |  | Capital Tech
Task | Validate PLA and backtesting with treated data | Data Analytics | Analyze | PLA/BT validation report
Subtask | Re-run PLA tests (Spearman, KS-distance) with treated RF data — quantify improvement per desk, attribute to specific data changes | Data Analytics | Analyze |  | PLA team
Subtask | Re-run backtesting — does exception count change? Do clustering patterns shift? Do any desks change traffic-light status? | Data Analytics | Analyze
Subtask | If any results worsen: investigate — genuine model issue revealed (good: now we know) or data treatment artefact (bad: fix the treatment) | Data Analytics | Analyze |  | RA + Risk Model
Task | Produce firm-wide readiness assessment | Data Analytics | Develop | Readiness report → Senior Mgmt
Subtask | Per RF: readiness score across all dimensions (history, DQ, proxy, carry, RFET, backtesting, NTE/TSV) — how many production-ready vs. in-progress vs. blocked? | Data Analytics | Develop
Subtask | Per desk / asset class: traffic light roll-up showing data quality posture and remaining gaps | Data Analytics | Develop
Subtask | Capital impact summary: current state ES vs. target state ES — the capital benefit of closing all remaining gaps | Data Analytics | Analyze |  | Capital Tech
Task | Obtain senior management sign-off and execute production cutover | Cross-Team | Collaborate | Production go-live | Senior Mgmt
Subtask | Present capital impact, PLA/backtesting validation, readiness assessment — obtain sign-off to cutover | Cross-Team | Collaborate
Subtask | Work with Tech to execute production cutover: ES/VaR engines consume treated data, RFET classification drives IMCC/SES routing — with rollback plan | Tech Collab | Collaborate |  | Risk Tech
Subtask | Post-cutover monitoring: two weeks of daily comparison against pre-cutover baseline — confirm results are consistent | Data Analytics | Analyze
Subtask | Confirm with Capital Tech that IMCC/SES aggregation correctly reflects new data — capital numbers reported to regulators are based on treated source | Cross-Team | Collaborate |  | Capital Tech
Outcome | M22 Output → Treated, validated RF data integrated into ES, VaR, PLA, Backtesting — parallel-validated, capital impact signed off, production cutover complete
Milestone | M23 — Ongoing Monitoring: Keep Data Accurate, Complete, and Audit-Ready
Task | Operate the integrated monitoring across all foundations | Governance | Develop | Monitoring cadence
Subtask | Daily: review orchestration dashboard — any new DQ alerts (F2)? Proxy drift detected (F1)? Carry anomalies (F5)? New RF identified (WS-A)? Vendor feed issues? | Data Analytics | Analyze
Subtask | Weekly: cross-foundation triage — RFs in-progress, unblock dependencies, resource allocation, escalate constraints | Cross-Team | Collaborate
Subtask | Monthly: readiness progress report — how many RFs improved this month? New issues? Capital impact trajectory? Report to senior management | Data Analytics | Develop | Monthly report → Mgmt
Subtask | Quarterly: full readiness reconciliation, proxy validation refresh, DQ framework effectiveness review, RFET reclassification cycle, regulatory reporting preparation | Governance | Develop
Subtask | Annual: deep audit — end-to-end workflow effectiveness, full proxy lineage review, stress-period revalidation, regulatory examination preparation | Governance | Develop
Task | Continuous improvement: make the process faster and better over time | Data Analytics | Analyze | Improvement actions
Subtask | Track cycle time: how long does it take to move an RF from "needs work" to "production-ready"? Identify and eliminate bottlenecks (vendor lead time? MRM queue? Tech capacity?) | Data Analytics | Analyze
Subtask | Track foundation tool effectiveness: are DQ alerts catching real issues? Are proxy validations detecting drift early enough? Is carry removal stable across regimes? | Data Analytics | Analyze
Subtask | Feedback loop: lessons from each remediation and onboarding cycle feed back into methodology refinement across all foundations — improve the tools, not just the data | Cross-Team | Collaborate |  | RA + Risk Model
Task | Define roles and responsibilities for integrated operations | Governance | Develop | RACI matrix
Subtask | Quant Data: orchestration, readiness assessment, cross-foundation coordination, methodology ownership, execution leadership | Governance | Develop
Subtask | Risk Tech: infrastructure for all foundation tools, production deployment, SLA ownership | Governance | Develop
Subtask | Risk Model / MRM: methodology governance, approval gates, independent validation | Governance | Develop
Subtask | FO Models / FO Quant Strat: pricing model alignment, RF generation methodology, MDO-to-RF consistency | Governance | Develop
Subtask | Capital Tech: capital impact runs, IMCC/SES routing, readiness-to-capital linkage | Governance | Develop
Subtask | Market Data: vendor management, data sourcing, feed maintenance | Governance | Develop
Subtask | MRO: oversight, BAU approval, escalation authority | Governance | Develop
Subtask | Document: integrated operations manual — cross-foundation runbooks, RACI matrix, escalation paths, regulatory exam checklist | Governance | Develop | Integrated ops manual
Outcome | M23 Output → Ongoing integrated operations: daily/weekly/monthly/quarterly/annual cadence, cross-foundation monitoring, continuous improvement, RACI, fully documented and audit-ready — the data stays accurate, not just once, but permanently

## WS-B RFET Modellability
Level | Description | Work Type | Action | Output → To | Depends On
Deliverable | Deliverable 1: Risk Factor Identification, Mapping & Taxonomy
Output Summary | Outputs: RPO source registry · RPO database · RPO-to-RF mapping · Bucketing engine · Counting engine · Qualitative test results · Classification register (Modellable / NMRF A / NMRF B) · Dashboard
RPOs come from exchanges, TRACE, DTCC, Markit, Bloomberg, ICE — each in different formats, identifiers, and granularity. There is no universal RPO-to-RF key. The translation layer is the hardest engineering problem. Infrastructure must be multi-source by design.
Sequence | M1 (sourcing) starts immediately → M2 (Tech: RPO infra) starts when vendors onboarded → M3 (mapping) + M4 (bucketing) + M5 (counting) build sequentially → M6 (PoC) validates the full chain → M7 (prod spec) hands to Tech → M8 (UAT) after Tech delivers → M9 (BAU)
input/assumptions | list of risk factors in scope , prebuilt in EMR or RFMD with complete history
Milestone | M1 — RPO Sourcing & Vendor Infrastructure (start immediately) |  |  | RPO source registry + vendor contracts + storage decision
Long lead time — vendor negotiations and licensing can take months. Start immediately. This is pure sourcing and procurement, no Tech build yet.
Task | Identify and assess RPO data sources per asset class | Data Analytics | Gather | RPO source assessment → M1.2
Subtask | Inventory candidates: exchanges (listed derivatives, equities), TRACE (US corp bonds, ABS), DTCC (OTC derivatives), Markit (CDS, indices), Bloomberg (broad), ICE (commodities, rates), internal execution data | Sourcing | Gather
Subtask | Assess each source for coverage, quality, and regulatory acceptability: does it qualify as a "real price" under NPR rules (committed quote, executed transaction, verifiable price)? Document evidence per source | Data Analytics | Analyze |  | RA: regulatory criteria
Subtask | Identify coverage gaps by asset class — for each gap, determine whether internal execution data can supplement, or whether the RF will default to NMRF | Data Analytics | Analyze | Gap report → capital impact
Subtask | Negotiate vendor contracts and data licensing agreements — coordinate with Procurement and Business for commercial terms, delivery format, ingestion timeline | Sourcing | Collaborate |  | Business + Procurement
Task | Get approval for data purchase and onboard RPO sources for all in-scope asset classes | Cross-Team | Collaborate | Signed contracts + data feeds | Business: budget approval
Dep | Dependency: Business — budget approval, vendor contract execution, licensing terms, data delivery format agreements |  |  |  | Business + Procurement
Task | Decide where RPO data will be stored — cross-team architecture decision | Cross-Team | Collaborate | Storage decision → M2 (Tech build) | Risk Tech + FO Tech
Subtask | Evaluate storage options: existing RFDM, MDSOR, new dedicated RPO database, or cloud — assess against volume (billions of observations), query patterns, and downstream integration needs | Tech Collab | Analyze |  | Risk Tech
Subtask | Agree on ownership: who hosts, who maintains, who pays — document decision and rationale | Cross-Team | Collaborate | Architecture decision doc | Risk Tech + Capital Tech
M1 Output → RPO source registry + signed vendor contracts + onboarded data feeds + storage architecture decision — feeds M2 (Tech build)
Milestone | M2 — Work with Tech to Build RPO Storage, Ingestion & Deduplication Infrastructure |  |  | Production RPO database | Requires M1 (vendors onboarded, storage decided)
This is a Tech Build milestone — Quant Data defines requirements and validates; Risk Tech builds and deploys. Every task below is a collaboration: Quant specifies, Tech implements, Quant tests.
Task | Work with Tech to design database schema for multi-source RPO storage | Tech Collab | Collaborate | Schema → Tech build | Risk Tech: architecture
Subtask | Specify requirements to Tech: accommodate different vendor formats, identifiers, metadata; unified query layer; support historical backfill, daily append, and full audit trail | Data Analytics | Develop | Requirements doc → Tech
Subtask | Review and validate Tech's schema design against requirements — confirm it handles all vendor formats and supports downstream mapping queries | Tech Collab | Analyze |  | Risk Tech: schema design
Task | Work with Tech to build daily ingestion pipelines per vendor | Tech Build | Build (Tech) | Ingestion pipelines | Risk Tech builds
Subtask | Specify to Tech: automated file/API pull per vendor, format parsing rules, validation checks (completeness, schema conformance, duplicate detection), error handling with retry logic and alerting | Data Analytics | Develop | Pipeline spec → Tech
Subtask | Tech builds ingestion connectors per vendor: exchange feeds, TRACE, DTCC, Markit, Bloomberg, ICE — each with vendor-specific parsing | Tech Build | Build (Tech) |  | Risk Tech builds
Subtask | Validate Tech's implementation: run test ingestion for each vendor, verify completeness, check for parsing errors, confirm dedup logic | Data Analytics | Analyze | Validation results
Task | Work with Tech to implement max-one-per-day deduplication logic per NPR requirements | Tech Collab | Collaborate | Dedup engine | Risk Tech builds
Subtask | Specify dedup rules to Tech: when multiple observations exist for the same instrument on the same day from same or different sources, apply regulatory rules — retain only one qualifying RPO per RF bucket per day | Risk Development | Develop | Dedup rules → Tech | RA: regulatory rules
Subtask | Tech implements dedup engine; Quant validates against known test cases | Tech Build | Build (Tech) |  | Risk Tech builds
Task | Work with Tech to build the RPO Normaliser | Tech Collab | Collaborate | Normaliser → M3 mapping | Risk Tech builds
Subtask | Specify normalisation rules to Tech: extract structured attributes from raw instrument descriptions — asset class, sub-type, currency, tenor, maturity, strike, issuer, sector, rating, region, index membership | Data Analytics | Develop | Normalisation rules → Tech
Subtask | Tech builds normaliser; Quant validates output against manually normalised sample across all asset classes | Tech Build | Build (Tech) |  | Risk Tech builds
Task | Work with Tech to design multi-source | Tech Collab | Collaborate | Multi-source logic | Risk Tech builds
Subtask | Specify to Tech: handle overlapping vendor coverage without double-counting, degrade gracefully when a feed is late or missing (use available sources, flag gaps) | Data Analytics | Develop
Task | Backfill 12+ months of historical RPOs from all onboarded vendors | Tech Collab | Collaborate | Historical RPO database | Risk Tech: ingestion
Subtask | Coordinate with Tech to ingest historical vendor files; validate completeness and consistency against vendor-provided record counts | Data Analytics | Analyze | Backfill validation
M2 Output → Production RPO database: multi-source, daily-ingested, deduplicated, normalised, with 12+ months backfill — built by Tech, specified and validated by Quant
Milestone | M3 — Build RPO-to-RF Mapping & Translation Layer ( BRD, PoC) |  |  | RPO-to-RF mapping engine | Requires M2 (RPO database) + WS-A RF taxonomy
The hardest engineering problem in RFET. RPOs speak in instrument IDs (CUSIPs, ISINs, tickers). RFs speak in risk taxonomy (IR_USD_3M_SOFR). Bridging these two worlds requires a mapping engine that doesn't exist today.
Task | Brainstorm the mapping architecture | Data Analytics | Analyze | Mapping design → build | RA + WS-A taxonomy
Subtask | Determine mapping path: RPO → instrument → MDO → RF (leveraging WS-A mapping) vs. RPO → RF direct vs. hybrid — document trade-offs (coverage vs. maintenance vs. accuracy) | Risk Development | Analyze |  | RA
Subtask | Determine whether trade-level detail should inform mapping: can internal execution data establish MDO consumption patterns that improve RPO-to-RF linkage? | Data Analytics | Analyze |  | FO: trade data access
Task | Brainstorm instrument-level metadata enrichment | Data Analytics | Analyze | Enrichment engine
Subtask | For each RPO, resolve to canonical instrument: CUSIP, ISIN, asset class, issuer, sector, region, tenor, strike, currency, index membership — using vendor reference data and internal securities master | Data Analytics | Develop |  | FO: securities master
Task | Build and Design PoC for the RF linkage engine | Data Analytics | Analyze | Linkage engine → M4 bucketing | WS-A: RF taxonomy
Subtask | Map enriched RPO instruments to internal RF keys: match on asset class, sub-type, currency, tenor bucket, strike bucket, issuer/sector/region dimensions | Risk Development | Develop |  | Consumes WS-A taxonomy
Task | Handle mapping edge cases | Data Analytics | Analyze | Edge case rules | RA
Subtask | Instruments mapping to multiple RFs (bond → credit spread + IR), instruments mapping to no RF (traded but not in model), ambiguous bucket boundary cases | Data Analytics | Analyze |  | RA: methodology
Task | Brainstorm the final mapping output | Data Analytics | Analyze | Mapping table → M4
Subtask | RPO_ID → Instrument → RF_Key → Bucket → mapping confidence score → mapping method (direct/inferred/trade-based) — with full audit trail | Data Analytics | Develop
M3 Output → RPO-to-RF mapping engine linking every normalised RPO to internal RF keys, with confidence scoring and audit trail — feeds M4 bucketing
Task | Hand it off to Tech | Tech Collab | Collaborate
Milestone | M4 — Build Bucketing Engine |  |  | Bucketing methodology + automated engine | Requires M3 (RPO-to-RF mapping)
Task | Define RF bucketing methodology per NPR requirements | Data Analytics | Analyze | Bucketing rules → engine | RA + Risk Model
Subtask | Define bucket boundaries per asset class: IR (tenor buckets), EQ (single-name vs. index), Credit (issuer/sector/rating), Commodity (contract/grade/location), FX (currency pair) | Risk Development | Develop |  | RA
Subtask | Determine own vs. prescribed bucketing — document regulatory basis and justification (supervisors will challenge bucket definitions that are too broad, inflating RPO counts) | Risk Development | Develop | Bucketing justification doc | Risk Model: governance
Task | Brainstorm how to automate RPO → bucket → RF mapping engine | Data Analytics | Develop | Bucketing engine → M5
Subtask | For each normalised, RF-linked RPO, assign to the correct bucket and validate bucket-RF consistency against the WS-A taxonomy | Data Analytics | Develop |  | Consumes WS-A taxonomy
M4 Output → Bucketing methodology documented + automated bucketing engine — feeds M5 counting engine
Milestone | M5 —Brainstorm Quantitative Counting Engine with Regulatory Thresholds |  |  | Per-RF modellability scores | Requires M4 (bucketing)
Task | Implement rolling 12-month RPO counting logic | Data Analytics | Develop | Counting engine
Subtask | For each RF bucket, count distinct RPO days over trailing 12-month window, applying max-one-per-day dedup | Data Analytics | Develop
Task | Apply prescribed pass/fail thresholds | Data Analytics | Develop | Pass/fail per RF | WS-A: LH assignments
Subtask | ≥24 RPOs for LH ≤ 20 days, ≥16 RPOs for LH > 20 days — consume LH assignments from WS-A | Risk Development | Develop |  | Consumes WS-A LH
Task | Handle threshold edge cases | Data Analytics | Analyze | Edge case rules | RA
Subtask | RFs near the boundary (23 or 15 RPOs), oscillating RFs, newly onboarded RFs with <12 months history | Data Analytics | Analyze |  | RA: methodology
Task | Produce per-RF quantitative test output | Data Analytics | Develop | Quant test results → M6 PoC
Subtask | RPO count, threshold, pass/fail, days-to-breach, trend over time — per RF | Data Analytics | Develop
M5 Output → Counting engine producing per-RF modellability scores with threshold comparison and trend analytics — feeds M6 PoC
Milestone | M6 — RFET Quantitative PoC (validate full chain end-to-end) |  |  | Validated PoC + stakeholder sign-off | Requires M2-M5 components
This is NOT a Tech build — this is Quant Data building a Python-based proof of concept to validate the full chain before handing to Tech for production-grade buildout.
Task | Build end-to-end PoC on a single asset class | Data Analytics | Build PoC | PoC results → Demo
Subtask | Select PoC asset class (e.g., IR — exchange-traded, well-structured tenor buckets, high RPO density) to demonstrate full chain: ingest → normalise → map to RF → bucket → count → classify | Data Analytics | Analyze
Subtask | Build PoC in Python: end-to-end pipeline from raw vendor file to modellability classification — using M3 mapping, M4 bucketing, M5 counting logic | Data Analytics | Build PoC
Subtask | Validate PoC: compare automated classification against manual expert assessment — quantify accuracy, identify mapping failures, document edge cases requiring rule refinement | Data Analytics | Analyze | Accuracy report | RA: expert review
Task | Demo PoC to stakeholders and obtain sign-off for production build | Cross-Team | Collaborate | Sign-off → M7 (prod spec) | All stakeholders
Subtask | Present to Risk Model, Capital Tech, Risk Tech, senior management: demonstrate pipeline, show classification accuracy, highlight capital impact, present scaling plan for all asset classes | Cross-Team | Collaborate
Subtask | Collect feedback on bucketing definitions, mapping logic, threshold handling, integration requirements — incorporate into production specification | Cross-Team | Collaborate | Feedback → M7 spec
Subtask | Obtain formal approval: scope (all asset classes), timeline, Risk Tech resource commitment for production build, Capital Tech commitment for IMCC/SES consumption, agreed ownership model | Cross-Team | Collaborate | Formal approval | Risk Tech + Capital Tech
M6 Output → Validated PoC with accuracy metrics + stakeholder sign-off — handoff to M7 (production specification for Tech)
Milestone | M7 — Production Specification (→ handoff to Tech) |  |  | Complete prod spec → Risk Tech | Requires M6 PoC sign-off
Quant Data translates PoC learnings into detailed production requirements. Tech builds from this specification. This is the formal handoff document.
Task | Produce detailed production requirements for RFET infrastructure | Cross-Team | Collaborate | Production spec → Risk Tech | M6 PoC learnings
Subtask | Database schema spec: multi-source RPO storage, dedup logic, historical backfill, audit trail | Data Analytics | Develop
Subtask | Ingestion pipeline spec per vendor: file/API formats, parsing rules, validation, error handling, retry logic | Data Analytics | Develop
Subtask | RPO normaliser spec: attribute extraction rules, multi-source blending, graceful degradation | Data Analytics | Develop
Subtask | RPO-to-RF mapping spec: enrichment rules, linkage logic, confidence scoring, edge case handling | Data Analytics | Develop
Subtask | Bucketing engine spec: bucket boundaries per asset class, RPO-to-bucket assignment logic | Data Analytics | Develop
Subtask | Counting engine spec: rolling 12-month, max-one-per-day dedup, thresholds (≥24 LH≤20d, ≥16 LH>20d) | Data Analytics | Develop
Subtask | Classification engine spec: qualitative + quantitative → Modellable / NMRF A / NMRF B → capital routing API for IMCC/SES consumption | Data Analytics | Develop
Subtask | Dashboard spec: desk-level view, asset-class view, early-warning alerts (approaching threshold), capital impact simulator (what-if vendor onboarding) | Data Analytics | Develop
Dep | Handoff → Risk Tech (WS-C): Tech builds production-grade infrastructure from these specifications |  |  |  | Risk Tech: accepts spec
Dep | Handoff → Capital Tech: confirms IMCC/SES engine will consume classification output via API |  |  |  | Capital Tech: confirms
M7 Output → Complete production specification package: RPO infra, normaliser, mapping, bucketing, counting, classification, dashboard — formally handed to Tech (WS-C) for build
Milestone | M8 — UAT, Final Classification & Go-Live (after Tech delivers WS-C) |  |  | Classification register in production | Requires: WS-C Tech delivery
Tech has built the production system. Quant now validates it works correctly, runs the final classification, and cuts over to production.
Task | Test Technology's production implementation against acceptance criteria | Tech Collab | Analyze | UAT results → Go/No-Go | Risk Tech: delivery
Subtask | Define acceptance criteria: ingestion completeness (100%), normalisation accuracy (≥99%), mapping coverage (≥95%), counting correctness (zero discrepancy vs. manual recount), classification consistency (matches PoC baseline) | Data Analytics | Develop | Acceptance criteria doc
Subtask | Execute UAT across all asset classes: run full pipeline end-to-end, compare production output against PoC baseline and expert review | Data Analytics | Analyze |  | Risk Tech: production env
Subtask | Stress testing: simulate vendor feed failure (late, missing, corrupt), RPO volume spikes (month-end, roll dates), boundary-crossing scenarios (RF with exactly 24 RPOs losing one observation) | Data Analytics | Analyze |  | Risk Tech: test support
Subtask | Parallel run: operate new engine alongside existing manual/semi-manual process for at least one full month — reconcile outputs, resolve discrepancies before cutover | Tech Collab | Analyze | Reconciliation report | Risk Tech: parallel env
Task | Produce final RFET classification register | Tech Collab | Classify | Classification → Capital routing | Capital Tech
Subtask | Per RF: qualitative result + quantitative result (RPO count, threshold) → combined classification (Modellable / NMRF Type A / NMRF Type B) → capital routing (IMCC vs. SES) + estimated capital impact | Data Analytics | Classify
Subtask | Per NMRF: estimate SES capital charge vs. IMCC counterfactual — quantify the capital cost of each NMRF classification | Data Analytics | Analyze | Capital impact report → Mgmt | Capital Tech: SES estimates
Task | Sign off and go live | Cross-Team | Collaborate | Production go-live | Senior Management
Subtask | Production readiness sign-off: document test results, known limitations, agreed workarounds, remediation timeline | Cross-Team | Collaborate | Sign-off doc | Risk Model + Capital Tech
M8 Output → Final classification register (Modellable / NMRF A / NMRF B) in production, with capital routing to IMCC vs. SES, validated and signed off
Milestone | M9 — BAU Process & Governance |  |  | BAU operating model + governance docs | After M8 go-live
Task | Establish RFET BAU process | Governance | Develop | BAU manual → Operations
Subtask | Daily operating model: automated ingestion and classification runs, daily exception review (failed ingestions, unmapped RPOs, classification changes), SLA for resolution | Governance | Develop
Subtask | Quarterly RFET refresh: formal re-run of full classification, comparison against prior quarter, documentation of all reclassifications (Modellable → NMRF or vice versa) with root cause and capital impact | Governance | Develop
Subtask | Trigger-based reclassification: vendor loss, market liquidity event, new RF onboarded, bucket methodology change — define events and approval workflow for each | Governance | Develop
Subtask | Escalation paths: who is notified when material RF approaches threshold, who approves NMRF acceptance vs. remediation investment, how decision is documented for regulatory exam | Governance | Develop
Subtask | Roles and responsibilities: Quant Data (methodology, mapping logic, bucketing), Risk Tech (infrastructure, SLA, monitoring), Capital Tech (consumption, capital routing), Risk Model (classification governance), Market Data (vendor management) | Governance | Develop
Subtask | Document BAU process: operating procedures manual, runbooks for common and exceptional scenarios, escalation matrices, SLA definitions, regulatory exam preparation checklist | Governance | Develop | BAU manual
Dep | Dependency: Capital Tech — reclassification triggers automatic re-routing between IMCC and SES capital streams; Capital Tech must confirm consumption within SLA |  |  |  | Capital Tech
M9 Output → Governed BAU process: daily ops, quarterly refresh, trigger-based reclassification, documented and audit-ready