## RFET Project Plan
# | Level | Description | Primary Owner | Tech | Data Eng | Quant | Business/SME | Duration | Dependency | Status
D1 | Deliverable | Identify Trading Desks in Scope for IMA | Business/SME | ● | ○ | ○ | ● | 4–6 weeks | —
M1.1 | Milestone | Trading Desk Scope Defined & Approved | Business/SME |  |  |  | ● | Week 4 | —
T1.1.1 | Task | Obtain current Volcker trading desk structure | Business/SME |  |  |  | ● | 1 week | —
S1.1.1a | Subtask | Identify all desks under Rates & FX umbrella: IR Options, IR Swaps, FX Spot, FX Forward, EM, Agencies, Inflation | Business/SME |  |  |  | ● | 3 days | —
S1.1.1b | Subtask | Identify all desks under Credit, Equity, Commodities, Munis | Business/SME |  |  |  | ● | 3 days | —
S1.1.1c | Subtask | Document desk hierarchy: legal entity, business line, Volcker desk, sub-desk | Business/SME |  |  |  | ● | 2 days | —
B1.1.1 | BCA | Desk structure document reviewed and signed off by desk heads and risk management | Business/SME |  |  |  | ● |  | S1.1.1c
T1.1.2 | Task | Determine IMA eligibility intent per desk | Business/SME |  |  | ● | ● | 2 weeks | T1.1.1
S1.1.2a | Subtask | Run preliminary SA vs. IMA capital comparison per desk (order of magnitude) | Quant |  |  | ● | ○ | 1 week | T1.1.1
S1.1.2b | Subtask | Identify desks where IMA capital savings justify the implementation cost | Business/SME |  |  | ● | ● | 3 days | S1.1.2a
S1.1.2c | Subtask | Document rationale for inclusion/exclusion of each desk from IMA scope | Business/SME |  |  |  | ● | 3 days | S1.1.2b
B1.1.2 | BCA | IMA desk scope approved by CRO and CFO; documented in scope memo | Business/SME |  |  |  | ● |  | S1.1.2c
T1.1.3 | Task | Map desk structure to regulatory trading desk definition | Quant |  |  | ● | ● | 1 week | T1.1.2
S1.1.3a | Subtask | Confirm each desk meets NPR trading desk definition (head trader, clear strategy, limits) | Business/SME |  |  |  | ● | 3 days | T1.1.2
S1.1.3b | Subtask | Document desk-level risk factor ownership: which RFs belong to which desk | Quant |  |  | ● | ○ | 3 days | S1.1.3a
B1.1.3 | BCA | Regulatory desk mapping document completed and reviewed by compliance | Business/SME |  |  |  | ● |  | S1.1.3b
D2 | Deliverable | Risk Factor Identification & MDO Mapping | Data Eng | ● | ● | ● | ● | 8–12 weeks | D1
M2.1 | Milestone | Complete MDO Inventory Across All In-Scope Desks | Data Eng | ● | ● |  | ● | Week 4 | D1
T2.1.1 | Task | Extract all Market Data Objects (MDOs) used in FO pricers | Data Eng | ● | ● |  | ○ | 2 weeks | D1
S2.1.1a | Subtask | Connect to FO pricing systems and extract MDO consumption logs per desk | Tech | ● | ● |  |  | 1 week | D1
S2.1.1b | Subtask | Catalog every MDO by type: IR curve, FX spot, vol surface, credit spread, basis, correlation, dividend | Data Eng |  | ● |  |  | 1 week | S2.1.1a
S2.1.1c | Subtask | Tag each MDO with source system, update frequency, data vendor, and desk consumer | Data Eng |  | ● |  |  | 3 days | S2.1.1b
B2.1.1 | BCA | Complete MDO inventory spreadsheet delivered and validated by desk quants | Data Eng |  | ● |  | ● |  | S2.1.1c
T2.1.2 | Task | Extract all Risk Factors used in the risk model | Quant |  | ● | ● |  | 2 weeks | D1
S2.1.2a | Subtask | Pull complete risk factor catalog from risk engine: name, type, asset class, tenor grid, strike grid | Tech | ● |  | ● |  | 1 week | D1
S2.1.2b | Subtask | Map each risk factor to its risk class (GIRR, CSR, FX, EQ, COMM) per NPR taxonomy | Quant |  |  | ● |  | 3 days | S2.1.2a
S2.1.2c | Subtask | Identify risk factors that exist in risk but have no corresponding MDO in FO | Quant |  | ● | ● |  | 3 days | S2.1.2b
B2.1.2 | BCA | Complete risk factor catalog delivered; cross-referenced with MDO inventory | Quant |  |  | ● |  |  | S2.1.2c
M2.2 | Milestone | MDO → RF Mapping Complete with Gap Analysis | Quant |  | ● | ● | ● | Week 8 | M2.1
T2.2.1 | Task | Classify every MDO into one of four categories | Quant |  | ● | ● | ● | 3 weeks | M2.1
S2.2.1a | Subtask | Category 1: Mapped — MDO directly corresponds to an existing risk factor | Quant |  | ● | ● |  | 1 week | M2.1
S2.2.1b | Subtask | Category 2: Not mapped — MDO has no RF but SHOULD have one (gap → create new RF) | Quant |  | ● | ● | ● | 1 week | S2.2.1a
S2.2.1c | Subtask | Category 3: Not mapped — MDO is a pricing input, NOT a risk factor (fixings, reset costs, impact pricing) | Quant |  |  | ● | ● | 3 days | S2.2.1b
S2.2.1d | Subtask | Category 4: FO/Risk disconnect — MDO maps to a fundamentally different RF in risk (structural gap) | Quant |  |  | ● | ● | 1 week | S2.2.1c
B2.2.1 | BCA | Gap analysis report delivered: count by category, by desk, by asset class. Reviewed by risk and desk heads. | Quant |  |  | ● | ● |  | S2.2.1d
T2.2.2 | Task | Create new risk factors for identified gaps (Category 2) | Quant | ● | ● | ● |  | 3 weeks | T2.2.1
S2.2.2a | Subtask | Define RF specification: name, type, tenor/strike grid, source, update frequency | Quant |  |  | ● |  | 1 week | T2.2.1
S2.2.2b | Subtask | Build data pipeline to source and store the new RF time series | Data Eng | ● | ● |  |  | 2 weeks | S2.2.2a
S2.2.2c | Subtask | Backfill historical data for new RFs (minimum 2 years, target back to 2007 for stress) | Data Eng |  | ● |  |  | 2 weeks | S2.2.2b
S2.2.2d | Subtask | Integrate new RFs into risk engine and validate P&L impact | Tech | ● |  | ● |  | 1 week | S2.2.2c
B2.2.2 | BCA | New risk factors live in production; validated by quant and confirmed by desk | Quant | ● | ● | ● | ● |  | S2.2.2d
T2.2.3 | Task | Document and remediate FO/Risk disconnects (Category 4) | Business/SME | ● |  | ● | ● | Ongoing | T2.2.1
S2.2.3a | Subtask | For each disconnect: document FO model, risk model, the gap, and proposed fix | Quant |  |  | ● | ● | 2 weeks | T2.2.1
S2.2.3b | Subtask | Prioritize disconnects by PLA impact (which ones will cause the most PLA noise) | Quant |  |  | ● |  | 1 week | S2.2.3a
S2.2.3c | Subtask | Initiate FO model upgrade requests (e.g., RVF+ → Full Config for credit) | Business/SME | ● |  |  | ● | Varies | S2.2.3b
B2.2.3 | BCA | Disconnect remediation plan approved by CRO; timelines agreed with FO technology | Business/SME |  |  |  | ● |  | S2.2.3c
D3 | Deliverable | Risk Factor Taxonomy, Metadata & Liquidity Horizons | Quant | ● | ● | ● | ○ | 6–8 weeks | D2
M3.1 | Milestone | RF Taxonomy & Definition Framework Complete | Quant |  |  | ● |  | Week 4 | D2
T3.1.1 | Task | Define risk factor taxonomy and granularity standards | Quant |  |  | ● | ● | 2 weeks | D2
S3.1.1a | Subtask | Define asset class hierarchy: GIRR, CSR_NS, CSR_SEC, FX, EQ, COMM → sub-types | Quant |  |  | ● |  | 3 days | D2
S3.1.1b | Subtask | Define risk factor attributes: name, type, currency, tenor, maturity, strike, moneyness, issuer, sector, region | Quant |  |  | ● |  | 3 days | S3.1.1a
S3.1.1c | Subtask | Define granularity level for each RF type: issuer-level vs. sector vs. rating bucket vs. index | Quant |  |  | ● | ● | 1 week | S3.1.1b
S3.1.1d | Subtask | Determine RF definition: overlapping vs. non-overlapping returns, absolute vs. relative, log vs. simple | Quant |  |  | ● |  | 3 days | S3.1.1c
B3.1.1 | BCA | RF taxonomy document finalized; approved by quant lead and model validation | Quant |  |  | ● |  |  | S3.1.1d
T3.1.2 | Task | Classify all risk factors per taxonomy | Quant |  | ● | ● |  | 2 weeks | T3.1.1
S3.1.2a | Subtask | Tag every RF with asset class, sub-type, currency, tenor bucket, and granularity level | Data Eng |  | ● | ● |  | 1 week | T3.1.1
S3.1.2b | Subtask | Build RF metadata repository (structured database, not spreadsheets) | Tech | ● | ● |  |  | 1 week | S3.1.2a
B3.1.2 | BCA | RF metadata repository live; all RFs tagged and queryable | Data Eng | ● | ● |  |  |  | S3.1.2b
M3.2 | Milestone | Liquidity Horizons Assigned to All Risk Factors | Quant |  |  | ● | ● | Week 6 | M3.1
T3.2.1 | Task | Assign liquidity horizons to all risk factors | Quant |  |  | ● | ● | 2 weeks | M3.1
S3.2.1a | Subtask | Map each RF to one of 5 prescribed LH tiers (10, 20, 40, 60, 120 days) per NPR rules | Quant |  |  | ● |  | 1 week | M3.1
S3.2.1b | Subtask | Handle edge cases: cross-currency basis, bespoke credit, multi-underlying instruments | Quant |  |  | ● | ● | 3 days | S3.2.1a
S3.2.1c | Subtask | Document justification for each LH assignment (supervisor will challenge) | Quant |  |  | ● |  | 3 days | S3.2.1b
S3.2.1d | Subtask | Build weighted-average LH calculator for multi-underlying instruments | Tech | ● |  | ● |  | 3 days | S3.2.1c
B3.2.1 | BCA | LH assignment file completed; reviewed by model validation and risk management | Quant |  |  | ● | ● |  | S3.2.1d
T3.2.2 | Task | Identify and document all proxy relationships | Quant |  | ● | ● | ● | 2 weeks | T3.2.1
S3.2.2a | Subtask | For each RF using a proxy: document the proxy RF, the justification, and the track record | Quant |  |  | ● | ● | 1 week | T3.2.1
S3.2.2b | Subtask | Classify proxies: green (same data), yellow (operational gap), red (structural mismatch) | Quant |  |  | ● |  | 3 days | S3.2.2a
S3.2.2c | Subtask | Build proxy mapping table: original RF → proxy RF → justification → review date | Data Eng |  | ● | ● |  | 3 days | S3.2.2b
S3.2.2d | Subtask | Validate proxy quality: correlation analysis, volatility ratio, regime behavior | Quant |  |  | ● |  | 1 week | S3.2.2c
B3.2.2 | BCA | Proxy registry completed; all proxies documented with justification and validation metrics | Quant |  |  | ● |  |  | S3.2.2d
D4 | Deliverable | RFET Qualitative Test Engine | Quant | ● | ● | ● | ○ | 6–8 weeks | D3
M4.1 | Milestone | Qualitative Test Framework Designed | Quant |  |  | ● |  | Week 3 | D3
T4.1.1 | Task | Design qualitative test methodology | Quant |  |  | ● | ● | 2 weeks | D3
S4.1.1a | Subtask | Define the 7 quality standards and how each will be evaluated per RF | Quant |  |  | ● |  | 1 week | D3
S4.1.1b | Subtask | Define pass/fail criteria for each standard (binary vs. scored) | Quant |  |  | ● |  | 3 days | S4.1.1a
S4.1.1c | Subtask | Define data sources for each check: update frequency logs, source reliability scores, proxy registers | Data Eng |  | ● | ● |  | 3 days | S4.1.1b
S4.1.1d | Subtask | Design exception/override workflow for edge cases | Quant |  |  | ● | ● | 2 days | S4.1.1c
B4.1.1 | BCA | Qualitative test methodology document approved by model validation | Quant |  |  | ● |  |  | S4.1.1d
M4.2 | Milestone | Qualitative Test Engine Built & Validated | Tech | ● | ● | ● |  | Week 7 | M4.1
T4.2.1 | Task | Build automated qualitative test engine | Tech | ● | ● | ● |  | 3 weeks | M4.1
S4.2.1a | Subtask | Build data quality check 1: real market price verification (arm's-length transaction check) | Tech | ● | ● |  |  | 3 days | M4.1
S4.2.1b | Subtask | Build data quality check 2: update frequency monitor (weekly minimum threshold) | Tech | ● | ● |  |  | 2 days | S4.2.1a
S4.2.1c | Subtask | Build data quality check 3: source reliability scoring | Tech | ● | ● |  |  | 2 days | S4.2.1b
S4.2.1d | Subtask | Build data quality check 4: volatility capture validation | Quant | ● |  | ● |  | 3 days | S4.2.1c
S4.2.1e | Subtask | Build data quality check 5: correlation capture validation | Quant | ● |  | ● |  | 3 days | S4.2.1d
S4.2.1f | Subtask | Build data quality check 6: model-derived vs. real price flag | Tech | ● | ● |  |  | 2 days | S4.2.1e
S4.2.1g | Subtask | Build data quality check 7: proxy justification and track record verification | Quant | ● |  | ● |  | 3 days | S4.2.1f
S4.2.1h | Subtask | Build aggregation logic: all 7 checks → single pass/fail per RF | Tech | ● |  | ● |  | 2 days | S4.2.1g
S4.2.1i | Subtask | Build quarterly scheduling and automation framework | Tech | ● |  |  |  | 3 days | S4.2.1h
B4.2.1 | BCA | Qualitative test engine passes UAT; validated against manual test results for 500 sample RFs | Tech | ● |  | ● | ● |  | S4.2.1i
D5 | Deliverable | RFET Quantitative Test Engine & RPO Infrastructure | Data Eng | ● | ● | ● | ○ | 10–14 weeks | D3
M5.1 | Milestone | RPO Sourcing & Storage Infrastructure Live | Data Eng | ● | ● |  |  | Week 5 | D3
T5.1.1 | Task | Source Real Price Observations (RPOs) | Data Eng | ● | ● |  | ● | 3 weeks | D3
S5.1.1a | Subtask | Identify RPO sources: exchanges (CME, ICE, LCH), TRACE, DTCC, Markit, Bloomberg BVAL | Data Eng |  | ● |  | ● | 1 week | D3
S5.1.1b | Subtask | Negotiate data agreements and licensing for each RPO source | Business/SME |  |  |  | ● | 2 weeks | S5.1.1a
S5.1.1c | Subtask | Identify arm's-length transaction requirements per NPR definition | Quant |  |  | ● |  | 3 days | S5.1.1a
S5.1.1d | Subtask | Identify third-party providers requiring public audit of pricing data validity | Business/SME |  | ● |  | ● | 1 week | S5.1.1c
B5.1.1 | BCA | RPO source inventory complete; data agreements in place; audit requirements identified | Data Eng |  | ● |  | ● |  | S5.1.1d
T5.1.2 | Task | Build RPO storage and ingestion infrastructure | Tech | ● | ● |  |  | 3 weeks | T5.1.1
S5.1.2a | Subtask | Design RPO database schema: observation date, RF ID, price, source, type (trade/bid/offer/committed quote) | Tech | ● | ● |  |  | 3 days | T5.1.1
S5.1.2b | Subtask | Build automated daily ingestion pipelines from each RPO source | Tech | ● | ● |  |  | 2 weeks | S5.1.2a
S5.1.2c | Subtask | Build deduplication logic: max 1 observation per RF per day | Tech | ● |  | ● |  | 3 days | S5.1.2b
S5.1.2d | Subtask | Build data quality checks on incoming RPOs: stale price detection, outlier flagging | Tech | ● | ● |  |  | 3 days | S5.1.2c
S5.1.2e | Subtask | Build historical backfill: load 12+ months of RPOs for initial classification run | Data Eng |  | ● |  |  | 1 week | S5.1.2d
B5.1.2 | BCA | RPO database live; daily feeds running; historical backfill complete; validated by data team | Tech | ● | ● |  |  |  | S5.1.2e
M5.2 | Milestone | RPO → RF Mapping Complete | Quant |  | ● | ● |  | Week 8 | M5.1
T5.2.1 | Task | Map RPOs to risk factor buckets | Quant |  | ● | ● |  | 3 weeks | M5.1
S5.2.1a | Subtask | Define bucketing approach per RF type: own bucketing vs. standard bucketing (NPR prescribed grids) | Quant |  |  | ● |  | 1 week | M5.1
S5.2.1b | Subtask | For each RPO: determine which RF bucket it maps to (tenor, maturity, strike, moneyness) | Quant |  | ● | ● |  | 1 week | S5.2.1a
S5.2.1c | Subtask | Build automated RPO → bucket → RF mapping engine | Tech | ● | ● | ● |  | 1 week | S5.2.1b
S5.2.1d | Subtask | Validate mapping: spot-check 1000 RPOs across asset classes | Quant |  |  | ● | ● | 3 days | S5.2.1c
B5.2.1 | BCA | RPO-to-RF mapping validated; automated engine running in production | Quant |  | ● | ● |  |  | S5.2.1d
M5.3 | Milestone | Quantitative Test Engine Built & First Classification Run | Quant | ● | ● | ● | ● | Week 12 | M5.2
T5.3.1 | Task | Build quantitative test counting engine | Tech | ● |  | ● |  | 2 weeks | M5.2
S5.3.1a | Subtask | Build observation counter: count distinct RPOs per RF over rolling 12-month window | Tech | ● |  | ● |  | 3 days | M5.2
S5.3.1b | Subtask | Implement threshold logic: ≥24 for LH≤20d, ≥16 for LH>20d | Tech | ● |  | ● |  | 2 days | S5.3.1a
S5.3.1c | Subtask | Implement max-1-per-day deduplication in counting | Tech | ● |  |  |  | 1 day | S5.3.1b
S5.3.1d | Subtask | Build quarterly scheduling: auto-refresh classification every quarter | Tech | ● |  |  |  | 3 days | S5.3.1c
B5.3.1 | BCA | Quantitative test engine passes UAT; counts validated against manual sample | Tech | ● |  | ● |  |  | S5.3.1d
T5.3.2 | Task | Combine qualitative + quantitative results → classification | Quant | ● |  | ● |  | 1 week | T5.3.1
S5.3.2a | Subtask | Build classification logic: pass both → Modellable; pass qual only → Type A; fail qual → Type B | Tech | ● |  | ● |  | 2 days | T5.3.1
S5.3.2b | Subtask | Build exception/override workflow with approval chain | Tech | ● |  |  | ● | 2 days | S5.3.2a
S5.3.2c | Subtask | Run first full classification across all in-scope risk factors | Quant |  |  | ● |  | 3 days | S5.3.2b
S5.3.2d | Subtask | Analyze results: % modellable, % Type A, % Type B by desk and asset class | Quant |  |  | ● | ● | 2 days | S5.3.2c
B5.3.2 | BCA | First RFET classification report delivered to risk committee; results reviewed with desk heads | Quant |  |  | ● | ● |  | S5.3.2d
T5.3.3 | Task | Build Modellable vs. Non-Modellable Dashboard | Tech | ● | ● |  | ● | 2 weeks | T5.3.2
S5.3.3a | Subtask | Design dashboard: by desk, by asset class, by RF type, trend over time | Tech | ● |  |  | ● | 3 days | T5.3.2
S5.3.3b | Subtask | Build drill-down: for each NMRF → show why it failed, which test, observation count | Tech | ● |  | ● |  | 1 week | S5.3.3a
S5.3.3c | Subtask | Build alerting: flag RFs approaching NMRF threshold (early warning) | Tech | ● |  |  |  | 3 days | S5.3.3b
S5.3.3d | Subtask | Build capital impact view: estimated SES charge per NMRF | Quant | ● |  | ● |  | 3 days | S5.3.3c
B5.3.3 | BCA | RFET dashboard live in production; accessible to risk, quant, and desk heads | Tech | ● |  |  | ● |  | S5.3.3d
D6 | Deliverable | Consolidate RF Metadata & Ongoing Governance | Quant | ● | ● | ● | ● | 4 weeks | D5
T6.1.1 | Task | Consolidate all RF metadata into single golden source | Data Eng | ● | ● | ● |  | 2 weeks | D5
S6.1.1a | Subtask | Merge: RF catalog + taxonomy + LH assignment + proxy registry + RFET classification + RPO counts | Data Eng |  | ● | ● |  | 1 week | D5
S6.1.1b | Subtask | Build API layer for downstream consumers: ES engine, SES engine, capital calc, reporting | Tech | ● |  |  |  | 1 week | S6.1.1a
B6.1.1 | BCA | Golden RF metadata source live; consumed by all downstream systems | Data Eng | ● | ● |  |  |  | S6.1.1b
T6.1.2 | Task | Establish ongoing governance and refresh cycle | Business/SME |  |  | ● | ● | 2 weeks | T6.1.1
S6.1.2a | Subtask | Define quarterly RFET refresh process: who runs it, who reviews, who approves reclassifications | Business/SME |  |  |  | ● | 3 days | T6.1.1
S6.1.2b | Subtask | Define trigger-based re-classification: material portfolio change, new desk, new product | Quant |  |  | ● | ● | 3 days | S6.1.2a
S6.1.2c | Subtask | Define escalation path for RFs that flip from Modellable → NMRF | Business/SME |  |  | ● | ● | 2 days | S6.1.2b
S6.1.2d | Subtask | Document full RFET governance framework for supervisory submission | Business/SME |  |  | ● | ● | 1 week | S6.1.2c
B6.1.2 | BCA | RFET governance framework document approved by CRO; ready for supervisor review | Business/SME |  |  | ● | ● |  | S6.1.2d

## Legend
Level | Description
Deliverable | Major work package — the 'what' at the highest level
Milestone | Key checkpoint — a gate that must be reached before proceeding
Task | A discrete unit of work that produces a specific output
Subtask | A component of a task — the granular 'how'
BCA | Business Completion Activity — sign-off, review, or approval that marks completion
Symbol | Meaning
● | Primary / heavy involvement
○ | Secondary / advisory involvement
— | No dependency