## Historical-Proxy-DQ-Carry
# | Level | Description | Work Type | Action | Output → To | Depends On
| Deliverable | Deliverable 1: Proxy Enhancement & Establishment
| Output Summary | Outputs: Proxy principles paper · Asset-class methodologies · Proxy registry with full lineage · Validated proxy assignments (G/Y/R) · BAU proxy management process
| Sequence | M1 (principles) → M2 (asset-class methods) → M3 (BAU) are sequential ¦ M1 is the foundation — cannot assign proxies without the rules
This deliverable establishes the proxy framework first (rules of the game), then implements per asset class, then operationalises. Every proxy in production must be traceable back to this framework.
M1 | Milestone | M1 — Define Proxy Principles & Governance Framework |  |  | Formal proxy methodology paper
1.1 | Task | Define proxy acceptability criteria and quantitative thresholds | Risk Development | Develop | Acceptability rules → M2 | RA: co-develop
1.1.1 | Subtask | Collaborate with RA to define proximity requirements (same asset class, currency, sector, risk type), basis risk tolerance, and conditions that trigger NMRF reclassification | Risk Development | Collaborate |  | RA
1.1.2 | Subtask | Collaborate with RA to define quantitative thresholds: correlation floor, volatility ratio band, tracking error ceiling, cointegration test requirements | Risk Development | Develop |  | RA
1.1.3 | Subtask | Collaborate with RA to define stress-period validation: test over GFC, European Sovereign, COVID, 2022 rates — stress-specific pass/fail thresholds | Risk Development | Develop |  | RA
1.1.4 | Subtask | Collaborate with Capital Tech to define the NMRF boundary: what threshold separates "proxied but modellable" from "proxy too weak, must be NMRF" — direct capital implications | Cross-Team | Collaborate |  | Capital Tech: SES impact
1.2 | Task | Define proxy hierarchy, lifecycle, and governance rules | Risk Development | Develop | Lifecycle rules → M2 | RA
1.2.1 | Subtask | Establish hierarchy: direct observation > same-issuer different tenor > same-sector peer > sector/rating index > broad benchmark > cross-asset — document when each level is acceptable | Risk Development | Develop |  | RA
1.2.2 | Subtask | Define lifecycle: assign (new RF, no history) → upgrade (direct data becomes available) → challenge (metrics breach) → retire/NMRF (no fix) — with capital impact assessment at each decision | Risk Development | Develop |  | Capital Tech
1.2.3 | Subtask | Define override rules: when can a lower-hierarchy proxy be selected over a higher one (e.g., stress-period behaviour)? Define approval workflow for overrides | Governance | Develop |  | Risk Model: governance
1.3 | Task | Document formal proxy methodology paper | Risk Development | Develop | Methodology paper → MRM validation | RA + Risk Model
1.3.1 | Subtask | Produce standalone regulatory deliverable: acceptability criteria, thresholds, hierarchy, lifecycle, stress-period testing, override governance, NMRF escalation | Risk Development | Develop
1.3.2 | Subtask | Submit to Model Risk Management (MRM) for independent validation — address challenges, obtain sign-off | Model Validation | Collaborate | MRM sign-off | MRM / Risk Model
M1 Output → Formal proxy principles: validated by MRM, accepted as the governing framework for all proxy assignments in M2
M2 | Milestone | M2 — Develop & Implement Proxy Methodologies Per Asset Class |  |  | Proxy registry with full lineage | Requires M1 principles
2.1 | Task | Develop asset-class-specific proxy methodologies with RA | Risk Development | Develop | Proxy methods per AC | RA: co-develop
2.1.1 | Subtask | IR: collaborate with RA to develop tenor interpolation/extrapolation, curve-to-curve proxying, cross-currency basis, inflation — implement in Python, validate against known benchmarks | Risk Development | Develop |  | RA
2.1.2 | Subtask | FX: collaborate with RA to develop cross-rate triangulation, EM pegged-currency handling, vol surface proxying — implement and validate against direct observations where available | Risk Development | Develop |  | RA
2.1.3 | Subtask | Credit: collaborate with RA to develop issuer-to-sector, single-name to index, CDS-bond basis, recovery rate proxying — handle credit event contamination | Risk Development | Develop |  | RA
2.1.4 | Subtask | Equity: collaborate with RA to develop single-name to sector/index, dividend proxying, vol surface proxying — handle corporate actions (splits, mergers, delistings) | Risk Development | Develop |  | RA
2.1.5 | Subtask | Commodity: collaborate with RA to develop contract roll methodology, grade/quality substitution, location basis — implement with calendar-aware roll logic | Risk Development | Develop |  | RA
2.2 | Task | Run proxy assignment and validation across all RFs requiring proxying | Data Analytics | Analyze | Validated assignments | RA: expert review
2.2.1 | Subtask | Per RF: identify candidate proxies per hierarchy, compute validation metrics (correlation, vol ratio, tracking error, cointegration), rank by quality, select best | Data Analytics | Analyze
2.2.2 | Subtask | Run stress-period validation: compute metrics separately over GFC, European Sovereign, COVID, 2022 — document how each proxy behaved during each stress | Data Analytics | Analyze
2.2.3 | Subtask | Classify each proxy: green (all pass), yellow (marginal in stress — acceptable with justification), red (fails — must remediate, upgrade, or escalate to NMRF) | Data Analytics | Classify |  | RA
2.2.4 | Subtask | Red proxies: investigate alternatives with RA; if no fix, escalate to NMRF with capital impact quantification — collaborate with Capital Tech for SES estimate | Cross-Team | Collaborate | NMRF escalations → Capital | RA + Capital Tech
2.3 | Task | Produce proxy registry with full lineage | Data Analytics | Develop | Proxy registry → ES, Regulatory
2.3.1 | Subtask | Per proxy: original RF → proxy RF → time series → source → effective dates → splice methodology → validation metrics (benign + stress) → justification narrative | Data Analytics | Develop
2.3.2 | Subtask | Produce proxy concentration risk analysis: desks/ACs where large proportion of ES is driven by proxy relationships | Data Analytics | Analyze | Concentration report → Mgmt
2.3.3 | Subtask | Quantify capital impact: per red/yellow proxy, ES difference between proxy vs. direct data vs. NMRF — drives investment decisions | Data Analytics | Analyze | Capital impact → Mgmt | Capital Tech
2.4 | Task | Document asset-class proxy methodologies for MRM validation | Risk Development | Develop | AC methodology papers → MRM | RA
2.4.1 | Subtask | Per asset class: formal methodology paper (proxy types, selection algorithm, validation criteria, stress testing, edge cases, limitations) | Risk Development | Develop
2.4.2 | Subtask | Submit to MRM for independent validation — sample proxy re-derivation, methodology challenge, sign-off | Model Validation | Collaborate | MRM sign-off | MRM
M2 Output → Proxy registry with full lineage, validation metrics, quality classification, capital impact — MRM-validated methodology per asset class
M3 | Milestone | M3 — BAU Proxy Management |  |  | Proxy BAU process + tools | Requires M2 registry
3.1 | Task | Build proxy monitoring tools | Data Analytics | Develop | Monitoring tools → BAU ops
3.1.1 | Subtask | Build automated proxy drift detection: monthly refresh of validation metrics, alert when proxy breaches correlation/tracking-error thresholds | Data Analytics | Develop
3.1.2 | Subtask | Build proxy age tracker: flag proxies in place beyond review cycle without re-validation | Data Analytics | Develop
3.1.3 | Subtask | Work with Tech to deploy monitoring tools into production with dashboard and alerting | Tech Collab | Collaborate | Production dashboard | Risk Tech: deployment
3.2 | Task | Establish BAU proxy governance process | Governance | Develop | BAU process doc
3.2.1 | Subtask | Monthly: refresh validation metrics, flag drifting proxies, investigate and remediate | Governance | Develop
3.2.2 | Subtask | Quarterly: full proxy coverage reconciliation, quality distribution review, concentration risk update | Governance | Develop
3.2.3 | Subtask | Annual: deep audit — full lineage review, stress-period re-validation, regulatory exam prep | Governance | Develop
3.2.4 | Subtask | Promotion path: proxy → direct when vendor data becomes available — with capital impact assessment and cutover plan | Governance | Develop |  | Capital Tech
3.2.5 | Subtask | Roles: Quant Data (methodology, validation), Risk Tech (tools, monitoring), Risk Model (governance sign-off), Market Data (vendor management), Capital Tech (impact runs) | Governance | Develop
3.2.6 | Subtask | Document BAU process: runbooks, escalation matrices, SLA definitions | Governance | Develop | BAU manual
M3 Output → Governed proxy BAU: monitoring tools in production, monthly/quarterly/annual cadence, documented and audit-ready
| Deliverable | Deliverable 2: Advanced Data Quality Framework
| Output Summary | Outputs: 4-tier DQ methodology · DQ scoring engine · Early warning system · Production dashboard with alerting · BAU monitoring process
| Sequence | M4 (methodology with RA) → M5 (PoC + validation) → M6 (work with Tech to productionise) → M7 (BAU)
M4 | Milestone | M4 — Build Advanced DQ Check Methodologies |  |  | DQ framework methodology
Design the intelligence layer — not just "is data missing?" but "is this data behaving consistently with its peers, its own history, and what the market is doing?" Context-aware, not just rule-based.
4.1 | Task | Collaborate with RA to develop Tier 1 — Deterministic checks | Risk Development | Develop | Tier 1 rules → engine | RA: co-develop
4.1.1 | Subtask | Missing data detection: gap counts, consecutive gap length, weekend/holiday calendar validation per market | Risk Development | Develop |  | RA
4.1.2 | Subtask | Stale price flagging: unchanged value for N business days (configurable per asset class), with low-vol exceptions | Risk Development | Develop |  | RA
4.1.3 | Subtask | Extreme outlier detection: absolute thresholds (negative prices, rates outside plausible range) + relative thresholds (N-sigma daily return) | Risk Development | Develop |  | RA
4.2 | Task | Collaborate with RA to develop Tier 2 — Advanced statistical checks | Risk Development | Develop | Tier 2 rules → engine | RA: co-develop
4.2.1 | Subtask | Volatility regime shift detection: EWMA vs. historical vol divergence, CUSUM/Bai-Perron structural break tests | Risk Development | Develop |  | RA
4.2.2 | Subtask | Distribution shift tests: KS-test, Anderson-Darling against rolling baseline — detect series whose return distribution has changed vs. peers | Risk Development | Develop |  | RA
4.2.3 | Subtask | Autocorrelation anomaly detection: sudden appearance/disappearance of serial correlation (may indicate stale pricing or interpolation artefacts) | Risk Development | Develop |  | RA
4.3 | Task | Collaborate with RA to develop Tier 3 — Peer-group & context-aware checks | Risk Development | Develop | Tier 3 rules → engine | RA: co-develop
4.3.1 | Subtask | Cross-RF correlation monitoring: detect correlation breakdowns between historically correlated RFs (e.g., 5Y and 10Y swap rates) | Risk Development | Develop |  | RA
4.3.2 | Subtask | Sector-vs-name divergence: single names moving dramatically vs. sector peers — genuine event or data error? | Risk Development | Develop |  | RA
4.3.3 | Subtask | Basis relationship monitoring: CDS-bond basis, swap spread, cross-currency basis — detect when basis moves outside historical norms | Risk Development | Develop |  | RA
4.3.4 | Subtask | Proxy tracking drift: monitor proxied RFs vs. their proxies — detect divergence beyond tolerance from proxy framework (Deliverable 1) | Risk Development | Develop |  | RA
4.4 | Task | Collaborate with RA to develop Tier 4 — ML-based intelligent triage | Risk Development | Develop | ML model spec → PoC | RA: co-develop
4.4.1 | Subtask | Train XGBoost (or similar) classifier on historical DQ alert data — labelled by resolution outcome (genuine issue vs. false positive) — using Tier 1-3 features as inputs | Risk Development | Develop |  | RA
4.4.2 | Subtask | Design model output: severity score, routing recommendation (auto-resolve / analyst queue / immediate escalation), explainability (which inputs drove classification) | Risk Development | Develop |  | RA
4.4.3 | Subtask | Define model governance: quarterly retraining, performance monitoring (precision/recall), degradation alerting | Risk Development | Develop |  | RA + Risk Model
4.5 | Task | Collaborate with RA to design downstream impact linkage | Risk Development | Develop | Impact model → scoring | RA + Capital Tech
4.5.1 | Subtask | For each DQ alert, estimate: can this cause PLA failure? Backtesting exception? ES instability? — so remediation is prioritised by capital materiality, not just data severity | Data Analytics | Analyze |  | RA
4.5.2 | Subtask | Define severity tiers: Critical (capital misstatement risk → SLA), High (could escalate), Medium (batch remediation), Low (informational) | Risk Development | Develop |  | RA
M4 Output → 4-tier DQ methodology: deterministic, advanced statistical, peer-group context-aware, ML intelligent triage — with downstream capital impact linkage
M5 | Milestone | M5 — Build DQ PoC & Validate |  |  | Validated DQ scoring engine | Requires M4 methodology
5.1 | Task | Build DQ PoC in Python | Data Analytics | Build PoC | PoC results → demo
5.1.1 | Subtask | Implement all Tier 1-3 checks with configurable thresholds per asset class and RF type | Data Analytics | Build PoC
5.1.2 | Subtask | Implement composite scoring engine: aggregate into per-RF quality score with drill-down | Data Analytics | Build PoC
5.1.3 | Subtask | Implement alert generation and routing: generate alerts per severity, route to queue | Data Analytics | Build PoC
5.1.4 | Subtask | Build unit tests: inject synthetic deficiencies (gaps, outliers, stale prices, correlation breaks) — confirm correct detection and scoring | Data Analytics | Analyze
5.2 | Task | Validate PoC against real data | Data Analytics | Analyze | Validation report | RA: expert review
5.2.1 | Subtask | Run across all RF time series — compare DQ scores against expert assessment | Data Analytics | Analyze |  | RA
5.2.2 | Subtask | Backtest ML triage: precision/recall against historical DQ incidents | Data Analytics | Analyze |  | RA
5.2.3 | Subtask | Demo to stakeholders: show detection accuracy, false positive rate, alert routing, capital impact linkage | Cross-Team | Collaborate | Sign-off → Tech build | Risk Model + Capital Tech
M5 Output → Validated DQ PoC with stakeholder sign-off — ready for productionisation
M6 | Milestone | M6 — Work with Tech to Productionise DQ Framework |  |  | Production DQ engine + dashboard | Requires M5 PoC sign-off
6.1 | Task | Specify production requirements to Tech | Data Analytics | Develop | Production spec → Risk Tech
6.1.1 | Subtask | Scheduling spec: daily refresh after market data ingestion, compute requirements, database for scores and alert history | Data Analytics | Develop
6.1.2 | Subtask | Dashboard spec: per-RF quality scores, asset-class/desk aggregations, trend views, alert queue management, drill-down | Data Analytics | Develop
6.1.3 | Subtask | API spec: downstream consumers (ES engine, PLA, backtesting) can query DQ status per RF | Data Analytics | Develop
6.2 | Task | Work with Tech to build and deploy production DQ engine | Tech Build | Build (Tech) | Production DQ engine | Risk Tech builds
6.2.1 | Subtask | Tech builds: scoring engine, alert generation, dashboard, API — per Quant specification | Tech Build | Build (Tech) |  | Risk Tech builds
6.2.2 | Subtask | Validate Tech's implementation: run full DQ assessment, compare against PoC, confirm scoring consistency and alert accuracy | Data Analytics | Analyze | Validation report
6.3 | Task | Work with Tech to deploy ML triage model in production | Tech Collab | Collaborate | ML model in production | Risk Tech builds
6.3.1 | Subtask | Specify model deployment requirements: daily scoring, automated routing, confidence thresholds, retraining pipeline | Data Analytics | Develop
6.3.2 | Subtask | Tech deploys; Quant validates production model output against PoC baseline | Tech Build | Build (Tech) |  | Risk Tech
M6 Output → Production DQ engine: 4-tier assessment, ML triage, dashboard, alerting — built by Tech, specified and validated by Quant
M7 | Milestone | M7 — BAU DQ Monitoring & Early Warning |  |  | BAU DQ process | After M6 production
7.1 | Task | Establish BAU DQ operating model | Governance | Develop | BAU process doc
7.1.1 | Subtask | Daily: exception review, analyst assignment, resolution SLA per severity tier | Governance | Develop
7.1.2 | Subtask | Monthly: DQ governance report, trend analysis, ML model performance review | Governance | Develop
7.1.3 | Subtask | Quarterly: ML model retraining, threshold recalibration, framework effectiveness review | Governance | Develop |  | RA
7.1.4 | Subtask | Roles: Quant Data (methodology, thresholds), Risk Tech (infrastructure, SLA), Risk Model (governance), Market Data (vendor escalation) | Governance | Develop
7.1.5 | Subtask | Document: runbooks, escalation matrices, SLA definitions | Governance | Develop | BAU manual
M7 Output → Governed DQ BAU: daily monitoring, early warning, ML triage, documented and audit-ready
| Deliverable | Deliverable 3: Data Quality Remediation Methodologies
| Output Summary | Outputs: Approved remediation methods (interpolation, adjustments, overrides, special computation) · Event calendar · BAU process for applying historical treatments
| Sequence | M8 (methodology with RA) → M9 (work with Tech to build tools) → M10 (BAU process)
M8 | Milestone | M8 — Develop Approved Remediation Methodologies |  |  | Remediation methodology paper
8.1 | Task | Collaborate with RA to develop gap-filling methodologies per asset class | Risk Development | Develop | Gap-fill rules → tools | RA: co-develop
8.1.1 | Subtask | Single-day gaps: linear interpolation (rates), last-known-good carry-forward (prices) | Risk Development | Develop |  | RA
8.1.2 | Subtask | Multi-day gaps: cubic spline (curves/surfaces), vol-surface arbitrage-free interpolation | Risk Development | Develop |  | RA
8.1.3 | Subtask | Extended gaps: carry-forward with decay, proxy-based filling, or flag-and-exclude | Risk Development | Develop |  | RA
8.2 | Task | Collaborate with RA to develop outlier treatment methodologies | Risk Development | Develop | Outlier rules → tools | RA: co-develop
8.2.1 | Subtask | Detection: Z-score, IQR fencing, Hampel filter (MAD-based), market-event-aware overrides | Risk Development | Develop |  | RA
8.2.2 | Subtask | Treatment options: winsorisation, nearest-neighbour replacement, interpolation, flag-and-retain | Risk Development | Develop |  | RA
8.2.3 | Subtask | Build event calendar: registry of stress events, corporate actions, index reconstitutions, benchmark transitions — observations during these are tail risk, not outliers | Data Analytics | Develop | Event calendar → DQ engine | RA + FO
8.3 | Task | Collaborate with RA to develop special computation / adjustment methodologies | Risk Development | Develop | Adjustment methods → tools | RA: co-develop
8.3.1 | Subtask | Override rules: when manual correction is justified, approval workflow, documentation requirements | Risk Development | Develop |  | RA + Risk Model
8.3.2 | Subtask | Special computation: derived RF reconstruction, cross-source reconciliation, redenomination adjustment | Risk Development | Develop |  | RA
8.4 | Task | Validate that remediation preserves tail risk properties | Data Analytics | Analyze | Validation report → MRM | RA
8.4.1 | Subtask | Compare ES with pre- and post-remediation data — confirm gap-filling doesn't suppress tails, outlier treatment doesn't remove genuine stress | Data Analytics | Analyze |  | Capital Tech: ES runs
8.4.2 | Subtask | Submit remediation methodology paper to MRM for validation | Model Validation | Collaborate | MRM sign-off | MRM
M8 Output → MRM-validated remediation methodologies: gap-fill, outlier treatment, adjustments, overrides, event calendar
M9 | Milestone | M9 — Work with Tech to Build Remediation Tools |  |  | Production remediation pipeline | Requires M8 methodology
9.1 | Task | Specify remediation tool requirements to Tech | Data Analytics | Develop | Tool spec → Risk Tech
9.1.1 | Subtask | Automated remediation pipeline: detect DQ issue (from Deliverable 2) → apply approved method → log before/after → produce audit trail | Data Analytics | Develop
9.1.2 | Subtask | Manual override interface: analyst reviews, selects treatment, provides justification — all logged with timestamp and approver | Data Analytics | Develop
9.2 | Task | Work with Tech to build and deploy remediation pipeline | Tech Build | Build (Tech) | Production pipeline | Risk Tech builds
9.2.1 | Subtask | Tech builds automated pipeline + manual override interface per Quant specification | Tech Build | Build (Tech) |  | Risk Tech builds
9.2.2 | Subtask | Validate Tech's implementation: run remediation on known test cases, verify audit trail completeness | Data Analytics | Analyze
M9 Output → Production remediation tools: automated pipeline + manual override — built by Tech, validated by Quant
M10 | Milestone | M10 — BAU Process for Historical Data Treatment |  |  | BAU remediation process | After M9 tools
10.1 | Task | Establish BAU process, policies, and procedures for applying historical treatments | Governance | Develop | BAU policy doc
10.1.1 | Subtask | Define when automated remediation applies vs. when manual review is required | Governance | Develop
10.1.2 | Subtask | Define approval workflow: who can approve overrides, what documentation is needed, escalation for material corrections | Governance | Develop |  | Risk Model
10.1.3 | Subtask | Define capital impact assessment requirement: any remediation that changes ES by more than threshold requires pre-deployment sign-off | Governance | Develop |  | Capital Tech
10.1.4 | Subtask | Document: policies, procedures, runbooks, audit trail requirements | Governance | Develop | BAU policy manual
M10 Output → Governed BAU remediation: automated + manual, approval workflows, capital-aware, documented
| Deliverable | Deliverable 4: Risk Factor Onboarding & Rederivation Process
| Output Summary | Outputs: End-to-end RF onboarding process (vendor → methodology → proxy → prod build → VaR impact → backtesting → NTE/TSV → sign-off → production) · Documented lifecycle for every new RF
| Sequence | M11 is the end-to-end process — each step is sequential within a single RF onboarding, but multiple RFs can be onboarded in parallel
M11 | Milestone | M11 — Establish End-to-End RF Onboarding Process |  |  | Onboarding process + completed RF builds
This is a repeatable process — every new RF (from WS-A Cat 2/5 gap register, or from future model changes) follows this pipeline. Build the process once, execute many times.
11.1 | Task | Vendor assessment & selection for new RF data | Sourcing | Gather | Vendor recommendation
11.1.1 | Subtask | Assess available vendor sources for the new RF: coverage, history depth, quality, cost | Sourcing | Analyze
11.1.2 | Subtask | Select vendor and negotiate data licensing — coordinate with Procurement | Sourcing | Collaborate |  | Business + Procurement
11.2 | Task | Vendor onboarding & data ingestion | Tech Collab | Collaborate | Data feed live | Risk Tech: ingestion
11.2.1 | Subtask | Work with Tech to build ingestion connector for new vendor/feed — parsing, validation, storage | Tech Collab | Collaborate |  | Risk Tech builds
11.2.2 | Subtask | Validate ingested data: completeness, format, reconcile against vendor-provided benchmarks | Data Analytics | Analyze
11.3 | Task | Develop RF methodology: how to build history | Risk Development | Develop | RF history methodology | RA: co-develop
11.3.1 | Subtask | Collaborate with RA to define derivation methodology: direct observation, model-implied, interpolated, constructed from components | Risk Development | Develop |  | RA
11.3.2 | Subtask | Collaborate with RA to define backfill strategy to 2007: vendor sourcing, curve reconstruction, or proxy extension | Risk Development | Develop |  | RA
11.4 | Task | Develop RF methodology: how to generate ongoing | Risk Development | Develop | RF generation methodology | RA + FO Quant Strat
11.4.1 | Subtask | Collaborate with RA and FO Quant Strat to define daily generation logic: source MDOs, transformation steps, shift type, carry treatment | Risk Development | Develop |  | RA + FO Quant Strat
11.5 | Task | Assign proxy (if direct history insufficient) | Data Analytics | Analyze | Proxy assignment
11.5.1 | Subtask | Apply proxy framework (Deliverable 1): identify candidate, validate, classify, produce lineage record | Data Analytics | Analyze |  | Proxy framework from D1
11.6 | Task | Work with Tech to build RF in production (history + ongoing generation + proxy) | Tech Build | Build (Tech) | RF in production | Risk Tech builds
11.6.1 | Subtask | Work with Tech to implement historical time series (direct + backfill + proxy splice) in production data warehouse | Tech Collab | Collaborate |  | Risk Tech builds
11.6.2 | Subtask | Work with Tech to implement daily generation logic in RF generation pipeline | Tech Collab | Collaborate |  | Risk Tech builds
11.6.3 | Subtask | Validate production output: compare against methodology PoC, confirm history and daily generation are correct | Data Analytics | Analyze
11.7 | Task | Assess VaR / ES impact of new RF | Data Analytics | Analyze | VaR impact report | Capital Tech: ES runs
11.7.1 | Subtask | Run ES with and without the new RF — quantify desk-level and firm-level capital impact | Data Analytics | Analyze |  | Capital Tech
11.8 | Task | Assess backtesting impact | Data Analytics | Analyze | Backtesting report
11.8.1 | Subtask | Run backtesting with new RF included — does exception count change? Do clustering patterns shift? | Data Analytics | Analyze
11.9 | Task | Produce NTE / TSV documentation | Risk Development | Develop | NTE/TSV → Risk Model | Risk Model
11.9.1 | Subtask | Prepare New Trade Event (NTE) or Time Series Validation (TSV) documentation per internal governance requirements | Risk Development | Develop
11.9.2 | Subtask | Submit to Risk Model / MRM for review and approval | Model Validation | Collaborate | MRM approval | MRM
11.10 | Task | Obtain sign-off for production deployment | Cross-Team | Collaborate | Production sign-off | Senior Mgmt
11.10.1 | Subtask | Present VaR impact, backtesting results, NTE/TSV approval — obtain sign-off from Risk Model, Capital, and senior management | Cross-Team | Collaborate
11.11 | Task | Deploy to production and confirm consumption | Tech Collab | Collaborate | RF live in production | Risk Tech
11.11.1 | Subtask | Work with Tech to activate the new RF in ES/VaR engines, confirm PLA includes it, confirm backtesting picks it up | Tech Collab | Collaborate |  | Risk Tech + Capital Tech
11.11.2 | Subtask | Post-deployment monitoring: two weeks of daily validation that the new RF behaves as expected in production | Data Analytics | Analyze
M11 Output → End-to-end RF onboarding process: repeatable pipeline from vendor to production, with full governance gate at each step
| Deliverable | Deliverable 5: Carry Removal
| Output Summary | Outputs: Carry applicability assessment · Three-scenario methodology · Decision tree · Impact analysis · Production implementation (daily + historical)
| Sequence | M12 (methodology with RA) → M13 (PoC + impact) → M14 (work with Tech for production) → M15 (BAU)
M12 | Milestone | M12 — Assess Carry & Build Methodology |  |  | Carry methodology + decision tree
12.1 | Task | Assess carry applicability per RF type | Data Analytics | Analyze | Applicability assessment | RA: co-develop
12.1.1 | Subtask | Collaborate with RA to determine which RF types have material carry: IR rates (roll-down), IR/FX/EQ vols (time decay), commodity (contango/backwardation), equity (dividends) | Risk Development | Analyze |  | RA
12.1.2 | Subtask | Quantify carry magnitude per RF type: what fraction of daily/10-day returns is carry vs. genuine market moves? Analyze across benign and stress periods | Data Analytics | Analyze
12.1.3 | Subtask | Collaborate with RA to build carry applicability decision tree: map each RF type to appropriate scenario based on data availability and carry mechanism | Risk Development | Develop | Decision tree | RA
12.2 | Task | Develop carry stripping methodologies with RA | Risk Development | Develop | Three-scenario methodology | RA: co-develop
12.2.1 | Subtask | Scenario A — Curve interpolation carry removal: collaborate with RA to use full curve snapshots to interpolate aged-tenor rate and subtract carry directly — implement in Python | Risk Development | Develop |  | RA
12.2.2 | Subtask | Scenario B — Black-Scholes √T theta approximation: collaborate with RA for vol surface time decay estimation — implement in Python, validate against FO theta | Risk Development | Develop |  | RA + FO: theta comparison
12.2.3 | Subtask | Scenario C — Rolling median statistical estimator: collaborate with RA for equity/commodity fallback — implement in Python with configurable window | Risk Development | Develop |  | RA
12.2.4 | Subtask | Collaborate with RA on 10-day carry: sum ten daily carry values (not naive 10× scaling) to capture intraperiod curve shape changes | Risk Development | Develop |  | RA
12.2.5 | Subtask | Collaborate with RA on regime-conditioned adaptive windowing for Scenario C: shorter windows during stress using CDX IG regime signal | Risk Development | Develop |  | RA
M12 Output → Three-scenario carry methodology with decision tree, 10-day aggregation, regime conditioning — developed with RA
M13 | Milestone | M13 — Build PoC & Assess Impact |  |  | Validated PoC + impact analysis + methodology paper | Requires M12
13.1 | Task | Build carry removal PoC in Python | Data Analytics | Build PoC | PoC results → demo
13.1.1 | Subtask | Implement all three scenarios end-to-end on representative RFs per asset class | Data Analytics | Build PoC
13.1.2 | Subtask | Validate against known carry decompositions from Front Office — confirm methodology produces sensible carry estimates | FO Collaboration | Analyze |  | FO: carry decomposition
13.2 | Task | Assess impact on downstream outputs | Data Analytics | Analyze | Impact report → Mgmt | Capital Tech: ES runs
13.2.1 | Subtask | Impact on return distributions: does carry removal eliminate systematic drift? Does it change tail shape? | Data Analytics | Analyze
13.2.2 | Subtask | Impact on PLA: re-run Spearman/KS-distance with carry-adjusted returns — quantify improvement per desk | Data Analytics | Analyze |  | PLA team
13.2.3 | Subtask | Impact on ES: compare current and stress period ES with/without carry stripping — quantify capital delta | Data Analytics | Analyze |  | Capital Tech
13.3 | Task | Document carry methodology paper and submit to MRM | Risk Development | Develop | Methodology paper → MRM | RA
13.3.1 | Subtask | Produce formal methodology paper: regulatory motivation, three scenarios, decision tree, 10-day aggregation, regime conditioning, impact analysis | Risk Development | Develop
13.3.2 | Subtask | Submit to MRM for independent validation — address challenges, obtain sign-off | Model Validation | Collaborate | MRM sign-off | MRM
M13 Output → Validated carry PoC + impact analysis + MRM-approved methodology paper
M14 | Milestone | M14 — Work with Tech to Implement Carry in Production |  |  | Carry-adjusted returns in production | Requires M13 + Tech resources
14.1 | Task | Work with Tech to implement carry removal in daily RF generation | Tech Collab | Collaborate | Daily carry pipeline | Risk Tech builds
14.1.1 | Subtask | Specify to Tech: integrate decision tree into daily pipeline, apply assigned scenario per RF, compute carry-adjusted 1-day and 10-day returns alongside raw | Data Analytics | Develop | Pipeline spec → Tech
14.1.2 | Subtask | Specify to Tech: store both raw and carry-adjusted, implement regime-conditioned window for Scenario C | Data Analytics | Develop
14.1.3 | Subtask | Tech builds daily carry pipeline; Quant validates: parallel run for 1+ month against PoC output | Tech Build | Build (Tech) |  | Risk Tech builds
14.2 | Task | Work with Tech to apply carry removal to full historical time series | Tech Collab | Collaborate | Historical carry-adjusted series | Risk Tech builds
14.2.1 | Subtask | Specify to Tech: run carry stripping retrospectively across all carry-applicable RFs, handle periods where Scenario A data is incomplete (fallback to C) | Data Analytics | Develop
14.2.2 | Subtask | Tech builds historical backfill pipeline; Quant validates consistency across full history | Tech Build | Build (Tech) |  | Risk Tech builds
14.3 | Task | Run capital impact and obtain sign-off | Cross-Team | Collaborate | Sign-off → production | Capital Tech + Senior Mgmt
14.3.1 | Subtask | Run ES with raw vs. carry-adjusted across current + stress periods — produce capital impact report | Data Analytics | Analyze | Capital impact report | Capital Tech
14.3.2 | Subtask | Obtain senior management sign-off; deploy carry-adjusted series to production with audit trail | Cross-Team | Collaborate | Production deployment | Senior Mgmt
M14 Output → Carry-adjusted returns in daily production + full historical backfill, validated, signed off, audit-trailed
| Deliverable | Deliverable 6: History Assessment & Strengthening
| Output Summary | Outputs: History inventory register · Assessment (good vs. bad) · Remediation options analysis · Strengthening & extension methodology · Extended histories to 2007
| Sequence | M15 (assess) → M16 (decide good/bad) → M17 (develop methodology with RA for bad) → M18 (work with Tech to execute) → M19 (BAU)
M15 | Milestone | M15 — Assess History, Data Lineage & Proxy Coverage |  |  | History inventory register
15.1 | Task | Catalog all historical time series and their lineage | Data Analytics | Gather | History inventory → M16 | Risk Tech: system access
15.1.1 | Subtask | Per RF: source system, start date, end date, frequency, gap count, derivation chain, proxy flag, transition status | Data Analytics | Gather
15.1.2 | Subtask | Assess coverage vs. 2007 stress lookback — quantify gap per RF, identify missing stress periods | Data Analytics | Analyze
15.1.3 | Subtask | Audit existing proxy relationships: document proxy, splice, justification — classify green/yellow/red | Data Analytics | Classify
15.1.4 | Subtask | Catalog benchmark transitions: LIBOR→SOFR, EONIA→€STR, CDOR→CORRA — status per RF | Data Analytics | Analyze
15.1.5 | Subtask | Catalog structural breaks: EM rebasings, corporate actions, index reconstitutions | Data Analytics | Analyze
15.2 | Task | Produce History Inventory Register | Data Analytics | Develop | Register → all teams
15.2.1 | Subtask | One row per RF: source, coverage, gaps, derivation, proxy details, transitions, readiness (G/Y/R) | Data Analytics | Develop
15.2.2 | Subtask | Summary analytics: coverage heatmap, proxy concentration, transition readiness, top-priority remediation targets | Data Analytics | Analyze |  | RA: ES materiality
M15 Output → History inventory register — the single view of what exists, what's missing, and what's broken
M16 | Milestone | M16 — Decide: Good vs. Bad — Assess Remediation Options |  |  | Decision register + remediation plan | Requires M15
16.1 | Task | Classify each RF history as Good or Bad | Data Analytics | Classify | Classification → M17
16.1.1 | Subtask | Good: sufficient depth (to 2007), acceptable quality (DQ green/yellow), direct data or validated proxy, benchmark transitions handled — no action needed | Data Analytics | Classify
16.1.2 | Subtask | Bad: insufficient depth, poor quality (DQ red), unvalidated proxy, unhandled transitions, proxy chains — requires remediation | Data Analytics | Classify
16.2 | Task | For each "Bad" RF, assess remediation options | Data Analytics | Analyze | Remediation options → M17 | RA
16.2.1 | Subtask | Option A — Source: vendor data exists but hasn't been procured — assess cost, timeline, quality | Data Analytics | Analyze
16.2.2 | Subtask | Option B — Construct: data can be derived from available raw data (constant-maturity rolling, vintage reconstruction, cross-source derivation) | Data Analytics | Analyze |  | RA: feasibility
16.2.3 | Subtask | Option C — Proxy: no direct or constructible data — assign proxy per Deliverable 1 framework | Data Analytics | Analyze |  | Proxy framework from D1
16.2.4 | Subtask | Option D — Accept gap: document that history cannot be extended, flag for regulatory discussion, quantify ES impact of truncated stress window | Data Analytics | Analyze |  | Capital Tech: ES impact
16.2.5 | Subtask | Per RF: recommend option, estimate effort, quantify capital impact of each option vs. status quo — prioritise by net capital benefit | Data Analytics | Analyze | Prioritised remediation plan
M16 Output → Per-RF decision (good/bad), recommended remediation option, prioritised by capital impact
M17 | Milestone | M17 — Develop Data Strengthening & History Extension Methodology |  |  | Extension methodologies → Tech | Requires M16 decisions
17.1 | Task | Collaborate with RA to develop construction methodologies | Risk Development | Develop | Construction methods | RA: co-develop
17.1.1 | Subtask | Constant-maturity rolling curve construction: for IR and commodity RFs from archived raw curve snapshots | Risk Development | Develop |  | RA
17.1.2 | Subtask | Vintage curve reconstruction: rebuild historical curves from available node points using current bootstrap methodology | Risk Development | Develop |  | RA
17.1.3 | Subtask | Cross-source derivation: construct RF from combinations of other available data (implied vol from options, credit spread from bond yield minus swap) | Risk Development | Develop |  | RA
17.2 | Task | Collaborate with RA to develop benchmark transition methodologies | Risk Development | Develop | Transition methods → Tech | RA + FO Models
17.2.1 | Subtask | LIBOR→SOFR: direct splice with spread adjustment, reconstructed SOFR backcast (ISDA spreads), or hybrid — validate consistency with FO pricing | Risk Development | Develop |  | RA + FO Models
17.2.2 | Subtask | EONIA→€STR, CDOR→CORRA: apply same framework per currency | Risk Development | Develop |  | RA
17.2.3 | Subtask | Validate no artificial jumps at splice points — inspect return distributions, confirm ES not dominated by transition-day artefact | Data Analytics | Analyze
17.3 | Task | Validate all methodologies and submit to MRM | Model Validation | Collaborate | MRM sign-off | MRM
17.3.1 | Subtask | Confirm constructed/extended histories preserve tail behaviour, vol clustering, cross-asset correlation | Data Analytics | Analyze | Validation report
17.3.2 | Subtask | Submit methodology paper to MRM — obtain sign-off | Model Validation | Collaborate |  | MRM
M17 Output → MRM-validated construction and transition methodologies — ready for Tech execution
M18 | Milestone | M18 — Work with Tech to Execute History Extension |  |  | Extended histories in production | Requires M17 + vendor data from sourcing
18.1 | Task | Work with Tech to ingest sourced historical backfill data | Tech Collab | Collaborate | Sourced data ingested | Risk Tech builds
18.1.1 | Subtask | Coordinate with Tech to ingest vendor historical archives; validate against benchmarks at splice points | Tech Collab | Collaborate |  | Risk Tech
18.2 | Task | Work with Tech to implement construction methodologies in production | Tech Build | Build (Tech) | Constructed histories | Risk Tech builds
18.2.1 | Subtask | Tech implements constant-maturity rolling, vintage reconstruction, cross-source derivation per Quant specification — with configurable parameters and audit trail | Tech Build | Build (Tech) |  | Risk Tech builds
18.2.2 | Subtask | Validate Tech's output: compare against methodology PoC, confirm statistical properties preserved | Data Analytics | Analyze
18.3 | Task | Work with Tech to implement benchmark transition adjustments | Tech Build | Build (Tech) | Transition-adjusted histories | Risk Tech builds
18.3.1 | Subtask | Tech implements LIBOR→SOFR and other transitions per Quant specification; Quant validates splice points | Tech Build | Build (Tech) |  | Risk Tech builds
18.4 | Task | Run capital impact and obtain sign-off | Cross-Team | Collaborate | Sign-off → production | Capital Tech + Senior Mgmt
18.4.1 | Subtask | Run ES with old vs. new (extended) data — stress period sensitivity, capital delta decomposition | Data Analytics | Analyze | Capital impact report | Capital Tech
18.4.2 | Subtask | Obtain sign-off; deploy extended histories to production | Cross-Team | Collaborate |  | Senior Mgmt
M18 Output → All in-scope RFs extended to 2007, benchmark transitions handled, deployed to production with audit trail
M19 | Milestone | M19 — BAU History Maintenance & Ongoing Assessment |  |  | BAU history process | After M18
19.1 | Task | Establish BAU process for ongoing history maintenance | Governance | Develop | BAU process doc
19.1.1 | Subtask | Daily: automated data append, DQ scoring on new observations | Governance | Develop
19.1.2 | Subtask | Monthly: proxy drift review, gap detection, new RF onboarding queue | Governance | Develop
19.1.3 | Subtask | Quarterly: history completeness audit, proxy coverage reconciliation | Governance | Develop
19.1.4 | Subtask | Annual: deep audit — full lineage review, stress-period revalidation, regulatory exam prep | Governance | Develop
19.1.5 | Subtask | Change control: any data change (proxy swap, correction, backfill) requires capital impact assessment before production deployment | Governance | Develop |  | Capital Tech
19.1.6 | Subtask | Document: policies, procedures, runbooks, audit trail requirements | Governance | Develop | BAU manual
M19 Output → Governed BAU: daily/monthly/quarterly/annual cadence, change-controlled, capital-aware, audit-ready