## Quant Data
# | Level | Description | Primary Owner | FO Tech | Risk Tech | Capital Tech | Risk Model | FO Models | PLA / BT | Duration | Dependency
QD-A | Deliverable | Risk Factor Eligibility Test (RFET) Framework | Quant Data | ● | ● | ○ | ● | ● | ● | 26–40 weeks | —
A.1 | Milestone | Trading Desk Identification & Scope | Business/SME |  |  |  |  | ● |  | 4–6 weeks | —
A.1.1 | Task | Obtain Volcker desk structure (IR Options, IR Swaps, FX Spot, FX Forward, EM, Agencies, Inflation, etc.) | Business/SME |  |  |  |  | ● |  | 1 week | —
A.1.2 | Task | Run preliminary SA vs. IMA capital comparison per desk | Quant Data |  |  | ● | ● |  |  | 2 weeks | A.1.1
A.1.3 | Task | Determine which desks justify IMA — document inclusion/exclusion rationale | Business/SME |  |  |  |  | ● |  | 1 week | A.1.2
A.1.3a | Subtask | Map each desk to NPR regulatory trading desk definition (head trader, strategy, limits) | Business/SME |  |  |  |  | ● |  | 3 days | A.1.2
A.1.3b | Subtask | Document desk-level risk factor ownership: which RFs belong to which desk | Quant Data |  | ● |  | ● |  |  | 3 days | A.1.3a
A.2 | Milestone | Risk Factor Identification & MDO Mapping | Quant Data | ● | ● |  | ● | ● |  | 8–12 weeks | A.1
A.2.1 | Task | Extract all Market Data Objects (MDOs) from FO pricing systems | Quant Data | ● |  |  |  | ● |  | 2 weeks | A.1
A.2.1a | Subtask | Connect to FO pricers — extract MDO consumption logs per desk | FO Tech | ● | [5 empty] | 1 week | A.1
A.2.1b | Subtask | Catalog every MDO by type: IR curve, FX spot, vol surface, credit spread, basis, correlation, dividend | Quant Data | [6 empty] | 1 week | A.2.1a
A.2.2 | Task | Extract all Risk Factors from risk model catalog | Quant Data |  | ● |  | ● |  |  | 2 weeks | A.1
A.2.2a | Subtask | Pull complete RF catalog from risk engine: name, type, asset class, tenor/strike grid | Risk Tech |  | ● |  |  |  |  | 1 week | A.1
A.2.2b | Subtask | Map each RF to NPR risk class (GIRR, CSR, FX, EQ, COMM) | Quant Data |  |  |  | ● |  |  | 3 days | A.2.2a
A.2.3 | Task | Classify every MDO into 4 categories | Quant Data |  |  |  | ● | ● |  | 3 weeks | A.2.1
A.2.3a | Subtask | Category 1: Mapped — MDO directly corresponds to existing RF | Quant Data | [6 empty] | 1 week | A.2.1
A.2.3b | Subtask | Category 2: Not mapped — MDO needs a new RF (gap → create) | Quant Data |  | ● |  | ● |  |  | 1 week | A.2.3a
A.2.3c | Subtask | Category 3: Not mapped — MDO is a pricing input, NOT a risk factor (fixings, resets, impact pricing) | Quant Data |  |  |  |  | ● |  | 3 days | A.2.3b
A.2.3d | Subtask | Category 4: FO/Risk disconnect — structural model gap (e.g., FO uses Treasury, Risk uses Sovereign) | Quant Data |  |  |  | ● | ● | ● | 1 week | A.2.3c
A.2.4 | Task | Create new RFs for Category 2 gaps | Quant Data | ● | ● |  | ● |  |  | 3 weeks | A.2.3
A.2.4a | Subtask | Define RF spec: name, type, tenor/strike grid, source, update frequency | Quant Data |  |  |  | ● |  |  | 1 week | A.2.3
A.2.4b | Subtask | Build data pipeline for new RFs and backfill history (target: back to 2007) | Quant Data |  | ● |  |  |  |  | 2 weeks | A.2.4a
A.2.4c | SubSubtask | Depends on: Risk Tech to integrate new RFs into risk engine | Risk Tech |  | ● |  |  |  |  | 1 week | A.2.4b
A.2.4d | SubSubtask | Depends on: FO Tech to confirm MDO-to-new-RF linkage in pricing systems | FO Tech | ● | [5 empty] | 3 days | A.2.4c
A.2.5 | Task | Initiate FO/Risk disconnect remediation (Category 4) | Business/SME | ● | ● |  | ● | ● | ● | Ongoing | A.2.3
A.2.5a | Subtask | Document each disconnect: FO model, Risk model, gap, proposed fix | Quant Data |  |  |  | ● | ● |  | 2 weeks | A.2.3
A.2.5b | Subtask | Prioritize by PLA impact — which disconnects cause the most HPL vs. RTPL noise | Quant Data | [5 empty] | ● | 1 week | A.2.5a
A.2.5c | SubSubtask | Depends on: FO Models team to upgrade pricing models (e.g., RVF+ → Full Config for credit) | FO Models |  |  |  |  | ● |  | Varies | A.2.5b
A.2.5d | SubSubtask | Depends on: Risk Model team to align risk factor representation with upgraded FO model | Risk Model |  |  |  | ● |  |  | Varies | A.2.5c
A.2.5e | SubSubtask | Depends on: PLA team to validate alignment improvement after model changes | PLA / BT | [5 empty] | ● | 2 weeks | A.2.5d
A.3 | Milestone | RF Taxonomy, Metadata & Liquidity Horizons | Quant Data | ● | ● | ● | ● |  |  | 6–8 weeks | A.2
A.3.1 | Task | Define RF taxonomy and granularity standards | Quant Data |  |  |  | ● |  |  | 2 weeks | A.2
A.3.1a | Subtask | Define asset class hierarchy: GIRR, CSR_NS, CSR_SEC, FX, EQ, COMM → sub-types | Quant Data |  |  |  | ● |  |  | 3 days | A.2
A.3.1b | Subtask | Define RF attributes: name, type, currency, tenor, maturity, strike, issuer, sector, region | Quant Data |  |  |  | ● |  |  | 3 days | A.3.1a
A.3.1c | Subtask | Define return type: overlapping vs. non-overlapping, absolute vs. relative, log vs. simple | Quant Data |  |  |  | ● |  |  | 2 days | A.3.1b
A.3.2 | Task | Build RF metadata repository (golden source) | Quant Data | ● | ● |  |  |  |  | 2 weeks | A.3.1
A.3.2a | SubSubtask | Depends on: Risk Tech to build API layer for ES/SES/VaR engine consumption | Risk Tech |  | ● |  |  |  |  | 1 week | A.3.2
A.3.2b | SubSubtask | Depends on: Capital Tech to consume RF metadata for IMCC/SES classification | Capital Tech |  |  | ● |  |  |  | 3 days | A.3.2a
A.3.3 | Task | Assign liquidity horizons to all RFs (10, 20, 40, 60, 120 days) | Quant Data |  |  | ● | ● |  |  | 2 weeks | A.3.1
A.3.3a | Subtask | Map each RF to prescribed LH tier per NPR rules; handle edge cases (xccy basis → 60d, multi-underlying → weighted avg) | Quant Data |  |  |  | ● |  |  | 1 week | A.3.1
A.3.3b | Subtask | Document justification for each LH assignment (supervisor will challenge) | Quant Data |  |  |  | ● |  |  | 3 days | A.3.3a
A.3.3c | SubSubtask | Depends on: Capital Tech — LH feeds directly into ES shock scaling in capital calculation | Capital Tech |  |  | ● |  |  |  | — | A.3.3b
A.3.4 | Task | Identify and document all proxy relationships | Quant Data |  | ● |  | ● | ● |  | 2 weeks | A.3.3
A.3.4a | Subtask | For each proxy: document original RF → proxy RF → justification → track record → review date | Quant Data | [6 empty] | 1 week | A.3.3
A.3.4b | Subtask | Classify: green (same data), yellow (operational gap), red (structural mismatch) | Quant Data |  |  |  | ● |  |  | 3 days | A.3.4a
A.3.4c | Subtask | Validate proxy quality: correlation, vol ratio, regime behavior | Quant Data |  | ● |  | ● |  |  | 1 week | A.3.4b
A.4 | Milestone | RFET Qualitative Test Engine | Quant Data | ● | ● |  | ● |  |  | 6–8 weeks | A.3
A.4.1 | Task | Design qualitative test methodology (7 quality standards, pass/fail criteria) | Quant Data |  |  |  | ● |  |  | 2 weeks | A.3
A.4.2 | Task | Build automated qualitative test engine (all 7 checks) | Quant Data | ● | ● |  | ● |  |  | 3 weeks | A.4.1
A.4.2a | Subtask | Real market price verification, update frequency, source reliability, vol/correlation capture, model-derived flag, proxy justification | Quant Data | ● | ● |  | ● |  |  | 3 weeks | A.4.1
A.4.2b | SubSubtask | Depends on: Risk Tech to schedule quarterly automation and integrate into RF metadata | Risk Tech |  | ● |  |  |  |  | 3 days | A.4.2a
A.5 | Milestone | RFET Quantitative Test Engine & RPO Infrastructure | Quant Data | ● | ● | ● | ● |  | ● | 10–14 weeks | A.3
A.5.1 | Task | Source Real Price Observations (RPOs) — exchanges, TRACE, DTCC, Markit, Bloomberg | Quant Data |  | ● |  |  |  |  | 3 weeks | A.3
A.5.1a | Subtask | Identify RPO sources, negotiate data agreements, identify audit requirements for 3rd-party providers | Quant Data |  | ● |  |  |  |  | 3 weeks | A.3
A.5.1b | SubSubtask | Depends on: FO Tech / Business for vendor contract execution and licensing | FO Tech | ● | [5 empty] | 2 weeks | A.5.1a
A.5.2 | Task | Build RPO storage, ingestion & deduplication infrastructure | Quant Data | ● | ● |  |  |  |  | 3 weeks | A.5.1
A.5.2a | Subtask | Design schema, build daily ingestion pipelines, implement max-1-per-day dedup, build DQ checks on incoming RPOs | Quant Data | ● | ● |  |  |  |  | 3 weeks | A.5.1
A.5.2b | Subtask | Backfill 12+ months of RPOs for initial classification run | Quant Data |  | ● |  |  |  |  | 1 week | A.5.2a
A.5.3 | Task | Map RPOs → RF buckets (own vs. standard bucketing per NPR) | Quant Data |  | ● |  | ● |  |  | 3 weeks | A.5.2
A.5.3a | Subtask | Define bucketing approach per RF type, build automated RPO→bucket→RF mapping engine | Quant Data | ● | ● |  | ● |  |  | 3 weeks | A.5.2
A.5.4 | Task | Build quantitative counting engine (thresholds: ≥24 for LH≤20d, ≥16 for LH>20d) | Quant Data | ● |  |  | ● |  |  | 2 weeks | A.5.3
A.5.5 | Task | Combine qual + quant → classification: Modellable / Type A / Type B | Quant Data | ● |  | ● | ● |  |  | 1 week | A.5.4
A.5.5a | SubSubtask | Depends on: Capital Tech — classification feeds directly into IMCC vs. SES routing | Capital Tech |  |  | ● |  |  |  | — | A.5.5
A.5.5b | SubSubtask | Depends on: PLA team — classification affects which RFs are in ES model for RTPL | PLA / BT | [5 empty] | ● | — | A.5.5
A.5.6 | Task | Build Modellable vs. Non-Modellable Dashboard with drill-down and early warning | Quant Data | ● | ● |  |  |  | ● | 2 weeks | A.5.5
A.5.6a | Subtask | By desk, by asset class, trend over time, approaching-threshold alerts, estimated SES capital impact per NMRF | Quant Data | ● |  | ● |  |  | ● | 2 weeks | A.5.5
A.6 | Milestone | RF Metadata Consolidation & Ongoing Governance | Quant Data | ● | ● | ● | ● |  | ● | 4 weeks | A.5
A.6.1 | Task | Consolidate all RF metadata into single golden source with API for downstream consumers | Quant Data | ● | ● | ● |  |  |  | 2 weeks | A.5
A.6.2 | Task | Establish quarterly RFET refresh, trigger-based reclassification, escalation paths | Quant Data |  |  |  | ● |  | ● | 2 weeks | A.6.1
A.6.2a | SubSubtask | Depends on: Capital Tech — reclassification triggers re-routing between IMCC and SES | Capital Tech |  |  | ● |  |  |  | — | A.6.2
QD-B | Deliverable | Carry Removal from Risk Factors | Quant Data | ● | ● | ● | ● | ● | ● | 28–40 weeks | —
B.1 | Milestone | Assess Carry Removal Requirements | Quant Data |  |  |  | ● | ● | ● | 4–6 weeks | —
B.1.1 | Task | Define time effects per asset class (roll-down, forward points, dividends, theta, contango, spread carry) | Quant Data |  |  |  | ● |  |  | 2 weeks | —
B.1.2 | Task | Determine which RFs require carry removal — materiality assessment | Quant Data |  | ● |  | ● |  |  | 2 weeks | B.1.1
B.1.2a | Subtask | Quantify carry-vs-market-move ratio across asset classes; build decision tree: RF type → carry Y/N → scenario | Quant Data |  | ● |  | ● |  |  | 2 weeks | B.1.1
B.1.3 | Task | Determine carry horizon: 1-day only vs. 10-day (sum of 10 × 1-day, not naive scaling) | Quant Data |  |  |  | ● |  |  | 1 week | B.1.2
B.1.3a | SubSubtask | Depends on: PLA team — 1-day carry feeds HPL/RTPL; must confirm PLA test sensitivity | PLA / BT | [5 empty] | ● | — | B.1.3
B.1.3b | SubSubtask | Depends on: Capital Tech — 10-day carry feeds ES base horizon scaling | Capital Tech |  |  | ● |  |  |  | — | B.1.3
B.2 | Milestone | Build Carry Removal Methodology | Quant Data |  | ● |  | ● |  |  | 6–10 weeks | B.1
B.2.1 | Task | Design Scenario A: Observable carry from term structure (IR, FX, Commodity forwards) | Quant Data |  | ● |  | ● |  |  | 3 weeks | B.1
B.2.1a | Subtask | IR: interpolate aged-tenor rate from curve snapshots; FX: forward points from rate differential; Comm: forward curve roll | Quant Data |  | ● |  | ● |  |  | 3 weeks | B.1
B.2.2 | Task | Design Scenario B: Model-implied carry for vol surfaces (√T theta approximation) | Quant Data |  | ● |  | ● |  |  | 2 weeks | B.2.1
B.2.3 | Task | Design Scenario C: Statistical carry estimator — rolling median with regime conditioning (CDX IG signal) | Quant Data |  | ● |  | ● |  |  | 2 weeks | B.2.2
B.2.4 | Task | Build decision tree: asset class → scenario; define fallback chain (A → B → C) | Quant Data |  |  |  | ● |  |  | 1 week | B.2.3
B.3 | Milestone | Build Daily Carry Removal in RF Generation | Quant Data | ● | ● |  | ● | ● | ● | 6–8 weeks | B.2
B.3.1 | Task | Build daily carry computation module (COB snapshot → compute carry → next day subtract → stripped return) | Quant Data | ● | ● |  | ● |  |  | 3 weeks | B.2
B.3.1a | Subtask | Store carry component and carry-stripped return separately (audit trail) | Quant Data | ● | ● |  |  |  |  | — | B.3.1
B.3.2 | Task | Integrate carry-stripped returns into HPL and RTPL pipelines | Quant Data | ● | ● |  |  | ● | ● | 2 weeks | B.3.1
B.3.2a | Subtask | Critical: HPL and RTPL must consume SAME carry estimate — single source, not independently computed | Quant Data | ● |  |  |  | ● | ● | — | B.3.1
B.3.2b | SubSubtask | Depends on: FO Tech to modify HPL pipeline to consume carry-stripped RF returns | FO Tech | ● | [5 empty] | 1 week | B.3.2a
B.3.2c | SubSubtask | Depends on: Risk Tech to modify RTPL pipeline to consume carry-stripped RF returns | Risk Tech |  | ● |  |  |  |  | 1 week | B.3.2b
B.3.2d | SubSubtask | Depends on: PLA team to validate KS statistic improvement on carry-stripped streams | PLA / BT | [5 empty] | ● | 2 weeks | B.3.2c
B.3.3 | Task | Compute 10-day carry for ES base horizon (sum of 10 consecutive 1-day carries) | Quant Data | ● |  | ● | ● |  |  | 1 week | B.3.2
B.4 | Milestone | Build Historical Carry Removal for ES Calibration | Quant Data | ● | ● | ● | ● |  |  | 8–12 weeks | B.2
B.4.1 | Task | Assess historical MDO availability for carry computation (back to 2007) | Quant Data |  | ● |  |  |  |  | 2 weeks | B.2
B.4.1a | Subtask | Identify gaps by asset class × year; determine proxy approach for missing historical MDOs | Quant Data |  | ● |  | ● |  |  | 2 weeks | B.2
B.4.2 | Task | Compute historical carry estimates for full history (Scenario A/B/C per RF) | Quant Data |  | ● |  | ● |  |  | 4 weeks | B.4.1
B.4.3 | Task | Produce carry-stripped historical RF return series (1-day and 10-day) | Quant Data | ● | ● | ● | ● |  |  | 2 weeks | B.4.2
B.4.3a | SubSubtask | Depends on: Capital Tech — ES engine must consume carry-stripped historical series | Capital Tech |  |  | ● |  |  |  | 1 week | B.4.3
B.4.3b | SubSubtask | Depends on: Risk Tech — stress period selection may shift on carry-stripped data; re-validate | Risk Tech |  | ● |  |  |  |  | 3 days | B.4.3a
B.5 | Milestone | Technology Implementation: EMR & MARS | Quant Data | ● | ● | ● |  |  |  | 8–10 weeks | B.3
B.5.1 | Task | Architecture decision: on-the-fly calculation vs. pre-stored shifts vs. hybrid | Quant Data | ● | ● | ● | ● |  |  | 2 weeks | B.3
B.5.2 | Task | Implement carry removal in EMR (RF ingestion, ES engine, RTPL generation, reconciliation) | Quant Data | ● | ● |  |  |  |  | 3 weeks | B.5.1
B.5.2a | SubSubtask | Depends on: Risk Tech to extend EMR platform for carry-stripped data channel | Risk Tech |  | ● |  |  |  |  | 3 weeks | B.5.1
B.5.3 | Task | Implement carry removal in MARS (data layer, VaR/ES engines, cross-platform reconciliation) | Quant Data | ● | ● |  |  |  |  | 3 weeks | B.5.2
B.5.3a | SubSubtask | Depends on: Risk Tech to extend MARS platform and reconcile with EMR | Risk Tech |  | ● |  |  |  |  | 3 weeks | B.5.2
B.6 | Milestone | Validation, Documentation & Go-Live | Quant Data | ● | ● | ● | ● | ● | ● | 4–6 weeks | B.5
B.6.1 | Task | End-to-end validation: PLA improvement, ES impact, backtesting exception analysis, 30-day parallel run | Quant Data | ● |  | ● | ● |  | ● | 30 days | B.5
B.6.2 | Task | Documentation: methodology + technology + governance package for supervisor | Quant Data |  |  |  | ● |  |  | 2 weeks | B.6.1
B.6.3 | Task | Production cutover: switch HPL/RTPL/ES to carry-stripped; 5-day hypercare | Quant Data | ● | ● | ● |  | ● | ● | 1 week | B.6.2
B.6.3a | SubSubtask | Depends on: FO Tech — confirm HPL switchover; FO Models — confirm no pricing impact | FO Tech | ● |  |  |  | ● |  | 1 day | B.6.2
B.6.3b | SubSubtask | Depends on: PLA team — confirm PLA test running clean on carry-stripped data post-cutover | PLA / BT | [5 empty] | ● | 5 days | B.6.3a
QD-C | Deliverable | History Strengthening & Proxy Framework | Quant Data | ● | ● | ● | ● | ● | ● | 28–42 weeks | —
C.1 | Milestone | Proxy Framework, Justification & Lineage to 2007 | Quant Data | ○ | ● |  | ● | ● |  | 10–14 weeks | —
C.1.1 | Task | Inventory all proxy relationships: original RF → proxy RF → type → cause → documented Y/N | Quant Data |  | ● |  | ● | ● |  | 2 weeks | —
C.1.2 | Task | Assess proxy quality: correlation, vol ratio, regime behavior → green/yellow/red classification | Quant Data |  | ● |  | ● |  |  | 2 weeks | C.1.1
C.1.3 | Task | Enhance yellow/red proxies: find better candidates, source direct data, build improved methodology | Quant Data |  | ● |  | ● | ● |  | 4 weeks | C.1.2
C.1.3a | SubSubtask | Depends on: FO Models — some proxies are caused by FO model limitations (e.g., missing credit sensitivity) | FO Models |  |  |  |  | ● |  | — | C.1.2
C.1.3b | SubSubtask | Depends on: Risk Model — some proxies need risk model RF granularity upgrade (rating → sector → issuer) | Risk Model |  |  |  | ● |  |  | — | C.1.2
C.1.4 | Task | Build complete proxy lineage back to 2007: historical mapping table with effective dates, spliced series, validation | Quant Data | ● | ● |  | ● |  |  | 4 weeks | C.1.3
C.2 | Milestone | Fix Historical Data Quality & Adjust Time Series | Quant Data | ● | ● |  | ● |  |  | 8–12 weeks | C.1
C.2.1 | Task | Comprehensive historical DQ audit: missing dates, stale prices, outliers, insufficient history, redenomination events | Quant Data |  | ● |  | ● |  |  | 3 weeks | C.1
C.2.2 | Task | Fix missing data and stale prices (interpolation, proxy fill, winsorization — all with audit trail) | Quant Data | ● | ● |  | ● |  |  | 3 weeks | C.2.1
C.2.3 | Task | Adjust for current instrument universe: LIBOR→SOFR transition, post-crisis credit names, new EM currencies, corporate actions | Quant Data |  | ● |  | ● | ● |  | 3 weeks | C.2.2
C.2.3a | SubSubtask | Depends on: FO Models — SOFR-adjusted history must be consistent with current FO pricing model assumptions | FO Models |  |  |  |  | ● |  | — | C.2.2
C.2.3b | SubSubtask | Depends on: Risk Model — adjusted history must be consistent with risk model RF definitions | Risk Model |  |  |  | ● |  |  | — | C.2.2
C.3 | Milestone | Strengthen & Extend RF History | Quant Data | ● | ● |  | ● |  |  | 6–8 weeks | C.2
C.3.1 | Task | Assess history length per RF against ES requirements (current + stress period back to 2007) | Quant Data |  | ● |  | ● |  |  | 2 weeks | C.2
C.3.2 | Task | Extend via direct data sourcing (Bloomberg, Refinitiv, Markit, ICE — backfill licenses) | Quant Data | ● | ● |  |  |  |  | 3 weeks | C.3.1
C.3.2a | SubSubtask | Depends on: FO Tech / Business for vendor contract execution | FO Tech | ● | [5 empty] | 2 weeks | C.3.1
C.3.3 | Task | Extend via proxy/synthetic construction where direct data unavailable (regression-based, component-based) | Quant Data |  | ● |  | ● |  |  | 3 weeks | C.3.2
C.3.3a | Subtask | Validate extended series: out-of-sample testing, stress period plausibility, tail property preservation | Quant Data |  | ● |  | ● |  |  | 1 week | C.3.3
C.4 | Milestone | Advanced DQ Framework (4-Tier Early Warning) | Quant Data | ● | ● |  | ● |  | ● | 8–10 weeks | C.2
C.4.1 | Task | Design 4-tier framework: Deterministic → Statistical → Peer-Group → ML Triage | Quant Data | ● |  |  | ● |  |  | 2 weeks | C.2
C.4.2 | Task | Build Tier 1: missing data, stale prices, outliers, calendar validation, duplicates | Quant Data | ● | ● |  |  |  |  | 2 weeks | C.4.1
C.4.3 | Task | Build Tier 2: Z-score, volatility regime, autocorrelation, distribution shift (KS test) | Quant Data | ● |  |  | ● |  |  | 2 weeks | C.4.2
C.4.4 | Task | Build Tier 3: peer-group correlation, sector-vs-name divergence, basis monitoring, proxy tracking | Quant Data | ● |  |  | ● |  |  | 2 weeks | C.4.3
C.4.5 | Task | Build Tier 4: XGBoost triage model + alerting dashboard + daily summary + trend reporting | Quant Data | ● |  |  | ● |  |  | 2 weeks | C.4.4
C.4.5a | SubSubtask | Depends on: PLA team — DQ alerts should flag when issues could cause backtesting/PLA failures | PLA / BT | [5 empty] | ● | — | C.4.5
C.5 | Milestone | Integrate Strengthened History into ES, VaR & Capital | Quant Data | ● | ● | ● | ● |  | ● | 6–8 weeks | C.3
C.5.1 | Task | Replace raw history with quality-checked, proxy-lineage-complete, extended series in ES/VaR data warehouse | Quant Data | ● | ● | ● |  |  |  | 3 weeks | C.3
C.5.1a | SubSubtask | Depends on: Risk Tech — ES/VaR engines must switch to updated data source | Risk Tech |  | ● |  |  |  |  | 1 week | C.5.1
C.5.1b | SubSubtask | Depends on: Capital Tech — IMCC/SES must consume updated classification + history | Capital Tech |  |  | ● |  |  |  | 1 week | C.5.1a
C.5.2 | Task | Re-run ES stress period selection; compute ES impact (old vs. new history); parallel capital calc | Quant Data |  |  | ● | ● |  |  | 2 weeks | C.5.1
C.5.3 | Task | Build DQ-gated capital production: pre-calc DQ gate, fallback logic, daily sign-off workflow | Quant Data | ● | ● | ● | ● |  | ● | 2 weeks | C.5.2
C.5.3a | SubSubtask | Depends on: PLA team — integrate DQ metrics into backtesting attribution (can DQ issues explain exceptions?) | PLA / BT | [5 empty] | ● | — | C.5.3
C.6 | Milestone | Ongoing Governance: Proxy, History & DQ Operations | Quant Data | ○ | ● |  | ● |  | ● | 4 weeks | C.5
C.6.1 | Task | Establish quarterly proxy review, proxy promotion path, new proxy onboarding approval | Quant Data |  |  |  | ● |  |  | 2 weeks | C.5
C.6.2 | Task | Establish daily append, monthly review, annual deep audit, automated gap monitoring | Quant Data | ● | ● |  | ● |  |  | 2 weeks | C.6.1

## RFET Project Plan
# | Level | Description | Primary Owner | Tech | Data Eng | Quant | Business/SME | Duration | Dependency | Status
D1 | Deliverable | Identify Trading Desks in Scope for IMA | Business/SME | ● | ○ | ○ | ● | 4–6 weeks | —
M1.1 | Milestone | Trading Desk Scope Defined & Approved | Business/SME |  |  |  | ● | Week 4 | —
T1.1.1 | Task | Obtain current Volcker trading desk structure | Business/SME |  |  |  | ● | 1 week | —
S1.1.1a | Subtask | Identify all desks under Rates & FX umbrella: IR Options, IR Swaps, FX Spot, FX Forward, EM, Agencies, Inflation | Business/SME |  |  |  | ● | 3 days | —
S1.1.1b | Subtask | Identify all desks under Credit, Equity, Commodities, Munis | Business/SME |  |  |  | ● | 3 days | —
S1.1.1c | Subtask | Document desk hierarchy: legal entity, business line, Volcker desk, sub-desk | Business/SME |  |  |  | ● | 2 days | —
B1.1.1 | BCA | Desk structure document reviewed and signed off by desk heads and risk management | Business/SME |  |  |  | ● |  | S1.1.1c
T1.1.2 | Task | Determine IMA eligibility intent per desk | Business/SME |  |  | ● | ● | 2 weeks | T1.1.1
S1.1.2a | Subtask | Run preliminary SA vs. IMA capital comparison per desk (order of magnitude) | Quant |  |  | ● | ○ | 1 week | T1.1.1
S1.1.2b | Subtask | Identify desks where IMA capital savings justify the implementation cost | Business/SME |  |  | ● | ● | 3 days | S1.1.2a
S1.1.2c | Subtask | Document rationale for inclusion/exclusion of each desk from IMA scope | Business/SME |  |  |  | ● | 3 days | S1.1.2b
B1.1.2 | BCA | IMA desk scope approved by CRO and CFO; documented in scope memo | Business/SME |  |  |  | ● |  | S1.1.2c
T1.1.3 | Task | Map desk structure to regulatory trading desk definition | Quant |  |  | ● | ● | 1 week | T1.1.2
S1.1.3a | Subtask | Confirm each desk meets NPR trading desk definition (head trader, clear strategy, limits) | Business/SME |  |  |  | ● | 3 days | T1.1.2
S1.1.3b | Subtask | Document desk-level risk factor ownership: which RFs belong to which desk | Quant |  |  | ● | ○ | 3 days | S1.1.3a
B1.1.3 | BCA | Regulatory desk mapping document completed and reviewed by compliance | Business/SME |  |  |  | ● |  | S1.1.3b
D2 | Deliverable | Risk Factor Identification & MDO Mapping | Data Eng | ● | ● | ● | ● | 8–12 weeks | D1
M2.1 | Milestone | Complete MDO Inventory Across All In-Scope Desks | Data Eng | ● | ● |  | ● | Week 4 | D1
T2.1.1 | Task | Extract all Market Data Objects (MDOs) used in FO pricers | Data Eng | ● | ● |  | ○ | 2 weeks | D1
S2.1.1a | Subtask | Connect to FO pricing systems and extract MDO consumption logs per desk | Tech | ● | ● |  |  | 1 week | D1
S2.1.1b | Subtask | Catalog every MDO by type: IR curve, FX spot, vol surface, credit spread, basis, correlation, dividend | Data Eng |  | ● |  |  | 1 week | S2.1.1a
S2.1.1c | Subtask | Tag each MDO with source system, update frequency, data vendor, and desk consumer | Data Eng |  | ● |  |  | 3 days | S2.1.1b
B2.1.1 | BCA | Complete MDO inventory spreadsheet delivered and validated by desk quants | Data Eng |  | ● |  | ● |  | S2.1.1c
T2.1.2 | Task | Extract all Risk Factors used in the risk model | Quant |  | ● | ● |  | 2 weeks | D1
S2.1.2a | Subtask | Pull complete risk factor catalog from risk engine: name, type, asset class, tenor grid, strike grid | Tech | ● |  | ● |  | 1 week | D1
S2.1.2b | Subtask | Map each risk factor to its risk class (GIRR, CSR, FX, EQ, COMM) per NPR taxonomy | Quant |  |  | ● |  | 3 days | S2.1.2a
S2.1.2c | Subtask | Identify risk factors that exist in risk but have no corresponding MDO in FO | Quant |  | ● | ● |  | 3 days | S2.1.2b
B2.1.2 | BCA | Complete risk factor catalog delivered; cross-referenced with MDO inventory | Quant |  |  | ● |  |  | S2.1.2c
M2.2 | Milestone | MDO → RF Mapping Complete with Gap Analysis | Quant |  | ● | ● | ● | Week 8 | M2.1
T2.2.1 | Task | Classify every MDO into one of four categories | Quant |  | ● | ● | ● | 3 weeks | M2.1
S2.2.1a | Subtask | Category 1: Mapped — MDO directly corresponds to an existing risk factor | Quant |  | ● | ● |  | 1 week | M2.1
S2.2.1b | Subtask | Category 2: Not mapped — MDO has no RF but SHOULD have one (gap → create new RF) | Quant |  | ● | ● | ● | 1 week | S2.2.1a
S2.2.1c | Subtask | Category 3: Not mapped — MDO is a pricing input, NOT a risk factor (fixings, reset costs, impact pricing) | Quant |  |  | ● | ● | 3 days | S2.2.1b
S2.2.1d | Subtask | Category 4: FO/Risk disconnect — MDO maps to a fundamentally different RF in risk (structural gap) | Quant |  |  | ● | ● | 1 week | S2.2.1c
B2.2.1 | BCA | Gap analysis report delivered: count by category, by desk, by asset class. Reviewed by risk and desk heads. | Quant |  |  | ● | ● |  | S2.2.1d
T2.2.2 | Task | Create new risk factors for identified gaps (Category 2) | Quant | ● | ● | ● |  | 3 weeks | T2.2.1
S2.2.2a | Subtask | Define RF specification: name, type, tenor/strike grid, source, update frequency | Quant |  |  | ● |  | 1 week | T2.2.1
S2.2.2b | Subtask | Build data pipeline to source and store the new RF time series | Data Eng | ● | ● |  |  | 2 weeks | S2.2.2a
S2.2.2c | Subtask | Backfill historical data for new RFs (minimum 2 years, target back to 2007 for stress) | Data Eng |  | ● |  |  | 2 weeks | S2.2.2b
S2.2.2d | Subtask | Integrate new RFs into risk engine and validate P&L impact | Tech | ● |  | ● |  | 1 week | S2.2.2c
B2.2.2 | BCA | New risk factors live in production; validated by quant and confirmed by desk | Quant | ● | ● | ● | ● |  | S2.2.2d
T2.2.3 | Task | Document and remediate FO/Risk disconnects (Category 4) | Business/SME | ● |  | ● | ● | Ongoing | T2.2.1
S2.2.3a | Subtask | For each disconnect: document FO model, risk model, the gap, and proposed fix | Quant |  |  | ● | ● | 2 weeks | T2.2.1
S2.2.3b | Subtask | Prioritize disconnects by PLA impact (which ones will cause the most PLA noise) | Quant |  |  | ● |  | 1 week | S2.2.3a
S2.2.3c | Subtask | Initiate FO model upgrade requests (e.g., RVF+ → Full Config for credit) | Business/SME | ● |  |  | ● | Varies | S2.2.3b
B2.2.3 | BCA | Disconnect remediation plan approved by CRO; timelines agreed with FO technology | Business/SME |  |  |  | ● |  | S2.2.3c
D3 | Deliverable | Risk Factor Taxonomy, Metadata & Liquidity Horizons | Quant | ● | ● | ● | ○ | 6–8 weeks | D2
M3.1 | Milestone | RF Taxonomy & Definition Framework Complete | Quant |  |  | ● |  | Week 4 | D2
T3.1.1 | Task | Define risk factor taxonomy and granularity standards | Quant |  |  | ● | ● | 2 weeks | D2
S3.1.1a | Subtask | Define asset class hierarchy: GIRR, CSR_NS, CSR_SEC, FX, EQ, COMM → sub-types | Quant |  |  | ● |  | 3 days | D2
S3.1.1b | Subtask | Define risk factor attributes: name, type, currency, tenor, maturity, strike, moneyness, issuer, sector, region | Quant |  |  | ● |  | 3 days | S3.1.1a
S3.1.1c | Subtask | Define granularity level for each RF type: issuer-level vs. sector vs. rating bucket vs. index | Quant |  |  | ● | ● | 1 week | S3.1.1b
S3.1.1d | Subtask | Determine RF definition: overlapping vs. non-overlapping returns, absolute vs. relative, log vs. simple | Quant |  |  | ● |  | 3 days | S3.1.1c
B3.1.1 | BCA | RF taxonomy document finalized; approved by quant lead and model validation | Quant |  |  | ● |  |  | S3.1.1d
T3.1.2 | Task | Classify all risk factors per taxonomy | Quant |  | ● | ● |  | 2 weeks | T3.1.1
S3.1.2a | Subtask | Tag every RF with asset class, sub-type, currency, tenor bucket, and granularity level | Data Eng |  | ● | ● |  | 1 week | T3.1.1
S3.1.2b | Subtask | Build RF metadata repository (structured database, not spreadsheets) | Tech | ● | ● |  |  | 1 week | S3.1.2a
B3.1.2 | BCA | RF metadata repository live; all RFs tagged and queryable | Data Eng | ● | ● |  |  |  | S3.1.2b
M3.2 | Milestone | Liquidity Horizons Assigned to All Risk Factors | Quant |  |  | ● | ● | Week 6 | M3.1
T3.2.1 | Task | Assign liquidity horizons to all risk factors | Quant |  |  | ● | ● | 2 weeks | M3.1
S3.2.1a | Subtask | Map each RF to one of 5 prescribed LH tiers (10, 20, 40, 60, 120 days) per NPR rules | Quant |  |  | ● |  | 1 week | M3.1
S3.2.1b | Subtask | Handle edge cases: cross-currency basis, bespoke credit, multi-underlying instruments | Quant |  |  | ● | ● | 3 days | S3.2.1a
S3.2.1c | Subtask | Document justification for each LH assignment (supervisor will challenge) | Quant |  |  | ● |  | 3 days | S3.2.1b
S3.2.1d | Subtask | Build weighted-average LH calculator for multi-underlying instruments | Tech | ● |  | ● |  | 3 days | S3.2.1c
B3.2.1 | BCA | LH assignment file completed; reviewed by model validation and risk management | Quant |  |  | ● | ● |  | S3.2.1d
T3.2.2 | Task | Identify and document all proxy relationships | Quant |  | ● | ● | ● | 2 weeks | T3.2.1
S3.2.2a | Subtask | For each RF using a proxy: document the proxy RF, the justification, and the track record | Quant |  |  | ● | ● | 1 week | T3.2.1
S3.2.2b | Subtask | Classify proxies: green (same data), yellow (operational gap), red (structural mismatch) | Quant |  |  | ● |  | 3 days | S3.2.2a
S3.2.2c | Subtask | Build proxy mapping table: original RF → proxy RF → justification → review date | Data Eng |  | ● | ● |  | 3 days | S3.2.2b
S3.2.2d | Subtask | Validate proxy quality: correlation analysis, volatility ratio, regime behavior | Quant |  |  | ● |  | 1 week | S3.2.2c
B3.2.2 | BCA | Proxy registry completed; all proxies documented with justification and validation metrics | Quant |  |  | ● |  |  | S3.2.2d
D4 | Deliverable | RFET Qualitative Test Engine | Quant | ● | ● | ● | ○ | 6–8 weeks | D3
M4.1 | Milestone | Qualitative Test Framework Designed | Quant |  |  | ● |  | Week 3 | D3
T4.1.1 | Task | Design qualitative test methodology | Quant |  |  | ● | ● | 2 weeks | D3
S4.1.1a | Subtask | Define the 7 quality standards and how each will be evaluated per RF | Quant |  |  | ● |  | 1 week | D3
S4.1.1b | Subtask | Define pass/fail criteria for each standard (binary vs. scored) | Quant |  |  | ● |  | 3 days | S4.1.1a
S4.1.1c | Subtask | Define data sources for each check: update frequency logs, source reliability scores, proxy registers | Data Eng |  | ● | ● |  | 3 days | S4.1.1b
S4.1.1d | Subtask | Design exception/override workflow for edge cases | Quant |  |  | ● | ● | 2 days | S4.1.1c
B4.1.1 | BCA | Qualitative test methodology document approved by model validation | Quant |  |  | ● |  |  | S4.1.1d
M4.2 | Milestone | Qualitative Test Engine Built & Validated | Tech | ● | ● | ● |  | Week 7 | M4.1
T4.2.1 | Task | Build automated qualitative test engine | Tech | ● | ● | ● |  | 3 weeks | M4.1
S4.2.1a | Subtask | Build data quality check 1: real market price verification (arm's-length transaction check) | Tech | ● | ● |  |  | 3 days | M4.1
S4.2.1b | Subtask | Build data quality check 2: update frequency monitor (weekly minimum threshold) | Tech | ● | ● |  |  | 2 days | S4.2.1a
S4.2.1c | Subtask | Build data quality check 3: source reliability scoring | Tech | ● | ● |  |  | 2 days | S4.2.1b
S4.2.1d | Subtask | Build data quality check 4: volatility capture validation | Quant | ● |  | ● |  | 3 days | S4.2.1c
S4.2.1e | Subtask | Build data quality check 5: correlation capture validation | Quant | ● |  | ● |  | 3 days | S4.2.1d
S4.2.1f | Subtask | Build data quality check 6: model-derived vs. real price flag | Tech | ● | ● |  |  | 2 days | S4.2.1e
S4.2.1g | Subtask | Build data quality check 7: proxy justification and track record verification | Quant | ● |  | ● |  | 3 days | S4.2.1f
S4.2.1h | Subtask | Build aggregation logic: all 7 checks → single pass/fail per RF | Tech | ● |  | ● |  | 2 days | S4.2.1g
S4.2.1i | Subtask | Build quarterly scheduling and automation framework | Tech | ● |  |  |  | 3 days | S4.2.1h
B4.2.1 | BCA | Qualitative test engine passes UAT; validated against manual test results for 500 sample RFs | Tech | ● |  | ● | ● |  | S4.2.1i
D5 | Deliverable | RFET Quantitative Test Engine & RPO Infrastructure | Data Eng | ● | ● | ● | ○ | 10–14 weeks | D3
M5.1 | Milestone | RPO Sourcing & Storage Infrastructure Live | Data Eng | ● | ● |  |  | Week 5 | D3
T5.1.1 | Task | Source Real Price Observations (RPOs) | Data Eng | ● | ● |  | ● | 3 weeks | D3
S5.1.1a | Subtask | Identify RPO sources: exchanges (CME, ICE, LCH), TRACE, DTCC, Markit, Bloomberg BVAL | Data Eng |  | ● |  | ● | 1 week | D3
S5.1.1b | Subtask | Negotiate data agreements and licensing for each RPO source | Business/SME |  |  |  | ● | 2 weeks | S5.1.1a
S5.1.1c | Subtask | Identify arm's-length transaction requirements per NPR definition | Quant |  |  | ● |  | 3 days | S5.1.1a
S5.1.1d | Subtask | Identify third-party providers requiring public audit of pricing data validity | Business/SME |  | ● |  | ● | 1 week | S5.1.1c
B5.1.1 | BCA | RPO source inventory complete; data agreements in place; audit requirements identified | Data Eng |  | ● |  | ● |  | S5.1.1d
T5.1.2 | Task | Build RPO storage and ingestion infrastructure | Tech | ● | ● |  |  | 3 weeks | T5.1.1
S5.1.2a | Subtask | Design RPO database schema: observation date, RF ID, price, source, type (trade/bid/offer/committed quote) | Tech | ● | ● |  |  | 3 days | T5.1.1
S5.1.2b | Subtask | Build automated daily ingestion pipelines from each RPO source | Tech | ● | ● |  |  | 2 weeks | S5.1.2a
S5.1.2c | Subtask | Build deduplication logic: max 1 observation per RF per day | Tech | ● |  | ● |  | 3 days | S5.1.2b
S5.1.2d | Subtask | Build data quality checks on incoming RPOs: stale price detection, outlier flagging | Tech | ● | ● |  |  | 3 days | S5.1.2c
S5.1.2e | Subtask | Build historical backfill: load 12+ months of RPOs for initial classification run | Data Eng |  | ● |  |  | 1 week | S5.1.2d
B5.1.2 | BCA | RPO database live; daily feeds running; historical backfill complete; validated by data team | Tech | ● | ● |  |  |  | S5.1.2e
M5.2 | Milestone | RPO → RF Mapping Complete | Quant |  | ● | ● |  | Week 8 | M5.1
T5.2.1 | Task | Map RPOs to risk factor buckets | Quant |  | ● | ● |  | 3 weeks | M5.1
S5.2.1a | Subtask | Define bucketing approach per RF type: own bucketing vs. standard bucketing (NPR prescribed grids) | Quant |  |  | ● |  | 1 week | M5.1
S5.2.1b | Subtask | For each RPO: determine which RF bucket it maps to (tenor, maturity, strike, moneyness) | Quant |  | ● | ● |  | 1 week | S5.2.1a
S5.2.1c | Subtask | Build automated RPO → bucket → RF mapping engine | Tech | ● | ● | ● |  | 1 week | S5.2.1b
S5.2.1d | Subtask | Validate mapping: spot-check 1000 RPOs across asset classes | Quant |  |  | ● | ● | 3 days | S5.2.1c
B5.2.1 | BCA | RPO-to-RF mapping validated; automated engine running in production | Quant |  | ● | ● |  |  | S5.2.1d
M5.3 | Milestone | Quantitative Test Engine Built & First Classification Run | Quant | ● | ● | ● | ● | Week 12 | M5.2
T5.3.1 | Task | Build quantitative test counting engine | Tech | ● |  | ● |  | 2 weeks | M5.2
S5.3.1a | Subtask | Build observation counter: count distinct RPOs per RF over rolling 12-month window | Tech | ● |  | ● |  | 3 days | M5.2
S5.3.1b | Subtask | Implement threshold logic: ≥24 for LH≤20d, ≥16 for LH>20d | Tech | ● |  | ● |  | 2 days | S5.3.1a
S5.3.1c | Subtask | Implement max-1-per-day deduplication in counting | Tech | ● |  |  |  | 1 day | S5.3.1b
S5.3.1d | Subtask | Build quarterly scheduling: auto-refresh classification every quarter | Tech | ● |  |  |  | 3 days | S5.3.1c
B5.3.1 | BCA | Quantitative test engine passes UAT; counts validated against manual sample | Tech | ● |  | ● |  |  | S5.3.1d
T5.3.2 | Task | Combine qualitative + quantitative results → classification | Quant | ● |  | ● |  | 1 week | T5.3.1
S5.3.2a | Subtask | Build classification logic: pass both → Modellable; pass qual only → Type A; fail qual → Type B | Tech | ● |  | ● |  | 2 days | T5.3.1
S5.3.2b | Subtask | Build exception/override workflow with approval chain | Tech | ● |  |  | ● | 2 days | S5.3.2a
S5.3.2c | Subtask | Run first full classification across all in-scope risk factors | Quant |  |  | ● |  | 3 days | S5.3.2b
S5.3.2d | Subtask | Analyze results: % modellable, % Type A, % Type B by desk and asset class | Quant |  |  | ● | ● | 2 days | S5.3.2c
B5.3.2 | BCA | First RFET classification report delivered to risk committee; results reviewed with desk heads | Quant |  |  | ● | ● |  | S5.3.2d
T5.3.3 | Task | Build Modellable vs. Non-Modellable Dashboard | Tech | ● | ● |  | ● | 2 weeks | T5.3.2
S5.3.3a | Subtask | Design dashboard: by desk, by asset class, by RF type, trend over time | Tech | ● |  |  | ● | 3 days | T5.3.2
S5.3.3b | Subtask | Build drill-down: for each NMRF → show why it failed, which test, observation count | Tech | ● |  | ● |  | 1 week | S5.3.3a
S5.3.3c | Subtask | Build alerting: flag RFs approaching NMRF threshold (early warning) | Tech | ● |  |  |  | 3 days | S5.3.3b
S5.3.3d | Subtask | Build capital impact view: estimated SES charge per NMRF | Quant | ● |  | ● |  | 3 days | S5.3.3c
B5.3.3 | BCA | RFET dashboard live in production; accessible to risk, quant, and desk heads | Tech | ● |  |  | ● |  | S5.3.3d
D6 | Deliverable | Consolidate RF Metadata & Ongoing Governance | Quant | ● | ● | ● | ● | 4 weeks | D5
T6.1.1 | Task | Consolidate all RF metadata into single golden source | Data Eng | ● | ● | ● |  | 2 weeks | D5
S6.1.1a | Subtask | Merge: RF catalog + taxonomy + LH assignment + proxy registry + RFET classification + RPO counts | Data Eng |  | ● | ● |  | 1 week | D5
S6.1.1b | Subtask | Build API layer for downstream consumers: ES engine, SES engine, capital calc, reporting | Tech | ● |  |  |  | 1 week | S6.1.1a
B6.1.1 | BCA | Golden RF metadata source live; consumed by all downstream systems | Data Eng | ● | ● |  |  |  | S6.1.1b
T6.1.2 | Task | Establish ongoing governance and refresh cycle | Business/SME |  |  | ● | ● | 2 weeks | T6.1.1
S6.1.2a | Subtask | Define quarterly RFET refresh process: who runs it, who reviews, who approves reclassifications | Business/SME |  |  |  | ● | 3 days | T6.1.1
S6.1.2b | Subtask | Define trigger-based re-classification: material portfolio change, new desk, new product | Quant |  |  | ● | ● | 3 days | S6.1.2a
S6.1.2c | Subtask | Define escalation path for RFs that flip from Modellable → NMRF | Business/SME |  |  | ● | ● | 2 days | S6.1.2b
S6.1.2d | Subtask | Document full RFET governance framework for supervisory submission | Business/SME |  |  | ● | ● | 1 week | S6.1.2c
B6.1.2 | BCA | RFET governance framework document approved by CRO; ready for supervisor review | Business/SME |  |  | ● | ● |  | S6.1.2d

## Carry Removal
# | Level | Description | Primary Owner | Tech | Data Eng | Quant | Business/SME | Duration | Dependency | Status
C1 | Deliverable | Assess Whether Carry Removal Is Required per Risk Factor | Quant | ○ | ● | ● | ● | 4–6 weeks | —
CM1.1 | Milestone | Carry Removal Scope Decision Document Approved | Quant |  |  | ● | ● | Week 4 | —
CT1.1 | Task | Define what constitutes a 'time effect' per asset class | Quant |  |  | ● | ● | 2 weeks | —
CS1.1a | Subtask | IR_RATE: document roll-down mechanics — tenor shortening, forward rate slide along curve | Quant |  |  | ● |  | 3 days | —
CS1.1b | Subtask | FX_RATE: document forward points carry — interest rate differential accrual in spot FX | Quant |  |  | ● |  | 2 days | CS1.1a
CS1.1c | Subtask | EQ_PRICE: document expected dividend yield accrual and repo rate carry | Quant |  |  | ● |  | 2 days | CS1.1b
CS1.1d | Subtask | IR_VOL / EQ_VOL / FX_VOL: document theta decay — mechanical vol surface roll from expiry shortening | Quant |  |  | ● |  | 2 days | CS1.1c
CS1.1e | Subtask | COMM_PRICE: document contango/backwardation carry — term structure roll between contract months | Quant |  |  | ● |  | 2 days | CS1.1d
CS1.1f | Subtask | Credit (CDS/bonds): document spread carry, accrued premium, coupon accrual | Quant |  |  | ● | ● | 2 days | CS1.1e
CB1.1 | BCA | Time effects definition document completed per asset class; reviewed by desk quants | Quant |  |  | ● | ● |  | CS1.1f
CT1.2 | Task | Determine which risk factors require carry removal | Quant |  | ● | ● | ● | 2 weeks | CT1.1
CS1.2a | Subtask | For each RF type: assess materiality of carry component relative to daily market moves | Quant |  |  | ● |  | 3 days | CT1.1
CS1.2b | Subtask | Quantify carry vs. market move ratio across asset classes using 1-year sample data | Quant |  | ● | ● |  | 3 days | CS1.2a
CS1.2c | Subtask | Identify RFs where carry is negligible (e.g., equity spot prices) — document exclusion rationale | Quant |  |  | ● |  | 2 days | CS1.2b
CS1.2d | Subtask | Identify RFs where carry is material and must be stripped (e.g., IR rates, FX forwards, vol surfaces) | Quant |  |  | ● |  | 2 days | CS1.2c
CS1.2e | Subtask | Build decision tree: RF type → carry required (Y/N) → methodology scenario (1/2/3) | Quant |  |  | ● |  | 2 days | CS1.2d
CB1.2 | BCA | Carry removal scope matrix approved: which RFs require stripping, which are excluded, with rationale | Quant |  |  | ● | ● |  | CS1.2e
CT1.3 | Task | Determine carry horizon requirements: 1-day only vs. 10-day | Quant |  |  | ● |  | 1 week | CT1.2
CS1.3a | Subtask | Assess PLA needs: HPL and RTPL require 1-day carry-stripped returns (daily P&L comparison) | Quant |  |  | ● |  | 2 days | CT1.2
CS1.3b | Subtask | Assess ES needs: base LH is 10-day — determine if 10-day carry must be computed separately or summed from 10 × 1-day | Quant |  |  | ● |  | 2 days | CS1.3a
CS1.3c | Subtask | Document recommendation: sum 10 consecutive 1-day carry values (captures intraperiod curve shape changes) vs. naive 10× scaling | Quant |  |  | ● |  | 2 days | CS1.3b
CS1.3d | Subtask | Assess LH > 10 days: for 20/40/60/120-day horizons, determine carry scaling approach | Quant |  |  | ● |  | 1 day | CS1.3c
CB1.3 | BCA | 1-day vs. 10-day carry methodology decision documented and approved by quant lead | Quant |  |  | ● |  |  | CS1.3d
C2 | Deliverable | Build Carry Removal Methodology per Asset Class | Quant | ○ | ● | ● | ○ | 6–10 weeks | C1
CM2.1 | Milestone | Carry Removal Methodology Document Approved | Quant |  |  | ● |  | Week 6 | C1
CT2.1 | Task | Design Scenario A: Observable carry from term structure (IR, FX, Commodity forwards) | Quant |  | ● | ● |  | 3 weeks | C1
CS2.1a | Subtask | IR_RATE: design interpolation of aged-tenor rate from full curve snapshots to compute 1-day forward carry | Quant |  |  | ● |  | 3 days | C1
CS2.1b | Subtask | IR_RATE: compute carry as difference between spot rate at tenor T and interpolated rate at tenor T−1d | Quant |  |  | ● |  | 2 days | CS2.1a
CS2.1c | Subtask | FX_RATE: design carry as 1-day forward points derived from domestic vs. foreign interest rate differential | Quant |  |  | ● |  | 2 days | CS2.1b
CS2.1d | Subtask | COMM_PRICE (forwards): design carry as 1-day roll from forward curve term structure | Quant |  |  | ● |  | 2 days | CS2.1c
CS2.1e | Subtask | Validate Scenario A on 2-year sample: compare carry-stripped vs. raw returns, check for systematic bias | Quant |  | ● | ● |  | 1 week | CS2.1d
CS2.1f | Subtask | Document: mathematical specification, data requirements, edge cases, fallback logic | Quant |  |  | ● |  | 3 days | CS2.1e
CB2.1 | BCA | Scenario A methodology validated on sample data; methodology document reviewed by model validation | Quant |  |  | ● |  |  | CS2.1f
CT2.2 | Task | Design Scenario B: Model-implied carry for volatility surfaces (IR Vol, EQ Vol, FX Vol) | Quant |  | ● | ● |  | 2 weeks | CT2.1
CS2.2a | Subtask | Design theta approximation: Black-Scholes √T scaling to estimate vol surface roll from maturity shortening | Quant |  |  | ● |  | 3 days | CT2.1
CS2.2b | Subtask | Handle partial surface data: when only ATM vol or sparse strike grid is available, design interpolation fallback | Quant |  |  | ● |  | 2 days | CS2.2a
CS2.2c | Subtask | Validate Scenario B on 2-year sample across IR swaption vol, equity implied vol, FX implied vol | Quant |  | ● | ● |  | 1 week | CS2.2b
CS2.2d | Subtask | Document: mathematical specification, assumptions, limitations, regime sensitivity | Quant |  |  | ● |  | 2 days | CS2.2c
CB2.2 | BCA | Scenario B methodology validated; reviewed by model validation | Quant |  |  | ● |  |  | CS2.2d
CT2.3 | Task | Design Scenario C: Statistical carry estimator (fallback for equity/commodity spot prices) | Quant |  | ● | ● |  | 2 weeks | CT2.2
CS2.3a | Subtask | Design rolling median of daily RF changes as statistical carry proxy | Quant |  |  | ● |  | 2 days | CT2.2
CS2.3b | Subtask | Determine optimal rolling window length: 20-day vs. 60-day vs. adaptive | Quant |  |  | ● |  | 2 days | CS2.3a
CS2.3c | Subtask | Assess regime sensitivity: test carry estimate stability during stress periods (2008, 2020, 2022) | Quant |  | ● | ● |  | 3 days | CS2.3b
CS2.3d | Subtask | Design regime-conditioning: shorter window during stress, potentially conditioned on CDX IG spread regime signal | Quant |  |  | ● |  | 3 days | CS2.3c
CS2.3e | Subtask | Validate Scenario C on 5-year sample: compare vs. Scenario A/B where overlap exists | Quant |  | ● | ● |  | 3 days | CS2.3d
CS2.3f | Subtask | Document: methodology, window selection rationale, regime logic, known limitations | Quant |  |  | ● |  | 2 days | CS2.3e
CB2.3 | BCA | Scenario C methodology validated; documented as fallback with known limitations | Quant |  |  | ● |  |  | CS2.3f
CT2.4 | Task | Build decision tree mapping asset classes to scenarios | Quant |  |  | ● |  | 1 week | CT2.3
CS2.4a | Subtask | Map each RF type to primary scenario: IR_RATE→A, FX_RATE→A, IR_VOL→B, EQ_VOL→B, FX_VOL→B, EQ_PRICE→C, COMM_PRICE→A/C | Quant |  |  | ● |  | 2 days | CT2.3
CS2.4b | Subtask | Define fallback chain: if Scenario A data unavailable → try B → fall back to C | Quant |  |  | ● |  | 1 day | CS2.4a
CS2.4c | Subtask | Document edge cases: basis spreads, cross-currency, inflation linkers, credit spread carry | Quant |  |  | ● | ● | 2 days | CS2.4b
CB2.4 | BCA | Complete carry removal methodology package approved: 3 scenarios + decision tree + edge cases | Quant |  |  | ● |  |  | CS2.4c
C3 | Deliverable | Build Carry Removal into Daily RF Generation Process | Tech | ● | ● | ● | ○ | 6–8 weeks | C2
CM3.1 | Milestone | Daily Carry Engine Running in Dev Environment | Tech | ● | ● | ● |  | Week 4 | C2
CT3.1 | Task | Build daily carry computation module | Tech | ● | ● | ● |  | 3 weeks | C2
CS3.1a | Subtask | At COB: snapshot current term structure / vol surface / dividend curve / forward curve per asset class | Tech | ● | ● |  |  | 3 days | C2
CS3.1b | Subtask | Compute deterministic 1-day carry for each in-scope RF using assigned scenario (A, B, or C) | Tech | ● |  | ● |  | 1 week | CS3.1a
CS3.1c | Subtask | Next day: compute raw RF change, subtract carry component → produce carry-stripped return | Tech | ● |  | ● |  | 3 days | CS3.1b
CS3.1d | Subtask | Store carry component and carry-stripped return separately (both needed for audit trail) | Tech | ● | ● |  |  | 2 days | CS3.1c
CS3.1e | Subtask | Build QA checks: carry magnitude vs. total move ratio, sign consistency, outlier detection | Tech | ● |  | ● |  | 3 days | CS3.1d
CB3.1 | BCA | Daily carry engine producing carry-stripped returns for all in-scope RFs in dev; validated against manual calc for 200 sample RFs | Tech | ● |  | ● |  |  | CS3.1e
CT3.2 | Task | Integrate carry-stripped returns into HPL and RTPL pipelines | Tech | ● | ● | ● |  | 2 weeks | CT3.1
CS3.2a | Subtask | Feed carry-stripped RF returns into HPL generation (front office side) | Tech | ● | ● |  |  | 3 days | CT3.1
CS3.2b | Subtask | Feed carry-stripped RF returns into RTPL generation (risk model side) | Tech | ● |  | ● |  | 3 days | CS3.2a
CS3.2c | Subtask | Critical: ensure HPL and RTPL consume the SAME carry estimate — single source, not independently computed | Tech | ● | ● | ● |  | 2 days | CS3.2b
CS3.2d | Subtask | Validate: compare HPL vs. RTPL on carry-stripped basis — gap should be purely model-driven, not carry-driven | Quant |  |  | ● |  | 3 days | CS3.2c
CS3.2e | Subtask | Build reconciliation report: daily carry stripped vs. raw, by desk, with break detection | Tech | ● |  |  |  | 3 days | CS3.2d
CB3.2 | BCA | Carry-stripped HPL and RTPL running in parallel with raw versions; PLA test improvement quantified | Tech | ● |  | ● | ● |  | CS3.2e
CT3.3 | Task | Compute 10-day carry for ES base horizon | Tech | ● |  | ● |  | 1 week | CT3.2
CS3.3a | Subtask | Build 10-day carry as sum of 10 consecutive 1-day carry values (not naive 10× scaling) | Tech | ● |  | ● |  | 2 days | CT3.2
CS3.3b | Subtask | Handle overlapping vs. non-overlapping 10-day windows per ES methodology choice | Quant |  |  | ● |  | 2 days | CS3.3a
CS3.3c | Subtask | Validate: compare 10-day summed carry vs. 10× daily carry — quantify the difference | Quant |  | ● | ● |  | 2 days | CS3.3b
CB3.3 | BCA | 10-day carry computation validated; integrated into daily ES RF return pipeline | Tech | ● |  | ● |  |  | CS3.3c
C4 | Deliverable | Build Historical Carry Removal for Precomputed RF Shocks | Data Eng | ● | ● | ● | ○ | 8–12 weeks | C2
CM4.1 | Milestone | Historical MDO Availability Assessment Complete | Data Eng |  | ● | ● |  | Week 3 | C2
CT4.1 | Task | Assess historical market data availability for carry computation | Data Eng |  | ● | ● |  | 2 weeks | C2
CS4.1a | Subtask | For each asset class: inventory historical term structures / vol surfaces / dividend curves available back to 2007 | Data Eng |  | ● |  |  | 1 week | C2
CS4.1b | Subtask | Identify gaps: which asset classes / currencies / tenors have incomplete historical MDOs | Data Eng |  | ● | ● |  | 3 days | CS4.1a
CS4.1c | Subtask | For each gap: determine proxy approach — related curve, cross-sectional imputation, or Scenario C fallback | Quant |  |  | ● |  | 3 days | CS4.1b
CS4.1d | Subtask | Document: data availability matrix by asset class × year × scenario applicability | Data Eng |  | ● | ● |  | 2 days | CS4.1c
CB4.1 | BCA | Historical data availability report delivered; proxy strategies defined for all gaps | Data Eng |  | ● | ● |  |  | CS4.1d
CM4.2 | Milestone | Historical Carry-Stripped RF Series Produced | Quant | ● | ● | ● |  | Week 10 | CM4.1
CT4.2 | Task | Compute historical carry estimates for full history | Quant | ● | ● | ● |  | 4 weeks | CM4.1
CS4.2a | Subtask | For Scenario A RFs (IR, FX, Comm forwards): compute daily carry from historical term structures for each business day back to 2007 | Quant |  | ● | ● |  | 2 weeks | CM4.1
CS4.2b | Subtask | For Scenario B RFs (vol surfaces): compute daily theta from historical vol surface snapshots | Quant |  | ● | ● |  | 1 week | CS4.2a
CS4.2c | Subtask | For Scenario C RFs (equity/commodity spot): compute rolling median carry estimate across full history | Quant |  | ● | ● |  | 1 week | CS4.2b
CS4.2d | Subtask | For gaps: apply proxy carry methodology — validate proxy carry vs. actual carry where overlap exists | Quant |  | ● | ● |  | 1 week | CS4.2c
CB4.2 | BCA | Historical carry series produced for all in-scope RFs; spot-checked for reasonableness across 5 key dates (2008 crisis, 2013 taper, 2020 COVID, 2022 rates, current) | Quant |  | ● | ● |  |  | CS4.2d
CT4.3 | Task | Produce carry-stripped historical RF return series | Tech | ● | ● | ● |  | 2 weeks | CT4.2
CS4.3a | Subtask | Subtract historical carry from raw historical RF returns → produce carry-stripped return series | Tech | ● |  | ● |  | 3 days | CT4.2
CS4.3b | Subtask | Produce both 1-day and 10-day carry-stripped return series (10-day = sum of 10 × 1-day) | Tech | ● |  | ● |  | 3 days | CS4.3a
CS4.3c | Subtask | Store carry-stripped series in RF data warehouse alongside raw series (both must be available) | Tech | ● | ● |  |  | 3 days | CS4.3b
CS4.3d | Subtask | Validate: compare ES computed on carry-stripped vs. raw returns — quantify impact on tail shape | Quant |  |  | ● |  | 3 days | CS4.3c
CS4.3e | Subtask | Validate: stress period selection — confirm same stress window is selected on carry-stripped data | Quant |  |  | ● |  | 2 days | CS4.3d
CB4.3 | BCA | Carry-stripped historical RF series in production; ES calibration data updated; impact analysis delivered to risk committee | Quant | ● | ● | ● | ● |  | CS4.3e
C5 | Deliverable | Technology Implementation: Carry Removal in EMR and MARS | Tech | ● | ● | ● | ○ | 8–10 weeks | C3
CM5.1 | Milestone | Architecture Decision: On-the-Fly vs. Pre-Store | Tech | ● |  | ● | ● | Week 2 | C3
CT5.1 | Task | Evaluate computation strategy: on-the-fly calculation vs. pre-stored historical shifts | Tech | ● |  | ● | ● | 2 weeks | C3
CS5.1a | Subtask | Option 1 — On-the-fly: compute carry at runtime from curve snapshots; no separate storage needed but higher compute cost | Tech | ● |  | ● |  | 3 days | C3
CS5.1b | Subtask | Option 2 — Pre-store: precompute and store carry-stripped shifts separately; lower runtime cost but higher storage and data management overhead | Tech | ● | ● |  |  | 3 days | CS5.1a
CS5.1c | Subtask | Option 3 — Hybrid: pre-store for historical (ES calibration), on-the-fly for daily (HPL/RTPL) | Tech | ● | ● | ● |  | 2 days | CS5.1b
CS5.1d | Subtask | Assess: compute budget, storage capacity, latency requirements, audit trail needs | Tech | ● |  |  |  | 3 days | CS5.1c
CS5.1e | Subtask | Assess: which approach best supports the quarterly RFET refresh and dynamic RF reclassification | Tech | ● |  | ● |  | 2 days | CS5.1d
CB5.1 | BCA | Architecture decision documented: on-the-fly vs. pre-store vs. hybrid; approved by tech lead and quant lead | Tech | ● |  | ● | ● |  | CS5.1e
CM5.2 | Milestone | Carry Removal Integrated into EMR | Tech | ● | ● |  |  | Week 6 | CM5.1
CT5.2 | Task | Implement carry removal in EMR (Enterprise Market Risk) platform | Tech | ● | ● | ● |  | 3 weeks | CM5.1
CS5.2a | Subtask | Extend EMR RF ingestion pipeline to accept carry-stripped returns as separate data channel | Tech | ● | ● |  |  | 1 week | CM5.1
CS5.2b | Subtask | Modify EMR ES calculation engine to consume carry-stripped returns for both current and stress period | Tech | ● |  | ● |  | 1 week | CS5.2a
CS5.2c | Subtask | Modify EMR RTPL generation to use carry-stripped RF changes (must match HPL carry source) | Tech | ● |  | ● |  | 3 days | CS5.2b
CS5.2d | Subtask | Build EMR carry reconciliation module: compare raw vs. stripped, flag discrepancies | Tech | ● |  |  |  | 3 days | CS5.2c
CS5.2e | Subtask | UAT: validate EMR outputs on carry-stripped data against standalone Python reference implementation | Quant | ● |  | ● |  | 3 days | CS5.2d
CB5.2 | BCA | EMR carry removal integration passes UAT; ES and RTPL outputs validated | Tech | ● |  | ● |  |  | CS5.2e
CM5.3 | Milestone | Carry Removal Integrated into MARS | Tech | ● | ● |  |  | Week 9 | CM5.2
CT5.3 | Task | Implement carry removal in MARS (Market And Risk System) platform | Tech | ● | ● | ● |  | 3 weeks | CM5.2
CS5.3a | Subtask | Extend MARS data layer to ingest and serve carry-stripped RF return series | Tech | ● | ● |  |  | 1 week | CM5.2
CS5.3b | Subtask | Modify MARS VaR/ES engines to consume carry-stripped data for backtesting and capital calc | Tech | ● |  | ● |  | 1 week | CS5.3a
CS5.3c | Subtask | Ensure MARS and EMR produce identical carry-stripped outputs (cross-platform reconciliation) | Tech | ● | ● | ● |  | 3 days | CS5.3b
CS5.3d | Subtask | Build MARS reporting: carry impact attribution — how much capital change is driven by carry stripping | Tech | ● |  | ● |  | 3 days | CS5.3c
CS5.3e | Subtask | UAT: validate MARS outputs; reconcile against EMR | Quant | ● |  | ● |  | 3 days | CS5.3d
CB5.3 | BCA | MARS carry removal integration passes UAT; cross-platform reconciliation clean | Tech | ● | ● | ● |  |  | CS5.3e
C6 | Deliverable | Validation, Documentation & Production Go-Live | Quant | ● | ● | ● | ● | 4–6 weeks | C5
CT6.1 | Task | End-to-end validation | Quant | ● | ● | ● |  | 2 weeks | C5
CS6.1a | Subtask | Validate daily carry-stripped HPL and RTPL produce cleaner PLA test results (compare KS statistic before/after) | Quant |  |  | ● |  | 3 days | C5
CS6.1b | Subtask | Validate historical carry-stripped ES produces different stress period selection or ES level — quantify impact | Quant |  |  | ● |  | 3 days | CS6.1a
CS6.1c | Subtask | Validate carry-stripped backtesting exceptions vs. raw — confirm exception count changes are explainable | Quant |  |  | ● |  | 2 days | CS6.1b
CS6.1d | Subtask | Run parallel production: raw and carry-stripped side-by-side for 30 days minimum | Tech | ● |  | ● |  | 30 days | CS6.1c
CB6.1 | BCA | Validation report delivered: PLA improvement quantified, ES impact measured, backtesting exception analysis complete | Quant |  |  | ● | ● |  | CS6.1d
CT6.2 | Task | Documentation and governance | Quant |  |  | ● | ● | 2 weeks | CT6.1
CS6.2a | Subtask | Document carry removal methodology: full mathematical specification per scenario per asset class | Quant |  |  | ● |  | 1 week | CT6.1
CS6.2b | Subtask | Document technology implementation: data flows, storage decisions, system integration points | Tech | ● |  |  |  | 3 days | CS6.2a
CS6.2c | Subtask | Document governance: who owns the carry methodology, review cycle, change control process | Business/SME |  |  |  | ● | 2 days | CS6.2b
CS6.2d | Subtask | Prepare supervisory package: methodology document + validation report + impact analysis | Quant |  |  | ● | ● | 3 days | CS6.2c
CB6.2 | BCA | Complete carry removal documentation package approved by CRO; ready for supervisor review | Quant |  |  | ● | ● |  | CS6.2d
CT6.3 | Task | Production cutover | Tech | ● | ● | ● | ● | 1 week | CT6.2
CS6.3a | Subtask | Switch HPL and RTPL to carry-stripped mode in production | Tech | ● | ● |  |  | 1 day | CT6.2
CS6.3b | Subtask | Switch ES calibration data to carry-stripped historical series | Tech | ● | ● |  |  | 1 day | CS6.3a
CS6.3c | Subtask | Confirm all downstream consumers (backtesting, PLA, capital calc, reporting) are receiving carry-stripped data | Tech | ● | ● | ● |  | 2 days | CS6.3b
CS6.3d | Subtask | Monitor: 5-day hypercare period with daily reconciliation and break detection | Tech | ● |  | ● |  | 5 days | CS6.3c
CB6.3 | BCA | Carry removal live in production; hypercare complete; no breaks detected; signed off by risk and technology | Tech | ● | ● | ● | ● |  | CS6.3d

## History and Proxy
# | Level | Description | Primary Owner | Tech | Data Eng | Quant | Business/SME | Duration | Dependency | Status
H1 | Deliverable | Proxy Framework, Justification & Complete Proxy Lineage | Quant | ○ | ● | ● | ● | 10–14 weeks | —
HM1.1 | Milestone | Proxy Inventory & Current-State Assessment Complete | Quant |  | ● | ● | ● | Week 4 | —
HT1.1 | Task | Inventory all existing proxy relationships across all in-scope RFs | Quant |  | ● | ● | ● | 2 weeks | —
HS1.1a | Subtask | Extract every RF that currently uses a proxy: original RF → proxy RF → asset class → desk | Data Eng |  | ● | ● |  | 1 week | —
HS1.1b | Subtask | Classify each proxy by type: same-asset-class substitution, cross-asset proxy, rating-bucket aggregation, regional aggregation | Quant |  |  | ● |  | 3 days | HS1.1a
HS1.1c | Subtask | Classify each proxy by cause: data gap, granularity gap, product gap, FO/Risk misalignment, legacy/undocumented | Quant |  |  | ● | ● | 3 days | HS1.1b
HS1.1d | Subtask | Flag undocumented proxies: RFs where proxy usage exists but has no formal justification on file | Quant |  |  | ● | ● | 2 days | HS1.1c
HS1.1e | Subtask | Quantify proxy usage: count of proxied RFs by desk, asset class, and proxy type | Data Eng |  | ● | ● |  | 2 days | HS1.1d
HB1.1 | BCA | Proxy inventory report delivered: total count, by type, by cause, undocumented flag rate; reviewed by risk management | Quant |  | ● | ● | ● |  | HS1.1e
HT1.2 | Task | Assess proxy quality for RFET qualitative test compliance | Quant |  | ● | ● |  | 2 weeks | HT1.1
HS1.2a | Subtask | For each proxied RF: compute correlation between proxy and original (where original data exists, even partially) | Quant |  | ● | ● |  | 1 week | HT1.1
HS1.2b | Subtask | For each proxied RF: compare volatility ratio (proxy vol / original vol) — should be close to 1.0 | Quant |  | ● | ● |  | 3 days | HS1.2a
HS1.2c | Subtask | For each proxied RF: assess regime behavior — does the proxy track the original in stress periods (2008, 2020, 2022)? | Quant |  | ● | ● |  | 3 days | HS1.2b
HS1.2d | Subtask | Flag proxies that fail quality thresholds: correlation < 0.7, vol ratio outside 0.5–1.5, regime divergence | Quant |  |  | ● |  | 2 days | HS1.2c
HS1.2e | Subtask | Classify proxies as: green (acceptable for RFET), yellow (needs enhancement), red (unacceptable — must be replaced) | Quant |  |  | ● | ● | 2 days | HS1.2d
HB1.2 | BCA | Proxy quality assessment complete: green/yellow/red classification per proxy; remediation list for yellow and red | Quant |  |  | ● | ● |  | HS1.2e
HM1.2 | Milestone | Proxy Enhancement Plan Approved | Quant |  |  | ● | ● | Week 7 | HM1.1
HT1.3 | Task | Enhance and remediate yellow/red proxies | Quant |  | ● | ● | ● | 4 weeks | HT1.2
HS1.3a | Subtask | For yellow proxies: identify better proxy candidates — closer issuer, same sector, same currency, similar tenor | Quant |  |  | ● | ● | 1 week | HT1.2
HS1.3b | Subtask | For red proxies: determine if direct data can be sourced (new vendor, new exchange feed, desk contribution) | Data Eng |  | ● |  | ● | 1 week | HS1.3a
HS1.3c | Subtask | For red proxies where direct data unavailable: build improved proxy methodology with stronger justification | Quant |  |  | ● |  | 1 week | HS1.3b
HS1.3d | Subtask | Re-validate enhanced proxies: re-run correlation, vol ratio, regime tests on improved candidates | Quant |  | ● | ● |  | 1 week | HS1.3c
HS1.3e | Subtask | Document each proxy enhancement: old proxy → new proxy → justification → validation metrics | Quant |  |  | ● |  | 3 days | HS1.3d
HB1.3 | BCA | Proxy enhancement report approved by model validation; all red proxies either replaced or formally accepted with documented risk | Quant |  |  | ● | ● |  | HS1.3e
HM1.3 | Milestone | Complete Proxy Lineage Back to 2007 Built | Data Eng | ● | ● | ● |  | Week 12 | HM1.2
HT1.4 | Task | Build complete proxy lineage for full historical period | Data Eng | ● | ● | ● |  | 4 weeks | HT1.3
HS1.4a | Subtask | For each proxied RF: determine if the proxy relationship was the same in 2007–2024 or if the proxy changed over time | Quant |  |  | ● |  | 1 week | HT1.3
HS1.4b | Subtask | Build historical proxy mapping table: RF → proxy RF → effective dates (from/to) → methodology version | Data Eng |  | ● | ● |  | 1 week | HS1.4a
HS1.4c | Subtask | For RFs where proxy changed: splice historical time series using period-appropriate proxy for each date range | Data Eng |  | ● | ● |  | 1 week | HS1.4b
HS1.4d | Subtask | Validate spliced series: check for level jumps, volatility breaks, or correlation discontinuities at splice points | Quant |  | ● | ● |  | 3 days | HS1.4c
HS1.4e | Subtask | Store proxy lineage metadata: every RF must have a traceable chain from raw data → proxy → final series for every historical date | Data Eng | ● | ● |  |  | 3 days | HS1.4d
HB1.4 | BCA | Complete proxy lineage back to 2007 built and validated; supervisor can trace any RF on any historical date | Data Eng | ● | ● | ● |  |  | HS1.4e
H2 | Deliverable | Fix Historical Data Quality Issues & Adjust Time Series | Data Eng | ● | ● | ● | ● | 8–12 weeks | H1
HM2.1 | Milestone | Historical DQ Assessment Complete | Data Eng |  | ● | ● |  | Week 4 | H1
HT2.1 | Task | Conduct comprehensive historical data quality audit | Data Eng |  | ● | ● |  | 3 weeks | H1
HS2.1a | Subtask | Scan all historical RF time series for: missing dates, stale prices, zero returns, extreme outliers, negative prices | Data Eng |  | ● |  |  | 1 week | H1
HS2.1b | Subtask | Identify RFs with insufficient history length: series starting after 2007, series with large gaps | Data Eng |  | ● | ● |  | 3 days | HS2.1a
HS2.1c | Subtask | Identify currency/index/instrument redenomination events: EUR introduction, LIBOR→SOFR transition, index reconstitution | Quant |  |  | ● | ● | 3 days | HS2.1b
HS2.1d | Subtask | Identify instruments that exist today but did not exist pre-2010: post-crisis credit names, new EM currencies, new vol products | Quant |  |  | ● | ● | 3 days | HS2.1c
HS2.1e | Subtask | Flag corporate actions in equity series: stock splits, mergers, spin-offs, ticker changes | Data Eng |  | ● |  | ● | 3 days | HS2.1d
HS2.1f | Subtask | Quantify DQ issues: count of affected RFs by issue type, by asset class, by severity | Data Eng |  | ● | ● |  | 2 days | HS2.1e
HB2.1 | BCA | Historical DQ audit report delivered: issue inventory with severity classification and remediation priority | Data Eng |  | ● | ● | ● |  | HS2.1f
HM2.2 | Milestone | Historical Time Series Remediation Complete | Data Eng | ● | ● | ● |  | Week 10 | HM2.1
HT2.2 | Task | Fix missing data and stale prices in historical series | Data Eng | ● | ● | ● |  | 3 weeks | HM2.1
HS2.2a | Subtask | For missing dates: apply interpolation methodology (linear for rates, log-linear for vols, LOCF for illiquid) | Quant |  | ● | ● |  | 1 week | HM2.1
HS2.2b | Subtask | For stale prices: detect using zero-return streaks > threshold; apply proxy or interpolation fill | Data Eng |  | ● | ● |  | 1 week | HS2.2a
HS2.2c | Subtask | For extreme outliers: apply winsorization or replacement based on neighboring-day interpolation with audit flag | Quant |  | ● | ● |  | 3 days | HS2.2b
HS2.2d | Subtask | Build fill/fix audit trail: every historical adjustment must be logged (original value, adjusted value, method, date, analyst) | Tech | ● | ● |  |  | 3 days | HS2.2c
HB2.2 | BCA | Missing data and stale price remediation complete; all fixes logged in audit trail | Data Eng |  | ● | ● |  |  | HS2.2d
HT2.3 | Task | Adjust historical time series for current instrument universe | Quant |  | ● | ● | ● | 3 weeks | HT2.2
HS2.3a | Subtask | LIBOR→SOFR transition: build adjusted IR curve history that reflects SOFR-based pricing back through 2007 using spread-adjusted methodology | Quant |  | ● | ● |  | 1 week | HT2.2
HS2.3b | Subtask | Post-crisis credit names: for issuers that did not exist pre-2010, build proxy history from sector/rating peers | Quant |  | ● | ● | ● | 1 week | HS2.3a
HS2.3c | Subtask | New EM currencies/instruments: build synthetic history from related currency pairs or regional indices | Quant |  | ● | ● |  | 3 days | HS2.3b
HS2.3d | Subtask | Index reconstitution: adjust historical index composition to reflect current constituents where applicable | Quant |  | ● | ● |  | 3 days | HS2.3c
HS2.3e | Subtask | Equity corporate actions: apply split/merger adjustments to produce clean adjusted price series | Data Eng |  | ● |  |  | 3 days | HS2.3d
HS2.3f | Subtask | Validate adjusted series: compare statistical properties (vol, autocorrelation, tail behavior) of adjusted vs. raw | Quant |  | ● | ● |  | 3 days | HS2.3e
HB2.3 | BCA | Adjusted historical time series produced for all current instruments; validated and documented | Quant |  | ● | ● | ● |  | HS2.3f
H3 | Deliverable | Strengthen Risk Factor History & Extend Time Series | Data Eng | ● | ● | ● | ○ | 6–8 weeks | H2
HM3.1 | Milestone | History Extension Strategy Approved per Asset Class | Quant |  | ● | ● |  | Week 3 | H2
HT3.1 | Task | Assess history length and completeness per RF | Data Eng |  | ● | ● |  | 2 weeks | H2
HS3.1a | Subtask | For each RF: record earliest available date, total business day count, gap count, and longest gap | Data Eng |  | ● |  |  | 1 week | H2
HS3.1b | Subtask | Map RF history against ES requirements: current period (recent 12 months minimum), stress period (must include 2007–2009 at minimum) | Quant |  |  | ● |  | 3 days | HS3.1a
HS3.1c | Subtask | Identify RFs with insufficient stress period coverage: series starting after 2009 | Quant |  | ● | ● |  | 3 days | HS3.1b
HS3.1d | Subtask | For each short RF: determine extension strategy — direct data sourcing, proxy extension, or synthetic construction | Quant |  |  | ● |  | 3 days | HS3.1c
HB3.1 | BCA | History assessment matrix delivered: RF × history length × strategy; approved by quant lead | Quant |  | ● | ● |  |  | HS3.1d
HT3.2 | Task | Extend RF history using direct data sourcing | Data Eng | ● | ● |  | ● | 3 weeks | HT3.1
HS3.2a | Subtask | Source additional historical data from vendors: Bloomberg, Refinitiv, Markit, ICE — negotiate backfill licenses | Data Eng |  | ● |  | ● | 1 week | HT3.1
HS3.2b | Subtask | Ingest and integrate vendor historical data into RF time series warehouse | Tech | ● | ● |  |  | 1 week | HS3.2a
HS3.2c | Subtask | Cross-validate vendor data against internal data where overlap exists — reconcile discrepancies | Data Eng |  | ● | ● |  | 3 days | HS3.2b
HS3.2d | Subtask | Splice vendor data with internal data: handle level discontinuities at splice point | Quant |  | ● | ● |  | 3 days | HS3.2c
HB3.2 | BCA | Direct data extensions complete; all spliced series validated for continuity | Data Eng |  | ● | ● |  |  | HS3.2d
HT3.3 | Task | Extend RF history using proxy/synthetic construction where direct data unavailable | Quant |  | ● | ● |  | 3 weeks | HT3.2
HS3.3a | Subtask | For RFs with no direct pre-2009 data: build proxy-extended series using the closest available proxy RF with full history | Quant |  | ● | ● |  | 1 week | HT3.2
HS3.3b | Subtask | Apply regression-based extension: estimate relationship between RF and proxy in overlap period, then backcast | Quant |  |  | ● |  | 1 week | HS3.3a
HS3.3c | Subtask | For new product types: build synthetic history from underlying components (e.g., structured credit from IG/HY indices + correlation assumptions) | Quant |  |  | ● | ● | 1 week | HS3.3b
HS3.3d | Subtask | Validate extended series: out-of-sample testing on overlap periods, stress period plausibility checks | Quant |  | ● | ● |  | 3 days | HS3.3c
HS3.3e | Subtask | Document all extensions: method, proxy used, validation results, known limitations | Quant |  |  | ● |  | 2 days | HS3.3d
HB3.3 | BCA | All RF histories extended to cover stress period; documentation package complete for model validation review | Quant |  | ● | ● |  |  | HS3.3e
H4 | Deliverable | Build Advanced Data Quality Framework for Early Warning | Tech | ● | ● | ● | ○ | 8–10 weeks | H2
HM4.1 | Milestone | DQ Framework Architecture Designed | Quant | ● |  | ● |  | Week 3 | H2
HT4.1 | Task | Design multi-tier DQ check framework | Quant | ● |  | ● |  | 2 weeks | H2
HS4.1a | Subtask | Tier 1 — Deterministic checks: missing data, stale prices (zero-return streaks), negative prices, weekend/holiday detection, duplicate entries | Quant |  |  | ● |  | 3 days | H2
HS4.1b | Subtask | Tier 2 — Statistical checks: Z-score outlier detection, rolling volatility spike detection, autocorrelation anomalies, distribution shift detection | Quant |  |  | ● |  | 3 days | HS4.1a
HS4.1c | Subtask | Tier 3 — Peer-group checks: cross-RF correlation breakdown detection, sector-vs-name divergence, basis relationship monitoring | Quant |  |  | ● |  | 3 days | HS4.1b
HS4.1d | Subtask | Tier 4 — ML triage: XGBoost or similar model to prioritize DQ alerts by severity and likely root cause | Quant | ● |  | ● |  | 3 days | HS4.1c
HS4.1e | Subtask | Define alerting thresholds per tier: what triggers a warning vs. a block vs. a manual review | Quant |  |  | ● | ● | 2 days | HS4.1d
HB4.1 | BCA | DQ framework design document approved; tier definitions and thresholds reviewed by risk management | Quant | ● |  | ● |  |  | HS4.1e
HM4.2 | Milestone | DQ Engine Built and Running in Production | Tech | ● | ● | ● |  | Week 8 | HM4.1
HT4.2 | Task | Build Tier 1 — Deterministic DQ checks | Tech | ● | ● |  |  | 2 weeks | HM4.1
HS4.2a | Subtask | Build missing data detector: flag RFs with no update within expected frequency | Tech | ● | ● |  |  | 3 days | HM4.1
HS4.2b | Subtask | Build stale price detector: flag RFs with > N consecutive zero returns (configurable N per asset class) | Tech | ● | ● |  |  | 2 days | HS4.2a
HS4.2c | Subtask | Build outlier detector: flag absolute daily moves > configurable threshold (e.g., 10σ for rates, 20% for equity) | Tech | ● |  | ● |  | 2 days | HS4.2b
HS4.2d | Subtask | Build holiday/calendar validator: flag updates on non-business days, flag missing updates on business days per currency calendar | Tech | ● | ● |  |  | 2 days | HS4.2c
HS4.2e | Subtask | Build duplicate detector: flag multiple observations for same RF on same date | Tech | ● | ● |  |  | 1 day | HS4.2d
HB4.2 | BCA | Tier 1 DQ checks live in production; running daily on all in-scope RFs | Tech | ● | ● |  |  |  | HS4.2e
HT4.3 | Task | Build Tier 2 — Statistical DQ checks | Tech | ● |  | ● |  | 2 weeks | HT4.2
HS4.3a | Subtask | Build rolling Z-score module: flag daily returns > 4σ from rolling 60-day mean | Tech | ● |  | ● |  | 3 days | HT4.2
HS4.3b | Subtask | Build volatility regime detector: flag when rolling vol exceeds 3× long-term average or drops below 0.3× long-term | Tech | ● |  | ● |  | 3 days | HS4.3a
HS4.3c | Subtask | Build autocorrelation monitor: flag RFs with autocorrelation > 0.5 (possible stale pricing or model-driven marks) | Tech | ● |  | ● |  | 2 days | HS4.3b
HS4.3d | Subtask | Build distribution shift detector: KS test on rolling 60-day vs. prior 250-day return distribution | Tech | ● |  | ● |  | 3 days | HS4.3c
HB4.3 | BCA | Tier 2 statistical checks live; calibrated to minimize false positives | Tech | ● |  | ● |  |  | HS4.3d
HT4.4 | Task | Build Tier 3 — Peer-group and cross-RF checks | Quant | ● | ● | ● |  | 2 weeks | HT4.3
HS4.4a | Subtask | Build peer-group correlation monitor: flag when an RF's correlation with its peer group drops below threshold | Quant | ● |  | ● |  | 3 days | HT4.3
HS4.4b | Subtask | Build sector-vs-name divergence detector: flag when a single-name RF moves in opposite direction to its sector index for > N days | Quant | ● |  | ● |  | 3 days | HS4.4a
HS4.4c | Subtask | Build basis relationship monitor: flag when known basis relationships (e.g., CDS-bond basis, cash-futures basis) break historical bounds | Quant | ● |  | ● |  | 3 days | HS4.4b
HS4.4d | Subtask | Build proxy tracking monitor: flag when a proxied RF diverges from its proxy beyond documented tolerance | Quant | ● |  | ● |  | 3 days | HS4.4c
HB4.4 | BCA | Tier 3 peer-group checks live; integrated with proxy monitoring framework | Quant | ● |  | ● |  |  | HS4.4d
HT4.5 | Task | Build Tier 4 — ML-based triage and alerting dashboard | Tech | ● |  | ● |  | 2 weeks | HT4.4
HS4.5a | Subtask | Train XGBoost model on historical DQ issues: features = tier 1–3 signals, target = confirmed issue vs. false positive | Quant | ● |  | ● |  | 1 week | HT4.4
HS4.5b | Subtask | Build alerting dashboard: by RF, by desk, by tier, with drill-down to root cause and suggested action | Tech | ● |  |  |  | 3 days | HS4.5a
HS4.5c | Subtask | Build daily DQ summary email: top 20 alerts by severity, new issues, resolved issues | Tech | ● |  |  |  | 2 days | HS4.5b
HS4.5d | Subtask | Build historical DQ trend reporting: issue count over time, by desk, by asset class — early warning of degradation | Tech | ● |  | ● |  | 3 days | HS4.5c
HB4.5 | BCA | Full 4-tier DQ framework live in production; dashboard accessible to risk, quant, and desk heads | Tech | ● |  | ● | ● |  | HS4.5d
H5 | Deliverable | Integrate Strengthened History into ES, VaR & Capital Calculation | Tech | ● | ● | ● | ● | 6–8 weeks | H3
HM5.1 | Milestone | Updated RF History Feeding ES & VaR Engines | Tech | ● | ● | ● |  | Week 4 | H3
HT5.1 | Task | Integrate remediated and extended RF history into ES calculation | Tech | ● | ● | ● |  | 3 weeks | H3
HS5.1a | Subtask | Replace raw historical RF returns with quality-checked, proxy-lineage-complete, extended series in ES data warehouse | Tech | ● | ● |  |  | 1 week | H3
HS5.1b | Subtask | Re-run ES stress period selection on updated history — confirm stress window is still appropriate or has shifted | Quant |  |  | ● |  | 3 days | HS5.1a
HS5.1c | Subtask | Compute ES on updated vs. original history — quantify impact on ES level, IMCC, and SES | Quant |  |  | ● |  | 3 days | HS5.1b
HS5.1d | Subtask | Validate: ensure no artificial volatility reduction from data smoothing — tail properties must be preserved | Quant |  |  | ● |  | 3 days | HS5.1c
HS5.1e | Subtask | Update VaR engine to consume same quality-checked series — ensure VaR and ES use identical RF history | Tech | ● |  | ● |  | 3 days | HS5.1d
HB5.1 | BCA | Updated RF history live in ES and VaR engines; impact analysis delivered to risk committee | Tech | ● | ● | ● | ● |  | HS5.1e
HT5.2 | Task | Integrate into capital calculation pipeline | Tech | ● |  | ● |  | 2 weeks | HT5.1
HS5.2a | Subtask | Ensure IMCC calculation uses modellable RFs with quality-checked, carry-stripped, proxy-lineage-complete history | Tech | ● |  | ● |  | 3 days | HT5.1
HS5.2b | Subtask | Ensure SES calculation uses NMRF stress scenarios computed on quality-checked history | Tech | ● |  | ● |  | 3 days | HS5.2a
HS5.2c | Subtask | Build capital impact attribution: decompose capital change into: data quality fix, history extension, proxy enhancement, carry removal | Quant | ● |  | ● |  | 3 days | HS5.2b
HS5.2d | Subtask | Run full parallel capital calculation: old history vs. new history — quantify total capital impact | Quant |  |  | ● | ● | 3 days | HS5.2c
HB5.2 | BCA | Capital calculation running on strengthened history; impact quantified and approved by CFO/CRO | Tech | ● |  | ● | ● |  | HS5.2d
HT5.3 | Task | Integrate DQ framework as gating check for capital production | Tech | ● | ● | ● |  | 2 weeks | HT5.2
HS5.3a | Subtask | Build pre-calculation DQ gate: block ES/VaR calculation if critical DQ issues detected in input data | Tech | ● |  | ● |  | 3 days | HT5.2
HS5.3b | Subtask | Define severity levels: which DQ issues block production, which flag for review, which are informational | Quant |  |  | ● | ● | 2 days | HS5.3a
HS5.3c | Subtask | Build fallback logic: if primary RF data fails DQ, automatically switch to proxy or previous-day value with alert | Tech | ● |  | ● |  | 3 days | HS5.3b
HS5.3d | Subtask | Build daily DQ sign-off workflow: risk manager must acknowledge any overridden DQ flags before capital is final | Tech | ● |  |  | ● | 3 days | HS5.3c
HS5.3e | Subtask | Integrate DQ metrics into backtesting attribution: can DQ issues explain backtesting exceptions? | Quant | ● |  | ● |  | 3 days | HS5.3d
HB5.3 | BCA | DQ-gated capital production live; daily sign-off workflow active; DQ integrated into backtesting attribution | Tech | ● | ● | ● | ● |  | HS5.3e
H6 | Deliverable | Ongoing Governance: Proxy, History & DQ Operations | Quant | ○ | ● | ● | ● | 4 weeks | H5
HT6.1 | Task | Establish proxy governance and review cycle | Quant |  |  | ● | ● | 2 weeks | H5
HS6.1a | Subtask | Define quarterly proxy review: re-run correlation, vol ratio, regime tests on all active proxies | Quant |  |  | ● |  | 3 days | H5
HS6.1b | Subtask | Define proxy promotion path: when direct data becomes available, transition from proxy to direct with parallel period | Data Eng |  | ● | ● |  | 3 days | HS6.1a
HS6.1c | Subtask | Define new proxy onboarding process: approval workflow for any new proxy relationship | Quant |  |  | ● | ● | 2 days | HS6.1b
HS6.1d | Subtask | Define proxy documentation standard: minimum required fields, update cadence, sign-off authority | Quant |  |  | ● | ● | 2 days | HS6.1c
HB6.1 | BCA | Proxy governance framework documented and approved; integrated into quarterly RFET cycle | Quant |  |  | ● | ● |  | HS6.1d
HT6.2 | Task | Establish ongoing history maintenance process | Data Eng | ● | ● | ● |  | 2 weeks | HT6.1
HS6.2a | Subtask | Define daily history append process: new business day data → quality check → append to warehouse → available for next-day ES/VaR | Tech | ● | ● |  |  | 3 days | HT6.1
HS6.2b | Subtask | Define monthly history review: scan for newly discovered gaps, newly available vendor data, stale series | Data Eng |  | ● | ● |  | 3 days | HS6.2a
HS6.2c | Subtask | Define annual deep audit: comprehensive re-validation of all proxy relationships, history extensions, and DQ fixes | Quant |  | ● | ● | ● | 3 days | HS6.2b
HS6.2d | Subtask | Build automated monitoring: alert if any RF's history falls below ES minimum requirements (e.g., gaps emerge) | Tech | ● |  | ● |  | 3 days | HS6.2c
HB6.2 | BCA | Ongoing history maintenance process documented and operational; responsibilities assigned; monitoring live | Data Eng | ● | ● | ● | ● |  | HS6.2d

## Legend
Level | Description
Deliverable | Major work package — the 'what' at the highest level
Milestone | Key checkpoint — a gate that must be reached before proceeding
Task | A discrete unit of work that produces a specific output
Subtask | A component of a task — the granular 'how'
BCA | Business Completion Activity — sign-off, review, or approval that marks completion
Symbol | Meaning
● | Primary / heavy involvement
○ | Secondary / advisory involvement
— | No dependency