## Slide 1
RFET Data Project Plan — Working Session
Aligning Capital, Tech, Risk, and PM on what it takes to be IMA-ready
Central Question: If senior management or regulators ask us what it takes to be IMA-ready, does this plan answer that clearly enough?
Two parallel workstreams — they feed each other, they don't wait for each other
Workstream A: Make the Data Right
History, proxies, carry removal, DQ framework, lineage — defines the risk factor universe
⟷
Workstream B: Classify Every Risk Factor
RFET qualitative + quantitative tests, RPO sourcing, bucketing, modellable vs. non-modellable classification
A defines the RF universe that B tests. B's classification tells A which RFs are most capital-critical to fix. Non-modellable because of a weak proxy? → A's top priority.
What we need from this room today:
Is the task breakdown complete?
Does the sequencing make sense?
Where is ownership unclear?
What needs to be built vs. reused?
What exit criteria prove readiness?
What are we missing that could turn this red?
Today's focus: Workstream B — RFET. Classify every RF as Modellable (→ IMCC, capital-efficient) or Non-Modellable (→ SES, punitive).

## Slide 2
RFET — Why This Is One of the Most Complex Workstreams
Each box below is a design decision that, if scoped incorrectly, can turn the project red.
RPO Sourcing & Mapping
Which sources qualify as arm's-length? How do we map a 9.75Y trade to a 10Y bucket? Own vs. standard bucketing changes our entire classification outcome.
Bucketing Decisions
Bucket boundaries directly drive modellable vs. NMRF. Wider = more RPOs per RF = easier to pass. But qualitative test may push back. May force us to change our existing RF granularity.
RF Derivation Choices
How we parameterize vol surfaces (sigma, skew, smile, butterfly), whether we use forward rates or spread-based RFs, how we compute FX basis — are these consistent and defensible?
Proxy Defensibility
Will proxying SOFR to OIS pass qualitative tests? Do 2008 proxy assumptions still hold for stress period? Weak proxies = automatic Type B NMRF = maximum capital penalty.
Systematic vs. Idiosyncratic Risk
Are we capturing both correctly? Is there a gap in residual risk treatment? Regulator will test whether our RF decomposition is complete — no unaccounted-for risk.
Tech Infrastructure
Can we run qualitative + quantitative tests at scale across 35K RFs? Store and deduplicate RPOs daily? Build the dashboard? Support quarterly refresh? EMR + MARS integration.
NMRF-to-Modellable Migration
If a RF is NMRF today, what is the path to make it modellable? Source more RPOs? Improve proxy? Change bucketing? This scope is often missed — but it's where capital savings live.
Industry Alignment Drift
Are our derivation choices (vol parameterization, basis construction, spread methodology) aligned with industry/banking standards — or have we drifted? Misalignment = supervisory challenge.
Qualitative Test Cascade
Failing qualitative tests forces proxy enhancement, which forces history rebuild, which forces re-validation — a single failure can cascade across 3 workstreams and 6 months of rework.
High risk — can turn project red
Medium risk — design decision needed
Scope gap — often missed entirely

## Slide 3
Questions That Must Be Answered Before We Can Finalize Scope
Each unanswered question below is scope risk. If we don't resolve these now, they become surprises later.
Area | Question | Needs Answer From
RPOs & Bucketing | Do we use own bucketing or standard bucketing — and does that choice force us to change our existing RF granularity? | Quant + Capital
RPOs & Bucketing | Which RPO sources qualify as arm's-length per NPR? Do we need third-party audit verification for any vendor? | Quant + Legal
Proxy Quality | Will proxying SOFR to OIS pass qualitative tests? What about other common proxies in our universe? | Quant + Risk Model
Proxy Quality | Do our 2008 proxy assumptions still hold for stress period calibration — or has the relationship broken? | Quant
RF Derivation | How do we parameterize vol surfaces — sigma, skew, smile, butterfly? Is this consistent across asset classes? | Quant + Risk Model
RF Derivation | Is the way we compute FX cross-currency basis consistent and defensible under supervisor scrutiny? | Quant + Risk Model
RF Derivation | Are we using forward rates or spread-based risk factors for credit? Are derivation choices aligned with industry standards — or have we drifted? | Quant + FO Models
Coverage Gaps | Are we capturing systematic and idiosyncratic risk correctly, or is there a gap in residual risk treatment? | Risk Model
Coverage Gaps | If a RF is NMRF today, what is the concrete migration path to make it modellable? Is that scope captured anywhere? | Quant + Capital
Technology | Can our current infrastructure run qualitative + quantitative tests at scale across 35K RFs with quarterly refresh? | Risk Tech
Technology | On-the-fly vs. pre-stored for carry-stripped shifts and RPO mapping — which architecture, and can EMR + MARS both support it? | Risk Tech
Cascade Risk | If qualitative tests fail for a category of proxies, that triggers proxy enhancement → history rebuild → re-validation. Is the timeline buffer for this cascade in the plan? | All teams