## WS-A Data Analytics
Level | Description | Work Type | Action | Output → To | Depends On
Deliverable | Deliverable 1: Risk Factor Identification, Mapping & Taxonomy
Output Summary | Outputs: MDO catalog per desk · Unified RF catalog · RF taxonomy & LH assignments · Five-category MDO-to-RF mapping matrix · Gap & remediation register · RF specs for onboarding
Sequence | ⬇ M1 → M2 → M3 are sequential (each builds on prior output) ¦ M1 tasks can run in parallel within the milestone
Milestone | M1 — Extract, Catalog & Build RF Taxonomy |  |  | MDO catalog + unified RF catalog + taxonomy
First step: build the two inventories (MDO and RF) that everything else depends on. Pure data gathering and classification — no Tech dependency.
Task | Gather MDO catalog from FO pricing systems | Data Analytics | Gather | MDO catalog → M2 mapping | FO: system access
Subtask | Connect to each FO pricer (Vasara, Mercury, SPG, Endur) — extract all MDOs per desk, document system-of-record and access method | FO Collaboration | Collaborate |  | FO Tech
Subtask | Classify every MDO by type (IR curve, FX spot, vol surface, credit spread, basis, OAS, correlation, dividend, commodity, equity) — standardise naming across systems | Data Analytics | Classify
Subtask | Reconcile MDO extracts across systems: flag duplicates, aliases, naming conflicts | Data Analytics | Analyze |  | FO: confirm aliases
Task | Gather RF catalog from risk engines and SA engine | Data Analytics | Gather | Unified RF catalog → M2 | Risk Tech: engine access
Subtask | Pull RF catalog from EMR: name, type, asset class, tenor/strike grid, representation, derivation, proxy flag | Data Analytics | Gather |  | Risk Tech: EMR
Subtask | Pull RF catalog from MARS — flag EMR/MARS discrepancies | Data Analytics | Gather |  | Risk Tech: MARS
Subtask | Pull RF catalog from SA engine: Delta, Vega, Curvature across GIRR, CSR, FX, EQ, COMM | Data Analytics | Gather |  | Capital Tech: SA
Subtask | Pull RF set from PLA (HPL/RTPL) — identify mismatches vs. ES/VaR RF set | Data Analytics | Analyze |  | PLA team
Subtask | Reconcile across EMR, MARS, SA, PLA: produce unified RF master list with cross-system flags | Data Analytics | Analyze | Unified RF master → all
Task | Define RF taxonomy and granularity standards | Risk Development | Develop | RF taxonomy → RFET, ES, PLA | RA: methodology
Subtask | Create classification: curves, surfaces, spreads, basis, prices, vols, correlation — per issuer/sector/region/tenor/strike | Risk Development | Develop |  | RA
Subtask | Populate RF representation attributes: asset class, risk class, currency, tenor, strike, issuer, sector, region, source, transformation | Data Analytics | Classify
Subtask | Design queryable RF repository to replace spreadsheets — consumed by RFET, ES, SES, PLA, VaR | Data Analytics | Develop | RF repo spec → Tech
Task | Build RF-to-Liquidity Horizon mapping | Risk Development | Develop | LH assignments → RFET thresholds | RA
Subtask | Rule-based LH for IR and FX (well-defined regulatory mapping) | Data Analytics | Build PoC
Subtask | For EQ and Credit: source metadata for LH (market cap, index, rating, sector) | Data Analytics | Gather |  | FO: metadata
Task | Build complete proxy mapping back to 2007 | Data Analytics | Analyze | Proxy inventory → M4 (Hist)
Subtask | Per proxied RF: document proxy used, effective date, splice method, justification on record | Data Analytics | Analyze
M1 Output → MDO catalog, unified RF catalog, RF taxonomy, LH assignments, proxy inventory — feeds M2 below and WS-B (RFET)
Milestone | M2 — Map, Classify & Analyze Gaps (five-category matrix) |  |  | Mapping matrix + gap register | Requires M1 outputs
With both inventories in hand, now build the linkage and classify every relationship. This is the analytical core — where gaps, disconnects, and future needs surface.
Task | Map MDOs to Risk Factors — classify every relationship | Data Analytics | Classify | Five-category matrix → M3 | FO + Risk Model
Subtask | Category 1 — Correctly Mapped: direct MDO↔RF correspondence — document, no action | Data Analytics | Classify
Subtask | Category 2 — Not Mapped, In Scope: MDO with no RF (correlation, implied spreads, dividends) — decide: build, proxy, or accept NMRF | Data Analytics | Analyze | New RF needs → M3 | RA: capital cost-benefit
Subtask | Category 3 — Not In Scope: pricing inputs not representing market risk — document exclusion | Data Analytics | Classify |  | Risk Model: confirm
Subtask | Category 4 — FO/Risk Disconnect: representation mismatch (CDS, Muni, Corp, Structured Credit) | FO Collaboration | Analyze | Disconnect register → FO | FO Models + Risk Model
Subtask | Category 5 — Future RF Needs: Full Config, Vega, EQ vol, CCY basis, CLO/ABS, Vasara-triggered | Data Analytics | Analyze | Future RF list → Migration WS | FO Models
Task | Quantify gaps by capital and PLA impact | Data Analytics | Analyze | Prioritised gap register | RA + Capital Tech
Subtask | Per Cat 2/4 gap: estimate SES capital cost vs. build/fix investment — rank by net capital benefit | Data Analytics | Analyze |  | Capital Tech: SES est.
Subtask | Per Cat 2/4 gap: estimate HPL-RTPL noise contribution — identify primary PLA failure drivers | Data Analytics | Analyze |  | PLA team
Subtask | Produce consolidated register: gap, category, asset class, desks, capital rank, PLA rank, action, effort, dependencies | Data Analytics | Develop | Gap register → Mgmt
M2 Output → Five-category mapping matrix + prioritised gap register — feeds M3 and WS-D (Migration)
Milestone | M3 — RF Specifications & Remediation Planning |  |  | RF specs + dependency map → Tech/Migration WS | Requires M2 outputs
Task | Define specifications for new/fixed risk factors | Risk Development | Develop | RF specs → Tech build (WS-C) | RA + Risk Model
Subtask | Per RF: name, asset class, granularity (tenor/strike/issuer grid), representation, derivation, source MDOs | Risk Development | Develop |  | RA
Subtask | Per RF: historical data requirements, backfill feasibility to 2007, proxy strategy for gaps | Data Analytics | Analyze
Subtask | Per RF: cross-team dependency chain: FO Models → Risk Model → Risk Tech → Market Data → PLA | Cross-Team | Collaborate | Dependency map → all | All teams
M3 Output → RF specifications + dependency map — handoff to Tech (WS-C) for build and Migration (WS-D) for onboarding
Deliverable | Deliverable 2: Historical Data Inventory, Proxy Assessment & Data Quality
Output Summary | Outputs: History inventory register · Proxy framework & registry · DQ scorecard · Carry removal methodology · Data strengthening methodology · History extension plan
Sequence | ⬇ M4 → M5 → M6 are sequential ¦ M7 (DQ, Carry, Strengthening) can run in parallel with M5-M6 ¦ M4 can start in parallel with M1
Milestone | M4 — Historical RF Inventory & Data Lineage |  |  | History inventory register | Can start parallel with M1
Build the complete picture of what historical data exists, where it lives, how it was derived, and what's missing — before any strengthening work begins.
Task | Catalog all historical time series feeding VaR/ES | Data Analytics | Gather | History inventory → M5-M7 | Risk Tech: system access
Subtask | Per RF: source system (RFDM, MDSOR, vendor), start date, end date, frequency, format | Data Analytics | Gather
Subtask | Assess coverage vs. 2007 — quantify gap, identify missing stress periods (GFC, COVID, 2022) | Data Analytics | Analyze
Subtask | Catalog source systems: RFDM, MDSOR, Bloomberg, Refinitiv, Markit, ICE — access methods, owners | Data Analytics | Gather |  | Market Data
Task | Document derivation chains and detect inconsistencies | Data Analytics | Analyze | Derivation lineage → validation | RA
Subtask | Per RF: trace raw data → final series (all transformations: interpolation, roll, spread derivation, proxy) | Data Analytics | Analyze
Subtask | Flag derivation methodology changes over time (e.g., bootstrap method changed but history not re-derived) | Data Analytics | Analyze |  | RA
Subtask | Check consistency with current FO pricing model assumptions | FO Collaboration | Analyze |  | FO Models
Task | Audit existing proxies and catalog benchmark transitions | Data Analytics | Analyze | Proxy audit + transition register
Subtask | Per proxied RF: proxy used, effective date, splice method, justification — classify green/yellow/red | Data Analytics | Classify |  | RA
Subtask | Identify proxy chains (RF_A → RF_B → RF_C) — regulatory red flag | Data Analytics | Analyze
Subtask | Catalog benchmark transitions: LIBOR→SOFR, EONIA→€STR, CDOR→CORRA — status per RF | Data Analytics | Analyze
Subtask | Catalog structural breaks: EM rebasings, corporate actions, index reconstitutions, credit restructurings | Data Analytics | Analyze
Task | Produce History Inventory Register | Data Analytics | Develop | Register → all teams
Subtask | One row per RF: source, coverage, gaps, frequency, derivation, proxy details, transitions, readiness (G/Y/R) | Data Analytics | Develop
Subtask | Summary analytics: coverage heatmap, proxy concentration, transition readiness | Data Analytics | Analyze
Subtask | Top-priority remediation targets: short history + poor proxy + high ES materiality | Data Analytics | Analyze | Priority list → M5-M7 | RA: ES materiality
M4 Output → History inventory register with coverage, lineage, proxy status, transitions, readiness — foundation for M5, M6, M7
Milestone | M5 — Proxy Principles & Framework Design |  |  | Formal proxy methodology paper | Requires M4 (proxy audit)
Task | Define proxy acceptability criteria and quantitative thresholds | Risk Development | Develop | Proxy framework → M6 | RA + Risk Model
Subtask | Proximity requirements, basis risk thresholds, NMRF reclassification boundary | Risk Development | Develop |  | RA
Subtask | Quantitative: correlation floor, vol ratio band, tracking error ceiling, cointegration test | Risk Development | Develop |  | RA
Subtask | Stress-period validation: test over GFC, COVID, 2022 — stress-specific thresholds | Risk Development | Develop |  | RA
Task | Define hierarchy, lifecycle, and governance rules | Risk Development | Develop |  | RA
Subtask | Hierarchy: direct > same-issuer > same-sector > index > benchmark > cross-asset | Risk Development | Develop
Subtask | Lifecycle: assign → upgrade → challenge → retire/NMRF — with capital impact at each decision | Risk Development | Develop |  | Capital Tech
Task | Document formal proxy methodology paper | Risk Development | Develop | Methodology paper → MRM | RA + Risk Model
M5 Output → Proxy framework: acceptability criteria, thresholds, hierarchy, lifecycle, stress rules — feeds M6
Milestone | M6 — Asset-Class Proxy Implementation & Registry |  |  | Proxy registry with full lineage | Requires M5 framework
Task | Develop proxy methodologies per asset class with RA | Risk Development | Develop | Proxy methods per AC | RA: co-develop
Subtask | IR: tenor interpolation, curve-to-curve, cross-currency basis, inflation — implement in Python | Risk Development | Develop |  | RA
Subtask | FX: cross-rate triangulation, EM pegged-currency, vol surface proxying | Risk Development | Develop |  | RA
Subtask | Credit: issuer-to-sector, single-name to index, CDS-bond basis, recovery rate | Risk Development | Develop |  | RA
Subtask | Equity: single-name to sector/index, dividend proxying, vol surface proxying | Risk Development | Develop |  | RA
Subtask | Commodity: contract roll, grade substitution, location basis | Risk Development | Develop |  | RA
Task | Run proxy assignment and validation across all RFs | Data Analytics | Analyze | Validated proxy assignments | RA: validation
Subtask | Per RF: identify candidates, compute metrics, rank, select best proxy | Data Analytics | Analyze
Subtask | Stress-period validation over GFC, COVID, 2022 per proxy | Data Analytics | Analyze
Subtask | Classify: green (all pass), yellow (marginal in stress), red (fails → fix or NMRF) | Data Analytics | Classify |  | RA
Subtask | Red proxies: investigate alternatives or escalate to NMRF with capital impact | Data Analytics | Analyze | NMRF escalations → Capital | Capital Tech
Task | Produce proxy registry with full lineage | Data Analytics | Develop | Proxy registry → ES, Regulatory
Subtask | Per proxy: original RF → proxy RF → series → source → splice → metrics → justification | Data Analytics | Develop
Subtask | Concentration risk analysis and capital impact quantification | Data Analytics | Analyze | Capital impact → Mgmt | Capital Tech
M6 Output → Proxy registry: full lineage, validation metrics, quality classification, capital impact — feeds WS-C (Tech) and ES production
Sequence | ⬇ M7 runs in PARALLEL with M5-M6 — no dependency on proxy framework, only on M4 inventory
Milestone | M7 — DQ Assessment, Carry Methodology & Data Strengthening (parallel) |  |  | DQ scorecard + carry methodology + extension plan | Requires M4 inventory
Task | Run baseline DQ assessment across all RF time series | Data Analytics | Analyze | DQ scorecard → remediation | RA: methodology
Subtask | Execute Tier 1-3 checks: gaps, stale prices, outliers, stat anomalies, peer-group divergence | Data Analytics | Analyze
Subtask | Produce scorecard: per-RF quality (G/Y/R), downstream impact estimate, remediation action | Data Analytics | Develop | DQ scorecard → all teams
Task | Develop carry removal methodology with RA | Risk Development | Develop | Carry methodology → Tech (WS-C) | RA: co-develop
Subtask | Document regulatory motivation: carry biases ES, distorts PLA, misleads backtesting | Risk Development | Develop |  | RA
Subtask | Assess applicability per RF type, quantify magnitude, build decision tree | Data Analytics | Analyze |  | RA
Subtask | Develop Scenario A (curve interpolation), B (√T theta), C (rolling median) — build PoC in Python | Risk Development | Build PoC |  | RA
Subtask | Validate impact on return distributions, PLA tests, ES — document in methodology paper | Data Analytics | Analyze | Methodology paper → MRM | RA
Task | Develop data strengthening & history extension methodology | Risk Development | Develop | Methodology → Tech (WS-C) | RA: co-develop
Subtask | Gap-fill rules per asset class: linear, cubic spline, carry-forward — outlier treatment with event-aware overrides | Risk Development | Develop |  | RA
Subtask | LIBOR→SOFR transition methodology: backcast vs. splice, spread adjustments per currency | Risk Development | Develop |  | RA + FO Models
Subtask | Per RF: classify extension strategy (sourcing / methodology / proxy) — prioritise by capital impact | Data Analytics | Analyze | Extension plan → Sourcing WS
M7 Output → DQ scorecard + carry methodology (3 scenarios + decision tree) + data strengthening methodology + history extension plan — all feed WS-C (Tech build)

## WS-B RFET Modellability
Level | Description | Work Type | Action | Output → To | Depends On
Deliverable | Deliverable: RFET Quantitative & Qualitative Test Engine
Output Summary | Outputs: RPO source registry · RPO database · RPO-to-RF mapping · Qualitative test results · Counting engine · Classification register (Modellable / NMRF A / NMRF B) · Monitoring dashboard
Sequence | ⬇ M1 + M2 run in PARALLEL (sourcing + qualitative design) ¦ M3 requires M1 + WS-A taxonomy ¦ M4 requires M3 ¦ M5-M6-M7 are sequential
Milestone | M1 — RPO Sourcing & Vendor Infrastructure (start immediately) |  |  | RPO source registry + vendor contracts
Long lead time — vendor negotiations and licensing can take months. Start immediately alongside WS-A analytics.
Task | Identify and assess RPO data sources per asset class | Sourcing | Gather | RPO source registry
Subtask | Inventory candidates: exchanges, TRACE, DTCC, Markit, Bloomberg, ICE, internal execution data | Sourcing | Gather
Subtask | Assess each for coverage, quality, regulatory acceptability ("real price" under NPR) | Data Analytics | Analyze |  | RA: regulatory criteria
Subtask | Identify coverage gaps by asset class — can internal data supplement, or default to NMRF? | Data Analytics | Analyze
Subtask | Negotiate vendor contracts and licensing — coordinate with Procurement and Business | Sourcing | Collaborate |  | Business: procurement
Dep | Dependency: Business — vendor contract execution, licensing terms, delivery formats |  |  |  | Business + Procurement
M1 Output → RPO source registry + vendor contracts signed +
Milestone | M2 — RFET Qualitative Test Framework (start immediately, parallel with M1) |  |  | Qualitative test results per RF
Task | Design qualitative test methodology | Risk Development | Develop | Qual framework → M6 classification | RA + Risk Model
Subtask | Define six quality standards: real price backing, update frequency, source reliability, vol/corr capture, model-derived flagging, proxy justification | Risk Development | Develop |  | RA
Subtask | Build scoring rules and pass/fail criteria per standard | Risk Development | Develop |  | Risk Model: sign-off
Subtask | Run qualitative assessment across all RFs — produce per-RF results | Data Analytics | Analyze | Qual results → M6
M2 Output → Qualitative test framework + per-RF results — feeds M6 (final classification)
Milestone | M3 — RPO-to-RF Mapping Design & Bucketing |  |  | Mapping design + bucketing rules → PoC | Requires: M1 (RPO data) + WS-A M1 (RF taxonomy)
Task | Design RPO-to-RF translation architecture | Risk Development | Develop | Mapping design → M4 PoC | RA
Subtask | Determine mapping path: RPO → instrument → MDO → RF vs. RPO → RF direct vs. hybrid | Risk Development | Develop |  | RA
Subtask | Design instrument metadata enrichment: resolve to canonical instrument (CUSIP, ISIN, asset class, tenor, strike, issuer) | Data Analytics | Develop
Subtask | Design RF linkage engine: match enriched RPO to RF keys | Risk Development | Develop |  | Consumes: WS-A taxonomy
Subtask | Handle edge cases: one instrument → multiple RFs, unmapped instruments, boundary ambiguity | Data Analytics | Analyze |  | RA
Task | Define RF bucketing methodology per NPR | Risk Development | Develop | Bucketing rules → M4 | RA + Risk Model
Subtask | Define bucket boundaries: IR (tenor), EQ (name vs. index), Credit (issuer/sector/rating), Commodity (contract/grade/location), FX (pair) | Risk Development | Develop |  | RA
Subtask | Decide own vs. prescribed bucketing — document regulatory justification | Risk Development | Develop |  | Risk Model
M3 Output → RPO-to-RF mapping design + bucketing methodology — ready for PoC
Milestone | M4 — RFET Quantitative PoC |  |  | Validated PoC + stakeholder sign-off → prod spec | Requires M3 design + M1 RPO data
Task | Build end-to-end PoC on a single asset class | Data Analytics | Build PoC | PoC results → Demo
Subtask | Select PoC asset class (e.g., IR — exchange-traded, clear bucketing, high RPO density) | Data Analytics | Analyze
Subtask | Build in Python: ingest → normalise → RPO-to-RF map → bucket → count → classify | Data Analytics | Build PoC
Subtask | Validate: automated classification vs. manual expert assessment — quantify accuracy, document edge cases | Data Analytics | Analyze |  | RA: expert review
Task | Demo PoC and obtain sign-off for production build | Cross-Team | Collaborate | Sign-off → M5 (prod spec) | All stakeholders
Subtask | Present to Risk Model, Capital Tech, Risk Tech, senior management: accuracy, capital impact, scaling plan | Cross-Team | Collaborate
Subtask | Collect feedback — incorporate into production specification | Cross-Team | Collaborate
Subtask | Obtain approval: scope (all ACs), timeline, Tech commitment, ownership model | Cross-Team | Collaborate |  | Risk Tech + Capital Tech
M4 Output → Validated PoC + stakeholder sign-off — handoff to M5 (production spec for Tech)
Milestone | M5 — Production Specification (→ handoff to Tech WS-C) |  |  | Complete prod spec → Risk Tech | Requires M4 PoC
Task | Produce detailed production requirements for RPO infrastructure | Data Analytics | Develop | Prod spec → Risk Tech (WS-C) | PoC learnings
Subtask | Database schema spec: multi-source RPO storage, dedup logic, backfill, audit trail | Data Analytics | Develop
Subtask | Ingestion pipeline spec per vendor: formats, validation, error handling, retry | Data Analytics | Develop
Subtask | RPO normaliser spec: attribute extraction, multi-source blending, degradation handling | Data Analytics | Develop
Subtask | Counting engine spec: rolling 12-month, max-one-per-day dedup, thresholds (≥24 LH≤20d, ≥16 LH>20d) | Data Analytics | Develop
Subtask | Classification engine spec: qual + quant → Modellable / NMRF A / NMRF B → capital routing API | Data Analytics | Develop
Subtask | Dashboard spec: desk-level, asset-class-level, early-warning, capital simulator | Data Analytics | Develop
Dep | Handoff → Risk Tech (WS-C) builds production infrastructure from these specifications |  |  |  | Risk Tech
Dep | Handoff → Capital Tech confirms IMCC/SES engine will consume classification via API |  |  |  | Capital Tech
M5 Output → Complete production specification: RPO infra, normaliser, mapping, counting, classification, dashboard → handed to Tech (WS-C)
Milestone | M6 — UAT, Final Classification & Go-Live (after Tech delivers WS-C) |  |  | Classification register + go-live | Requires: WS-C Tech delivery + M2 qual results
Task | Test Technology's production implementation | Data Analytics | Analyze | UAT results → Go/No-Go | Risk Tech: delivery
Subtask | Define acceptance criteria: ingestion 100%, normalisation ≥99%, mapping ≥95%, counting zero-error | Data Analytics | Develop
Subtask | Execute UAT across all asset classes: compare production vs. PoC baseline + expert review | Data Analytics | Analyze
Subtask | Stress testing: vendor failure, volume spikes, boundary-crossing scenarios | Data Analytics | Analyze |  | Risk Tech
Subtask | Parallel run: new engine vs. existing process for 1+ month — reconcile | Data Analytics | Analyze |  | Risk Tech
Task | Produce final RFET classification register | Data Analytics | Classify | Classification → Capital routing | Capital Tech
Subtask | Per RF: qual result + quant result → Modellable / NMRF A / NMRF B → IMCC vs. SES routing + capital impact | Data Analytics | Classify
Subtask | Per NMRF: estimate SES charge vs. IMCC counterfactual — quantify capital cost | Data Analytics | Analyze | Capital impact → Mgmt | Capital Tech
Task | Sign off and go live | Cross-Team | Collaborate | Production go-live | Senior Mgmt
Subtask | Production readiness sign-off: test results, known issues, remediation plan | Cross-Team | Collaborate |  | Risk Model + Capital Tech
M6 Output → Final classification register (Modellable / NMRF A / NMRF B) in production with capital routing
Milestone | M7 — BAU Process & Governance |  |  | BAU operating model + governance docs | After M6 go-live
Task | Establish RFET BAU process | Governance | Develop | BAU manual → Operations
Subtask | Daily: automated ingestion, classification, exception review, SLA | Governance | Develop
Subtask | Quarterly: full reclassification, prior-quarter comparison, reclassification documentation | Governance | Develop
Subtask | Trigger-based: vendor loss, liquidity event, new RF, methodology change → out-of-cycle reclassification | Governance | Develop
Subtask | Roles: Quant Data (methodology), Risk Tech (infra), Capital Tech (routing), Risk Model (governance), Market Data (vendors) | Governance | Develop
Subtask | Runbooks, escalation matrices, SLA definitions, regulatory exam checklist | Governance | Develop | BAU manual
Dep | Dependency: Capital Tech — reclassification triggers re-routing between IMCC and SES |  |  |  | Capital Tech
M7 Output → Governed BAU process: daily ops, quarterly refresh, trigger-based reclassification, documented and audit-ready

## RFET_Feedback
Deliverable | Deliverable: RFET Quantitative & Qualitative Test Engine
Build an end-to-end, automated infrastructure that sources Real Price Observations from multiple vendors, maps them to the internal risk factor taxonomy, counts observations against regulatory thresholds, and produces a defensible Modellable vs. Non-Modellable classification for every risk factor in the IMA universe.
Reality constraint: RPOs come from exchanges, TRACE, DTCC, Markit, Bloomberg, ICE, and internal execution data — each in different formats, identifiers, and granularity. There is no universal RPO-to-RF key. The translation layer linking raw trade observations to the internal RF taxonomy is the hardest engineering problem in this milestone. Not every vendor covers every asset class, so the infrastructure must be multi-source by design.
Milestone | M1 — RPO Sourcing & Vendor Infrastructure (start immediately)
Task | Identify and assess RPO data sources per asset class
Subtask | Inventory candidates: exchanges, TRACE, DTCC, Markit, Bloomberg, ICE, internal execution data
Subtask | Assess each for coverage, quality, regulatory acceptability ("real price" under NPR)
Subtask | Identify coverage gaps by asset class — can internal data supplement, or default to NMRF?
Subtask | Negotiate vendor contracts and licensing — coordinate with Procurement and Business
Task | get approval for data purchase and onboard RPO data sources across all asset classes in scope
Task | Decide on RPO will be stored --> cross-team
Milestone | Work with Tech to Build RPO storage, ingestion, and deduplication infrastructure
Task | Work with Tech to Build RPO storage, ingestion, and deduplication infrastructure
Task | Design database schema for multi-source RPO storage: accommodate different vendor formats, identifiers, and metadata while maintaining a unified query layer — schema must support historical backfill, daily append, and audit trail of all ingested observations
Task | Build daily ingestion pipelines per vendor: automated file/API pull, format parsing, validation checks (completeness, schema conformance, duplicate detection), and error handling with retry logic and alerting
Task | Implement max-one-per-day deduplication logic per NPR requirements: when multiple observations exist for the same instrument on the same day from the same or different sources, apply regulatory dedup rules and retain only one qualifying RPO per RF bucket per day
Task | Build the RPO Normaliser: extract structured attributes from raw instrument descriptions — asset class, sub-type, currency, tenor, maturity, strike, issuer, sector, rating, region, index membership — to enable downstream mapping to internal RF taxonomy
Task | Design the infrastructure to be multi-source by construction: blend sources, handle overlapping coverage without double-counting, and gracefully degrade when a vendor feed is late or missing
Task | Backfill 12+ months of historical RPOs from all onboarded vendors to support the initial modellability classification run on day one
Milestone | Build the RPO-to-RF mapping and translation and linkage layer (the translation layer)
Task | Design the mapping architecture: determine whether to map RPO → instrument → MDO → RF (leveraging the A.2 MDO-to-RF mapping), or RPO → RF directly, or a hybrid approach — document trade-offs (coverage vs. maintenance burden vs. accuracy)
Task | Build instrument-level metadata enrichment: for each RPO, resolve to a canonical instrument with attributes (CUSIP, ISIN, asset class, issuer, sector, region, tenor, strike, currency, index membership) using vendor reference data and internal securities master
Task | Build the RF linkage engine: map enriched RPO instruments to internal RF keys using the RF taxonomy and metadata from Milestone A.3 — matching on asset class, sub-type, currency, tenor bucket, strike bucket, issuer/sector/region dimensions
Task | Determine whether trade-level detail should inform the mapping: can internal trade/execution data establish MDO consumption patterns that improve the RPO-to-RF linkage (e.g., a trade in instrument X consumed MDO Y which maps to RF Z — therefore RPO for instrument X supports RF Z)?
Task | Handle mapping edge cases: instruments that map to multiple RFs (a bond trade provides RPOs for both credit spread and interest rate RFs), instruments that map to no RF (traded but not in the risk model), and instruments where the mapping is ambiguous (sector/rating bucket boundary cases)
Task | Build the mapping output table: RPO_ID → Instrument → RF_Key → Bucket → mapping confidence score → mapping method (direct/inferred/trade-based) — with full audit trail
Outcome → RPO-to-RF mapping engine linking every normalised RPO to zero, one, or multiple internal RF keys, with confidence scoring and audit trail
Milestone | Biuild Bucketing Engine
Task | Define and implement RF bucketing approach per NPR requirements
Task | Define bucketing methodology per RF type: how tenor ranges, strike ranges, issuer groupings, and regional groupings define bucket boundaries — document approach per asset class (IR: tenor buckets; EQ: single-name vs. index; Credit: issuer/sector/rating; Commodity: contract/grade/location; FX: currency pair)
Task | Determine whether to use own bucketing approach or standard/prescribed bucketing — document regulatory basis and justification for chosen approach, as supervisors will challenge bucket definitions that are too broad (inflating RPO counts)
Task | Build automated RPO → bucket → RF mapping engine: for each normalised, RF-linked RPO, assign to the correct bucket and validate that the bucket-RF relationship is consistent with the taxonomy from A.3
Milestone | Build quantitative counting engine with regulatory thresholds
Task | Implement the rolling 12-month RPO counting logic: for each RF bucket, count distinct RPO days over the trailing 12-month window, applying max-one-per-day dedup
Task | Apply prescribed pass/fail thresholds: ≥24 RPOs for risk factors with liquidity horizon ≤ 20 days, ≥16 RPOs for risk factors with liquidity horizon > 20 days — consume LH assignments from Milestone A.3
Task | Handle threshold edge cases: risk factors near the boundary (e.g., 23 or 15 RPOs), risk factors that oscillate between modellable and non-modellable across consecutive months, and newly onboarded risk factors with less than 12 months of RPO history
Task | Produce per-RF quantitative test output: RPO count, threshold, pass/fail, days-to-breach (how many RPOs would need to drop off before reclassification), and trend over time
Milestone | M4 — RFET Quantitative PoC
Task | Build end-to-end PoC on a single asset class
Subtask | Select PoC asset class (e.g., IR — exchange-traded, clear bucketing, high RPO density)
Subtask | Build in Python: ingest → normalise → RPO-to-RF map → bucket → count → classify
Subtask | Validate: automated classification vs. manual expert assessment — quantify accuracy, document edge cases
Task | Demo PoC and obtain sign-off for production build
Subtask | Present to Risk Model, Capital Tech, Risk Tech, senior management: accuracy, capital impact, scaling plan
Subtask | Collect feedback — incorporate into production specification
Subtask | Obtain approval: scope (all ACs), timeline, Tech commitment, ownership model
M4 Output → Validated PoC + stakeholder sign-off — handoff to M5 (production spec for Tech)
Milestone | M5 — Production Specification (→ handoff to Tech WS-C)
Task | Produce detailed production requirements for RPO infrastructure
Subtask | Database schema spec: multi-source RPO storage, dedup logic, backfill, audit trail
Subtask | Ingestion pipeline spec per vendor: formats, validation, error handling, retry
Subtask | RPO normaliser spec: attribute extraction, multi-source blending, degradation handling
Subtask | Counting engine spec: rolling 12-month, max-one-per-day dedup, thresholds (≥24 LH≤20d, ≥16 LH>20d)
Subtask | Classification engine spec: qual + quant → Modellable / NMRF A / NMRF B → capital routing API
Subtask | Dashboard spec: desk-level, asset-class-level, early-warning, capital simulator
Dep | Handoff → Risk Tech (WS-C) builds production infrastructure from these specifications
Dep | Handoff → Capital Tech confirms IMCC/SES engine will consume classification via API
M5 Output → Complete production specification: RPO infra, normaliser, mapping, counting, classification, dashboard → handed to Tech (WS-C)
Milestone | M6 — UAT, Final Classification & Go-Live (after Tech delivers WS-C)
Task | Test Technology's production implementation
Subtask | Define acceptance criteria: ingestion 100%, normalisation ≥99%, mapping ≥95%, counting zero-error
Subtask | Execute UAT across all asset classes: compare production vs. PoC baseline + expert review
Subtask | Stress testing: vendor failure, volume spikes, boundary-crossing scenarios
Subtask | Parallel run: new engine vs. existing process for 1+ month — reconcile
Task | Produce final RFET classification register
Subtask | Per RF: qual result + quant result → Modellable / NMRF A / NMRF B → IMCC vs. SES routing + capital impact
Subtask | Per NMRF: estimate SES charge vs. IMCC counterfactual — quantify capital cost
Task | Sign off and go live
Subtask | Production readiness sign-off: test results, known issues, remediation plan
M6 Output → Final classification register (Modellable / NMRF A / NMRF B) in production with capital routing
Milestone | M7 — BAU Process & Governance
Task | Establish RFET BAU process
Subtask | Daily: automated ingestion, classification, exception review, SLA
Subtask | Quarterly: full reclassification, prior-quarter comparison, reclassification documentation
Subtask | Trigger-based: vendor loss, liquidity event, new RF, methodology change → out-of-cycle reclassification
Subtask | Roles: Quant Data (methodology), Risk Tech (infra), Capital Tech (routing), Risk Model (governance), Market Data (vendors)
Subtask | Runbooks, escalation matrices, SLA definitions, regulatory exam checklist
Dep | Dependency: Capital Tech — reclassification triggers re-routing between IMCC and SES
M7 Output → Governed BAU process: daily ops, quarterly refresh, trigger-based reclassification, documented and audit-ready